## Slide 1: LHC BE-BI activities in EYETS 2016/17

## Slide 2: LHC BE-BI activities in EYETS 2016/17

## Slide 3
Details BLM (S. Grishin)

## Slide 4
Details BPM (Ch. Boccard)
Impact | Location | Subject | Task
85564 | 5R | Wire collimator TCTPH.4R5.B2 | cablage des BPM et du fil sur le TCTPH.4R5.B2 + tests
85558 | 5L | Wire collimator TCL.4L5.B2 | cablage des BPM et du fil sur le TCL.4L5.B2 + tests
85566 | 7L | Installation of BPM collimator TCPP.C6L7.B1 | cablage des BPM sur le TCPP.C6L7.B1 + tests
85565 | 7R | Installation of BPM collimator TCSM.D4R7.B2 | cablage des BPM sur le TCSM.D4R7.B2 + tests
85567 | 1L | Cablage du BPMSA for AFP 6L1 | cablage du BPMSA pour AFP en 6L1 + tests

## Slide 5
DOROS (M. Gasior)
DOROS activities will concern:
- Adding new DOROS electronics for the new collimators with BPMs in P7 (TCSPM and TCPP);
- Adding new DOROS electronics for the BBLR collimator in P5 (TCTW);
- Potentially upgrading DOROS installations in P1, P2, P5, P6 and P8.
The work will be just installation of electronic modules and connecting them to the beam signals, Ethernet and timing fibres.
For the new installations the estimate is two days per point and for the upgrades also two days per point.
Most of the concerned locations are UAs.