## Slide 1: 5th Steering Meeting
R. Mundt, 7.April 2017

## Slide 2: Agenda
Session: Welcome and Approval of Agenda Time and Place: Building 1, SR 1b / Convener: Ralph Wolfgang Assmann
Session: Approval of minutes from 4th Steering Meeting Time and Place: Building 1, SR 1b / Convener: Ralph Wolfgang Assmann
Session: Action Items of 4th Steering Meeting Time and Place: Building 1, SR 1b / WebEx(09:10-09:25) Convener: Ralph Wolfgang Assmann
Session: Work progress WP sessions Time and Place: Building 1, SR 1b / WebEx(09:25-11:10)
Session: Discussion Calendar Management 2017 Time and Place: Building 1, SR 1b / WebEx(11:10-11:25)
Session: AOB Time and Place: Building 1, SR 1b / Convener: Ralph Wolfgang Assmann
Adjourn

## Slide 3: Milestone-Reports 2017
12 | M2.2 Report defining tolerance | CEA | 18 | 30.04.2017 | x | x
13 | M2.3 Simulation tools and theory set up | CEA | 18 | 30.04.2017 | x | x
14 | M3.1 Design for an electron injector and a laser plasma stage proposed | CNRS | 18 | 30.04.2017 | x | x
15 | M4.2 Preliminary laser requirements table and tech survey | CNR | 18 | 30.04.2017 | x | x
16 | M7.2 Users workshop | CNRS | 18 | 30.04.2017 | x | 
17 | M6.3 Models and scaling laws for Plasma FEL dynamics | SOLEIL | 20 | 30.06.2017 | x | 
18 | M2.4 Preliminary simulations set up | CEA | 24 | 31.10.2017 |  | 
19 | M5.3 Specification of the transfer line from the RF-injector to the plasma | INFN | 24 | 31.10.2017 |  | 
20 | M3.2 Design for interaction chambers proposed | CNRS | 24 | 31.10.2017 |  | 
21 | M3.3 Design for implementation of diagnostics proposed | CNRS | 24 | 31.10.2017 |  | 
22 | M8.2 Decision for top 3 science / outreach stories | ULIV | 24 | 31.10.2017 |  | 

## Slide 4: Deliverable-Reports 2017
WP No | Del No | EU No | Title | Lead Benef. | Month | Est. Del. Date | requested | received
WP8 | D8.3 | 8 | Project initial brochure | ULIV | 15 | 31.01.2017 | x | x
WP10 | D10.1 |  | Tests are performed to extract an ultra-cold electron bunch from an alternating current magneto-optical trap | DESY | 17 | 31.03.2017 | x | x
WP2 | D2.1 | 9 | Report defining baseline design | CEA | 18 | 30.04.2017 | x | x
WP7 | D7.2 | 10 | Application survey assessment | CNRS | 18 | 30.04.2017 | x | 
WP14 | D14.1 |  | Design of an optimized plasma ionization module | USTRATH | 18 | 30.04.2017 | x | 
WP4 | D4.2 | 11 | Preliminary laser design | CNR | 24 | 31.10.2017 |  | 
WP4 | D4.3 | 12 | Preliminary design of transverse functions | CNR | 24 | 31.10.2017 |  | 
WP6 | D6.2 | 13 | Models, scaling laws Plasma FEL dynamics | SOLEIL | 24 | 31.10.2017 |  | 
WP6 | D6.3 | 14 | Diagnostic requirements and technical approaches | SOLEIL | 24 | 31.10.2017 |  | 
WP12 | D12.2 |  | Programm for tests including schedules and teams | STFC | 24 | 31.10.2017 |  | 

## Slide 5: Events 2017

## Slide 6: Events 2018

## Slide 7: Events 2019

## Slide 8: Agenda
Session: Welcome and Approval of Agenda Time and Place: Building 1, SR 1b / Convener: Ralph Wolfgang Assmann
Session: Approval of minutes from 4th Steering Meeting Time and Place: Building 1, SR 1b / Convener: Ralph Wolfgang Assmann
Session: Action Items of 4th Steering Meeting Time and Place: Building 1, SR 1b / WebEx(09:10-09:25) Convener: Ralph Wolfgang Assmann
Session: Work progress WP sessions Time and Place: Building 1, SR 1b / WebEx(09:25-11:10)
Session: Discussion Calendar Management 2017 Time and Place: Building 1, SR 1b / WebEx(11:10-11:25)
Session: AOB Time and Place: Building 1, SR 1b / Convener: Ralph Wolfgang Assmann
Adjourn