## Slide 1: ELICA (Elimination of TFA Cables)
Francesco La Torre
on behalf of the ELICA project team
EDMS No:1773038

## Slide 3: The ELICA pilot project
LS2 will require about 3000 m3 of waste storage
SHERPA can free about 2000 m3
Cable waste stored in the ISR about 1200 m3
Extremely high fire load in the ISR sectors
ELICA allows to liberate1000 m3 of space in due time for the LS2 reducing at the same time the fire load in the ISR

## Slide 5: Timeline & deliverables
ANDRA dossier for the disposal of 1000 m3 over 3 years
200 m3 of processed TFA cables ready to go
Characterization plan
Quality assurance plan
Processing plan
Validation plan
05/2016
09/2016
12/2016
Start processing
End processing
[200 m3]
Start
project
01/2016
End
project
03/2017
Drafting

## Slide 6: Resources
Name | Project Role | Engagement
F. La Torre | Project Leader, Characterization | 40% + 30%
B.A. Cellerier | Deputy Project, Operations | 20%
M. Magistris | Quality assurance, characterization | 20%
R. Michaud | Quality controls, ANDRA contacts | 10%
J. Germa | Work instructions and procedures | On request
D. Dalban | Work instructions and procedures | On request
Main budget items | Cost [kCHF]
Radiological characterization | 100
Operators | 100
Containers | 100
Transport and elimination to ANDRA | 200
TOTAL | 500
Elimination of 1 m3 ~ 2’500 CHF
Radioactive Waste Treatment Center (RWTC)
In-situ gamma spectroscopy station
Framework contracts with the CNRS, ANDRA and AMEC company
Budget

## Slide 7: Work Breakdown Structure (WBS)

## Slide 8: What really happened…

## Slide 10: Méthodologie de caractérisation

## Slide 11
Summary cable families [wt-%]* |  |  |  |  |  |  | 
Matrix | Power Al | Power Cu | Signal Cu | Coax Cu | Coax Cu+Al | Stripped | Shredded
Density (g/cm3) | 1.9 | 2.8 | 1.6 | 1.7 | 1.3 | 0.95 | 0.5
Total | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Copper | 0% | 63.8% | 47.2% | 42.5% | 31.2% | 0% | 0%
Aluminium | 53.5% | 0% | 0% | 0% | 15.4% | 0% | 0%
Outer insulation | 19.7% | 22.8% | 30.4% | 30.3% | 25.3% | 54.4% | 57.7%
Inner insulation | 26.8% | 13.4% | 22.3% | 27.3% | 28.1% | 45.6% | 42.3%
*based on 40 types of cable samples

## Slide 12: A big issue…

## Slide 13
0.5 cm

## Slide 15
Portable XRF analyzer
Niton XL3t
by Thermo

## Slide 16
Power cables (aluminium) |  |  |  |  |  |  |  |  | 
Sample | CR-049718 | CR-049719 | CR-049962 | CR-049963 |  |  |  |  | 
Pb [wt-%] | 0.52 | 1.58 | 0.38 | 0.80 |  |  |  |  | 
Power cables (copper) |  |  |  |  |  |  |  |  | 
Sample | CR-049959 | CR-049960 | CR-049961 |  |  |  |  |  | 
Pb [wt-%] | 0.03 | 0.00 | 0.002 |  |  |  |  |  | 
Signal cables (copper) |  |  |  |  |  |  |  |  | 
Sample | CR-049976 | CR-049977 | CR-049978 | CR-049979 | CR-049980 | CR-049981 | CR-049982 | CR-049983 | CR-049984
Pb [wt-%] | 1.26 | 2.27 | 2.86 | 1.24 | 0.69 | 0.50 | 0.13 | 0.85 | 0.004
Sample | CR-049985 | CR-049986 | CR-049987 | CR-049988 | CR-049989 | CR-049990 | CR-049991 | CR-049992 | 
Pb [wt-%] | 1,08 | 0 | 0,01 | 0,21 | 0,55 | 0,001 | 0,71 | 1,41 | 
Coaxial cable (copper) |  |  |  |  |  |  |  |  | 
Sample | CR-049964 | CR-049965 | CR-049966 | CR-049968 | CR-049969 | CR-049970 | CR-049971 | CR-049972 | CR-049973
Pb [wt-%] | 1,09 | 0,56 | 0,36 | 0,91 | 0,06 | 0 | 0,8 | 3,25 | 0,54
Sample | CR-049974 | CR-049975 |  |  |  |  |  |  | 
Pb [wt-%] | 1,06 | 2,82 |  |  |  |  |  |  | 
Coaxial cable (copper +aluminium) |  |  |  |  |  |  |  |  | 
Sample | CR-049720 | CR-049721 | CR-049967 |  |  |  |  |  | 
Pb [wt-%] | 0,01 | 0,409 | 0,001 |  |  |  |  |  | 
Lead content measurements for the collected cable samples. The results are given as mass fraction over the entire cable.

## Slide 17: ELICA elimination pathway

## Slide 18
1 | Program manager | Selection of elimination campaign
2 | Characterization | Campaign boundaries and batch selection (TREC info + visual inspection)
3 | Operation | Radiological info (RADOS or dose rate measurements)
4 | Characterization | Sampling definition (numbers and containers)
5 | Operation | Sample collection and traceability
6 | Characterization | Radionuclides inventory (ActiWiz calculations) and shipping for gamma spectroscopy and radiochemical
7 | Operation | Cable sorting and packaging + in situ gamma spectroscopy of packages
8 | Characterization | Scaling factors and IRAS calculations
9 | Operation | Quality controls on cable containers
10 | Characterization | Quality controls on calculations and IRAS values + communications to ANDRA
11 | Operation | Shipping of cable containers

## Slide 19: Lessons learned

## Slide 20
Increased project effort with a cut of resources
Dos
Don’ts
Project manager with other tasks in the same project
Consultant support with no CERN experience
Underestimation of the required info (physical, chemical)
ANDRA and AMEC framework contracts
Project support from the RP management
Team with many years of RW experience at CERN!
Approved project charter

## Slide 21: Summary (24/03/2017)
Pre-treatment:
452 metallic baskets of cables
ISR occupied volume: ~ 452 m3
Average density: 0.47
Post-treatment:
192 ANDRA container
Total volume: 249.6 m3
Average density: 0.85
211 tons of processed cables
112 containers shipped to ANDRA
348 m3 of space freed at ISR

## Slide 22
03/2016

## Slide 23
03/2017

## Slide 24: Thank you
Luca Bruno
Bertand Cellerier
Matteo Magistris
Regis Michaud
Luisa Ulrici
Nick Walter

## Slide 25: Backup slides

## Slide 26
Planned |  | Actual | 
Deliverable | Date | Deliverable | Date
Dossier for the disposal of 1000 m3 of historical TFA cables (2016 – 2018) | Draft: 05/2016 Approval: 09/2016 | Dossier for the disposal of 2110 m3 of historical and future TFA cables (2016-2023) | Draft: 06/2016 Final: 01/2017
200 m3 of processed TFA cables ready to go | January 2017 | 200 m3 of processed TFA cables ready to go | November 2016
Characterization plan for historical TFA cables | Draft: 05/2016 | Characterization plan for historical and future TFA cables | Draft: 05/2016 Final: 06/2016
Quality assurance plan | Draft: 05/2016 | Quality assurance plan | - -
Processing plan | Draft: 05/2016 | Processing plan | Draft: 10/2016
Validation plan | Draft: 05/2016 | Validation plan | Draft: 10/2016
Planned cost per m3 | Actual cost per m3
2500 CHF | 2443 CHF

## Slide 27
R < 0.5
Spectrométrie gamma
Analyse de radiochimie (principaux radionucléides difficiles à mesurer)
“Echantillons primaires” des colis les plus radioactives du lot
IRAS
IRAS < 0.5
et
Ai < LDFi
Application d’une activité massique forfaitaire à l’ensemble des colis (même famille)
Mesures de débit de dose sur chaque colis constitué
IRAS > 0.5
et/ou
Ai > LDFi
Analyse statistique de ratios émetteur beta/traceur (coefficient de corrélation R)
Méthode des ratios (facteurs de correlation)
Moyenne arithmétique + 2σ des résultats des échantillons
Control qualité
Spectrométries gamma in situ et calcul de l’IRAS sur chaque colis constitué
R > 0.5
Calculs analytiques (radionuclides en presence)
Determination des colis les plus radioactifs (Debit de dose ou RADOS)
Echantillonnage par famille des câbles
Ratios analytiques (autres radionucléides difficiles à mesurer)
Control qualité