## Slide 1: RW master Planning
Infrastructure steering board,
6th April 2017
L. Ulrici for the RP group

## Slide 2: Eliminations
2016 S2 | 2017 S1 | 2017 S2 | 2018 S1 | 2018 S2 | 2019 S1 | 2019 S2 | 2020 S1 | 2020 S2 | 2021 S1 | 2021 S2
Milestone planned
Deadline
Period Planned
ELICA
800 m3
SHERPA «standard» («plan B»)
600 m3
Containment enclosure
SHERPA (with containment enclosure)
300 m3
Study/pilot
2000 m3
CLEAR
Asbestos facility (SMB)
SHERPA «asbestos» after treatment in SMB facility
220 m3
INCA
150 m3
Tritiated water
200 m3
Magnets
40 m3
preparation
elimination from rad. mat. storage & ISR
40 m3
400 m3
400 m3
Ventilation Filters (Clearance)
220 m3
150 m3
300 m3
150 m3
40 m3
40 m3
Pilot project 10 m3
preparation
LEP Vacuum chambers (Pb)
110 m3
Magnets
Ventilation Filters
Volumes are expressed as gross volume in the temporary storage before treatment
m3
220 m3
Treatment in SMB facility
Moved forward w.r.t. previous planning
Faster w.r.t. previous planning
Faster w.r.t. previous planning
Defined w.r.t. previous planning
Postponed w.r.t. previous planning
Defined w.r.t. previous planning
Volumes depend on location of evaporation

## Slide 3: Planning 2017-2018
Type | Category (Destination) | Total Volumes (m3) | Volumes foreseen 2017 (m3) | Volumes foreseen 2018 (m3)
Cables (ELICA) | TFA (F) | 1000 | 680 1000 | 320
Metallic waste (SHERPA) | TFA (F) | 200 | 50 | 150 50
Burnable waste (INCA) | CL (CH) | 190 | 150 | 40
LEP modules (CLEAR) | TFA (F) CL (CH) | 2000 | 950 2000 | 1050
Tritiated water | CL (CH) | 140 | 70 | 70
TOTAL |  | 3330 | 1900 | 1410
Magnets | TFA (F) |  | 25-100 10 | 75-150
Isolde targets | FMA(CH) |  |  | 40
Ventilation filters | TFA(F) CL(CH) |  |  | 500 220
LEP vacuum chambers | TFA (F) | 110 |  | 110
Notes: This is what is eliminated. More work goes into the RWTC to prepare the batches before elimination or as “plan B”
Magnets are waiting for ANDRA confirmation of the dossier, and Isolde targets is waiting from EN-STI confirmation on planning of the hot cell use.

## Slide 4: Storage tunnel - Periods of availability
The ISR will be available by ½ octants for one semester.
Within the semester, the floor would be available by ¼ octant.
Walls/ceiling will be available for the whole semester.
2022 S2
2018 S2
2017 S1
2022 S1
2016 S2
2021 S1
2015 S2
2020 S1
ISR 2R
ISR 3L
ISR 6L
ISR 3R
ISR 5R
ISR 5L
ISR 6R
ISR 7R
ISR 7L
2015 S2
o n - g o i n g
Availability
Could be anticipated to S2 2019

## Slide 5: Conditions for the availability
S2 2022
S2 2018
S1 2017
S1 2022
S2 2016
S1 2021
2015
S1 2020
ISR 2R
ISR 3L
ISR 6L
ISR 3R
ISR 5R
ISR 5L
ISR6R
ISR 7R
ISR 7L
2015
Storage of LS2 rad. Waste.
Move of - tritiated water to B.573
- Magnets >8t to ISR 5.
- Comb. RW to B.225
Cont.enclosure by S1 2019.
Elimination of cables and combustible RW.
Move of residual combustible RW to B.225
Dismantling of old shielded area.
Storage of not-stackable RW (pallets).
No floor access (shielded areas for highly rad. waste).
Elimin. of . LEP Cavities, . Pb chamb. . asbest. RW
B.225 refurb. with sprinkler by S1 2018 (to be discussed).
Floor waterproof. before sh. area extension
B.573 refurb. by S2 2017
Contain. enclosure by S2 2018
B.225 refurb. by S1 2018
Evaporation in B.573 by end of S2 2017
Possibility to keep racks in place to be studied.
Asbestos facility avail. By S1 2018
Floor waterpr. compatible with the existing sh. area.
HSE-RP
SMB
Conditions
o n - g o i n g
Civil eng. work and HVAC possible before S2 2018. Elec., fire det., access ctrl, waterproof.
painting in S2 2018.
Waterpr. partially possible after ISR6 sh. extension.
Elec., IT & painting ongoing. All other work in 2017. HVAC in 2018.
Civil eng. work and HVAC
possible before S2 2022.
Waterprof. in S1 2018.
Elec., fire det., access ctrl,
waterproof. & painting in
S1 & S2 2022.
Civil eng. work possible in 2017. HVAC in 2018.
CE work
possible in 2017.
HVAC in 2018. Remaining works in S1
2020. .
Floor waterpr.
and all remaining
work possible in 2017.
HVAC in 2018.
INFRASTR.
Remarks
Could be anticipated to S2 2019
EDMS 1783548 v.1