## Slide 1: SPS Test-stand Integration
G.Vandoni
International Review of the Crab-Cavity Performance for HiLumi April 2017

## Slide 2: Cryogenic refrigeration & distribution
PA6 - shaft
BA6 – surface area
TA6 - alcove
CC SPS test stand
COLD-BOX
Cryogenic Tanks
Cryogenic compressor
He
N2
Valve-box 1
Warm pipework CRG
LN2 insulated lines
Valve-box 2

## Slide 3: HL-LHC CrabCavity SPS test stand
Transport lane
Cryo-module
Transfer table
Valve-box2
Service box
RF power, loads & circulators
Y-chamber + VVS valves

## Slide 4: WP4 Planning
SPS prototype beam tests
preparation
SPS Test (CM1)
SPS Test (CM2)
TS-bound activities
Run 2
2015
2016
2017
2018
2019
2020
2021
2022
2023
2024
2025
2026
LS2
LS3
EYETS
Run 3
Run 4
YETS
YETS
Test run
(E)YETS=(Extended) Year-End Technical Stop

## Slide 5: EYETS goals and achievements
12.4 weeks
Objective | 
Cable (211, 20km) | 80%
Cryo distribution line | 
3 rails (4 tons CMU) | 
Vacuum sectorization | 
Civil engineering | 
RF power lines | 
Water pipework | 
Warm cryo pipework | 75%
He pumps | 
Survey | 
3D scan new configuration | 

## Slide 6: From EYETS to YETS
CRYO
Service Box, ValveBoxes, precommissioning at warm
Installation of GHe and LN2 tanks
INFRASTR.
Installation of power equipment, connections and commissioning
Construction of 3 slabs for cryogenic tanks and transformer
False floor of Faraday cage
BE/RF
Installation of RF power equipment, connections and commissioning
BA6 SURFACE BUILDING
Tendering
Production
assembly
LLRF
!
Faraday cage for LLRF

## Slide 7: A challenging YETS
9 weeks
23/2
9

## Slide 8: YETS detailed planning