## Sheet1
|  |  | DECEMBER | [13 empty] | JANUARY | [30 empty] | FEBRUARY | [27 empty] | MARCH
|  | Calendar | [91 empty] | EN/MME | time axis 2017-12-18 to 2018-03-18
|  |  | 51 | [6 empty] | 52 | [6 empty] | 1 | [6 empty] | 2 | [6 empty] | 3 | [6 empty] | 4 | [6 empty] | 5 | [6 empty] | 6 | [6 empty] | 7 | [6 empty] | 8 | [6 empty] | 9 | [6 empty] | 10 | [6 empty] | 11
YETS | access | 8 weeks | 2017-12-23: Christmas break
| cold check-out | 3 weeks | [91 empty] | TE/CRG | bar: 2018-02-26 to 2018-03-02; 2018-03-05 to 2018-03-09; 2018-03-12 to 2018-03-16
BE/RF
Transfer table installation | installation & test | 1 week | bar: 2017-12-18 to 2017-12-22; 2018-01-08 to 2018-01-10
TE/VSC
Installation of RF equipment on the table | installation and fixation | 2 days | [91 empty] | EN/ACE | bar: 2018-01-11 to 2018-01-12
| connection | 1 day | bar: 2018-01-15
| connections validation | 2 days | bar: 2018-01-16 to 2018-01-17
Installation of Service Module, Cryomodule | installation Service Module | 1 day | bar: 2018-01-18
| installation cryomodule | 1 day | bar: 2018-01-19
| leak detection on beam vacuum via plug-valves | 1 day | bar: 2018-01-22
| welding of internal lines with CM and VB | 2 days | bar: 2018-01-23 to 2018-01-24
| leak test | 1 day | bar: 2018-01-25
| insulation & welding of interconnex ext envelope | 2 days | bar: 2018-01-26; 2018-01-29
| vacuum pumping | 2 days | bar: 2018-01-30 to 2018-01-31
| leak test under vacuum | 1 day | bar: 2018-02-01
Alignment and survey | alignment and survey | 2 days | bar: 2018-02-02; 2018-02-05
RF connections | RF connections to the cryomodule | 2 days | bar: 2018-02-06
| RF connections validations | 3 days | bar: 2018-02-07 to 2018-02-09
Electrical connections | Electrical connections and validations | 3 days | bar: 2018-01-30 to 2018-02-01; 2018-02-07 to 2018-02-09
Cryogenic refrigeration, TA6 | installation cold box | 2 day | bar: 2018-01-17 to 2018-01-18
Cryogenic refrigeration, BA6 | installation skid 1 | 1 day | bar: 2018-01-17
| installation skid 2 | 1 day | bar: 2018-01-18
Cryogenic distribution, TA6 and tunnel | installation valve box 1 | 1 day | bar: 2018-01-08
| installation valve box 2 | 1 day | bar: 2018-01-09
| welding | 3 days | bar: 2018-01-10 to 2018-01-12
| distribution validated | 1 day | bar: 2018-01-15
Connection refrigeration + distribution | hydraulic connections BA6, TA6 | 6 days | bar: 2018-01-19; 2018-01-22 to 2018-01-26
| electrical connections & validation | 4 days | bar: 2018-01-29 to 2018-02-01
Cryogenics ready for commissioning
Vacuum | VAC chambers installation, alignment, connection | 12 days | bar: 2018-01-22 to 2018-01-26; 2018-01-29 to 2018-02-02; 2018-02-05 to 2018-02-06
| pumpdown | 3+3 days | bar: 2018-01-31 to 2018-02-02; 2018-02-07 to 2018-02-09
| leak detection | 1 day | bar: 2018-02-09
| Cryogenic system commissioning | 15 days | bar: 2018-02-02; 2018-02-05 to 2018-02-09; 2018-02-12 to 2018-02-20
Cryomodule | cooldown and commissioning | 14 days | bar: 2018-02-21 to 2018-03-06
Vacuum validation cryomodule | Leak test, with access | 1 day
Interlocks check | check of functionality of interlocks | 2 days | bar: 2018-03-07 to 2018-03-08