## Slide 2: HIE-ISOLDE Beam Properties and Beam Commissioning
Jose Alberto Rodriguez on behalf of BE-OP-ISO and the HIE-ISOLDE project team

## Slide 3
Outline:
Introduction
Beam Properties
Beam Commissioning
First Beam to Users
Users/Machine Interface
Summary
J.A. Rodriguez – 79th ISOLDE Collaboration Committee Meeting – Jun. 27th 2017

## Slide 4
Phase 2A HIE-ISOLDE project:
Additional cryomodule (CM3)
Additional HEBT line (XT03)
Modification of the XT02 HEBT line
Introduction:
End Tunnel
Layout after Phase 2A
XT02 extension (2017)
XT03 (2017)
Phase | 1A | 1B | 2A | 2B
Completion in: | 2015 | 2016 | 2017 | 2018
# cryomodules | 1 | 2 | 3 | 4
# HEBT lines | 2 | 2 | 3 | 3
Emax [MeV/u] (A/q = 2.5) | 5.6 | 8.6 | 11.5 | 14.2
Emax [MeV/u] (A/q = 4.33) | 4.4 | 6.1 | 7.9 | 9.6
Phases of the HIE-ISOLDE project
CM1
CM2
CM3 (2017)
J.A. Rodriguez – 79th ISOLDE Collaboration Committee Meeting – Jun. 27th 2017

## Slide 5
Outline:
Introduction
Beam Properties
Beam Commissioning
First Beam to Users
Users/Machine Interface
Summary
J.A. Rodriguez – 79th ISOLDE Collaboration Committee Meeting – Jun. 27th 2017

## Slide 6
Beam Properties: A/q
J.A. Rodriguez – 79th ISOLDE Collaboration Committee Meeting – Jun. 27th 2017
Since 2016:
Nominal minimum: A/q > 2.5
Nominal maximum: A/q < 4.33
Several REX amplifiers not reliable at the power levels needed for beams with A/q = 4.5
Impact of the change in specs is limited (needs to be analyzed case by case):
  Some light beams are not possible (ex: 9Li2+)
  Charge breeding efficiency for some heavy beams could become lower (by a factor 2-4)
Before 2016:
Nominal minimum: A/q > 2.5
Nominal maximum: A/q < 4.5

## Slide 7
Beam Properties: Time Structure
J.A. Rodriguez – 79th ISOLDE Collaboration Committee Meeting – Jun. 27th 2017
Expected for 2017:
Repetition rate: up to 50 Hz
RF Pulse length 2 ms  Beam Pulse Length ~ 1.7 ms
  Heat exchangers installed during the technical stop
  Bertronix was at CERN on wk. 7 and make the necessary modifications
Average power in 9gap < 2.5 kW
Spokesperson should inform OP if slow extraction is needed in advance (typically, a couple of hours are needed to set it up)
In 2016:
Repetition rate: up to 50 Hz
RF Pulse length: up to 1 ms  Beam Pulse Length ~ 0.7 ms (with slow extraction)
Average power in 9gap < 2.5 kW

## Slide 8
Beam Properties: Energy and Energy Spread
In 2016:
Two cryomodules installed
Dedicated energy measurement (~ 4 hours needed)
Chart: A/q
| 2.5 | 3 | 3.5 | 4 | 4.33 | 4.5
CM4 | 14.173 | 12.389 | 11.074 | 10.064 | 9.517 | 9.264
CM3 | 11.449 | 10.042 | 9.013 | 8.228 | 7.805 | 7.611
CM2 | 8.557 | 7.577 | 6.869 | 6.336 | 6.051 | 5.92
CM1 | 5.525 | 5.042 | 4.701 | 4.447 | 4.313 | 4.252
Highest beam energy (assuming all cavities at 6MV/m) for different A/q
1 mm vertical slits
All quads and steerers off
Silicon detector
J.A. Rodriguez – 79th ISOLDE Collaboration Committee Meeting – Jun. 27th 2017
In 2017:
Three cryomodules installed
A new timing class for the time information of the Si detectors has been developed and commissioned
Dedicated energy measurement (~ 1 hour needed)
Energy spread optimization may be possible (needs to be requested in advance)
Chart: A/q
| 2.5 | 3 | 3.5 | 4 | 4.33
6.0 MV/m | 11.4493 | 10.0424 | 9.0131 | 8.2282 | 7.8052
5.5 MV/m | 10.7509 | 9.4444 | 8.491 | 7.7656 | 7.3754
5.0 MV/m | 10.0424 | 8.8396 | 7.9642 | 7.3 | 6.9404
4.5 MV/m | 9.324 | 8.2282 | 7.4333 | 6.8318 | 6.507
4.0 MV/m | 8.5958 | 7.6107 | 6.8988 | 6.362 | 6.0751
Highest beam energy for average gradients

## Slide 9
Outline:
Introduction
Beam Properties
Beam Commissioning
First Beam to Users
Users/Machine Interface
Summary
J.A. Rodriguez – 79th ISOLDE Collaboration Committee Meeting – Jun. 27th 2017

## Slide 10
Triplet
IHS
RFQ
Buncher
7gap 1
7gap 2
7gap 3
9gap
Triplet
Triplet
Triplet
Triplet
Triplet
Doublet
HV Steerer
Diagnostics
Diagnostics
Beam Commissioning: Si detector at XLN2
Silicon detector at XLN2 used during the beam commissioning campaigns in 2016 and 2017
A 1 mm diameter collimator normally used in combination with the Si detector
Measurements with the collimator masking different areas of the detector carried out
Energy and energy spread with collimator at different locations
XLN2 Diagnostics Box
Signs of degradation of the Silicon detector at XLN2 observed:
  Energy spread artificially increased
  Offset in absolute energy measurement
J.A. Rodriguez – 79th ISOLDE Collaboration Committee Meeting – Jun. 27th 2017

## Slide 11
Beam Commissioning: Count Rate
New low-level controls (FESA class) Time Of Flight partially commissioned (channel settings and particle count rate)
Commissioning of the bunch time structure still pending
High-level application to use the Si detectors as very low current FC commissioned
Beam Intensity during a beam energy measurement
Measurement of the low-frequency jitter in energy of the beam
J.A. Rodriguez – 79th ISOLDE Collaboration Committee Meeting – Jun. 27th 2017

## Slide 12
The method works very well
  Can be used for low-intensity beams
  Can be completed in ~ 1 hour
  However, as with all measurements with Si detectors, special attention is required to avoid damaging it
We will need to consider installing them in the other two HEBT lines next year
1 mm vertical slits
All quads and steerers off
Silicon detector
Beam Commissioning: Energy Scan
Energy and energy spread of the beam can be carried out using the count rate measured at the Silicon detector at XT01.0400 after the first dipole magnet
Energy Scan after set-up of 7gap3 was completed
Energy Scan after set-up of 9gap was completed
J.A. Rodriguez – 79th ISOLDE Collaboration Committee Meeting – Jun. 27th 2017

## Slide 13
Unexpected behaviour observed:
  Occasionally not second zero-crossing
  Needed beam attenuation varies by several orders of magnitude from cavity to cavity
  Distance between zero-crossing phases not always 180 deg
Additional work needed to understand the sources of the issues observed
1 mm vertical slits
All quads and steerers off
Silicon detector
Beam Commissioning: Phase Scan
Phase Scan can be carried out using the count rate measured at the Silicon detector at XT01.0400 after the first dipole magnet
Fine Phase Scan to find the bunching zero-crossing of SRF02
Rough Phase Scan to find the bunching zero-crossing of SRF02
J.A. Rodriguez – 79th ISOLDE Collaboration Committee Meeting – Jun. 27th 2017

## Slide 14
10 mm vertical slit collimator
Faraday Cup
Beam Commissioning: Phase Scan
Phase Scan can also be carried out using the XT01.0400 FC after the first dipole magnet
  Due to the beam low current, focussing elements cannot be turned off and only one slit (10 mm) before the FC can be used
  Injection to the dipole on axis is not guaranteed
Rough Phase Scan to find the zero-crossings of SRF05
Fine Phase Scan to find the bunching zero-crossing of SRF05
Even though the measurements of the zero-crossing phases are less precise, they are a lot faster and less risky (Si detector can be damaged)  At this point, it is the preferred method to phase the cavities
J.A. Rodriguez – 79th ISOLDE Collaboration Committee Meeting – Jun. 27th 2017

## Slide 15
Beam Commissioning: Low Energy Beams
Tunes for beams with A/q = 3.5 to the end of XT01 after each REX RF structure was set-up
Precise energy measurement using the dipole for each tune
Transverse beam profiles at each diagnostics box measured (data not yet analysed)
Conclusions:
Low-energy beams can be transported without additional losses
Beam losses in HIE-ISOLDE (ie. XLN2 to end of XT01) negligible or at the very least small
Differences between different types of FC noticeable
J.A. Rodriguez – 79th ISOLDE Collaboration Committee Meeting – Jun. 27th 2017

## Slide 16
Beam Commissioning: Plan
Week 26:
Phasing of cavities in CM2 and CM3 with 14N4+ (Efinal = 6.6 MeV/u)
Scaling to A/q = 3.67 and 4.0
REX-TRAP and REX-EBIS synchronization with 39K from the pilot ion source
Scaling to A/q = 3.9
Week 27-28:
Set-up for first RIB and Physics
Week 29:
Scaling to A/q = 4.33
Week 30-32:
Set-up and Physics
Week 33:
First beam to XT03
Commissioning of all diagnostics devices
Commissioning of the stripping foils
J.A. Rodriguez – 79th ISOLDE Collaboration Committee Meeting – Jun. 27th 2017

## Slide 17
Outline:
Introduction
Beam Properties
Beam Commissioning
First Beam to Users
Users/Machine Interface
Summary
J.A. Rodriguez – 79th ISOLDE Collaboration Committee Meeting – Jun. 27th 2017

## Slide 18
First Beam to Users:
22Ne beam requested by Miniball users for testing and calibration last weekend
RF structure | REX |  | HIE | 
 | RFQ | 7GP3 | SRF02 | SRF04
# Trips | 1 | 3 | 2 | 8
Downtime [mins] | 15 | 0 | 10 | 40
Downtime [%] | 0.4 | 0 | 0.3 | 1.1
Ion | 22Ne6+
A/q | 3.667
HEBT | XT01
Transmission | ~ 72 %
E | 3.955 MeV/u
dEFWHM | 0.25 %
Length | ~ 60 hours
Rep. rate | 20 Hz
Both REX and the SRF cavities quite stable (1.5 trip/shift)
Cavity | E [MV/m]
SRF01 | 4.14
SRF02 | 4.14
SRF03 | 4.14
SRF04 | 4.14
SRF05 | 3.22
Cavity | Pf [kW]
RFQ | 32.8
Buncher | 1.45
IH | 38.0
7GP1 | 51.0
7GP2 | 50.2
7GP3 | 46.2
9GP | 61.5
However, note that 40% extra power will be needed at REX for beams with A/q = 4.33 and that the gradient of the SRF cavities was not pushed to 6 MV/m
J.A. Rodriguez – 79th ISOLDE Collaboration Committee Meeting – Jun. 27th 2017

## Slide 19
Outline:
Introduction
Beam Properties
Beam Commissioning
First Beam to Users
Users/Machine Interface
Summary
J.A. Rodriguez – 79th ISOLDE Collaboration Committee Meeting – Jun. 27th 2017

## Slide 20
Users/Machine Interface:
Vacuum:
Vacuum in experimental station of 10-6 mbar required before beam is delivered
Valves between HEBT lines and the experimental station need to be closed before a mechanical intervention takes place on the experiment side
Users need to be granted access to open/close last valve in the HEBT line (NICE usernames need to be provided at least a week in advance)
Visual sign with the status of the valve needs to be checked
ISOLDE low energy
REX
Usernames:
ISOLDE low energy: isoop
REX: rexop
HIE-ISOLDE: user’s NICE
HIE-ISOLDE
J.A. Rodriguez – 79th ISOLDE Collaboration Committee Meeting – Jun. 27th 2017

## Slide 21
Users/Machine Interface:
REX RF:
All 7 RF Systems need to be working to reach energies higher than 2.8 MeV/u
Working Set: REX/HIE LINAC > Linac: RF
All REX RF systems ok
9GAP Structure down
REX RF amplifiers need to be restarted locally (amplifier room)
Users trained to restart RFQ, 7GAP1, 7GAP2 and 7GAP3. Procedure can be found in RF amplifier room
For the IHS, contact Engineer in Charge if standard procedure fails more than three times
Procedure for the 9GAP not standard. Generally, the Engineer in Charge will need to be contacted
J.A. Rodriguez – 79th ISOLDE Collaboration Committee Meeting – Jun. 27th 2017

## Slide 22
Users/Machine Interface:
HIE-ISOLDE RF:
Generally not all SRF cavities will be used for a given experiment (OFF = not used)
Those that trip (STANDBY or READY) need to be restarted by users (up to 3 times in a row)
It takes a couple of minutes to complete the start sequence after the ON button is pressed
Start sequence can be followed in Detail Status (message to logbook in restart not successful)
Cavity Status at STANDBY or at READY after a trip happens
XLH3 (a.k.a. CM4) not available until 2018
All cavities in XLL2 (a.k.a. CM1) up and running in this example
Cavities in XLH1 and XLH2 available, but not used in this example
Cavity gradient
Status information (particularly relevant during start sequence
J.A. Rodriguez – 79th ISOLDE Collaboration Committee Meeting – Jun. 27th 2017

## Slide 23
Users/Machine Interface:
Injection into Experimental Station:
Operations will only deliver beam to the last diagnostics box of the HEBT line
Users are responsible for injection into their experimental station
Quadrupole Triplet
Diagnostics box
X-Y Steerer
Beam stop controls
FCs and active collimators in the experimental stations
Equipment array to steer and/or focus the beam
Version for users of the diagnostics application
Beam stop will be included in diagnostics application
Contact OP to add your FCs and active collimators to the application
Collimators (20, 10, 5, 2 mm diameters)
Beam profile scanner
Faraday cup
J.A. Rodriguez – 79th ISOLDE Collaboration Committee Meeting – Jun. 27th 2017

## Slide 24
Summary:
Beam Commissioning:
  Low energy tunes to the end of XT01 prepared (80% transmission)
  Cavities in CM1 phased
  New low and high level controls tested:
    TOF FESA class
    Count Rate application
    Energy Scan application
    Phase Scan application
  Phasing of SRF cavities in CM2 and CM3 and scaling to A/q = 4 on-going
  Commissioning of XT03 on week 33
Beam Properties:
  2.5 < A/q < 4.33
  0.1 ms < Pulse Length < 1.7 ms (needs to be requested in advance)
  Repetition rate < 50 Hz
  Energy and Energy Spread will be measured for each experiment
J.A. Rodriguez – 79th ISOLDE Collaboration Committee Meeting – Jun. 27th 2017