## Slide 1: CERN-MEDICIS Status and plans for 2017
Thierry Stora – ISCC 27th June 2017
Acknowledgements : S. Marzari, A. P. Bernardes, K. Kershaw, R. Catherall, J. Vollaire, S. Prodon, K. Johnston, U. Koster

## Slide 2
New radioisotopes in medicine
F. Bucchegger et al.
SPECT/CT
177Lu
C. Muller et al.
jnumed.112.107540v1
Sept 2015

## Slide 3: CERN-MEDICIS Principle: Isotope production in the HRS beam dump and mass separation in the lab
spallation
fragmentation
fission
1.4 GeV protons
1000+ isotopes of 70+
chemical elements

## Slide 4
Groundbreaking ceremony
3rd September 2013
Building reception
15th October 2014
Installation of beamline and laboratory: ongoing
MEDICIS
Laboratory
MEDICIS
Target
Irradiation
Rail
Conveyor
System
The facility today and the remaining Work Packages
Commissioning & start-up end 2017 *
*Pending budget, management and safety clearance

## Slide 5: From the last project review : Phase I + Phase II EDMS 1572421
1 collection point
Standard target design
Standard beam instrument box
Laboratory with reduced equipment
Phase II
(3 collections, BI, target, lab)

## Slide 6
Some milestones
Magnet from Leuven refurbished
Ventilation and cooling
Remote handling : Robot + Rail Conveyor
Personal Protection System (PPS):
Commissioned last week

## Slide 7
Detailled planning review

## Slide 8
Starting-up:
    Stable commissioning in September
    Start with low isotope activities irradiated at CERN and at ILL (169Er) in October/November.
    Meeting soon to clarify Collab budget + start-up
Tentative commissioning & operation planning

## Slide 9: Safety clearance
Descriptive and draft demonstrative parts of the safety file has been handed over and comments received.
Request to visit by OFSP, the Swiss authorities, for end of August/beginning of September.

## Slide 10
Dr. Forni (Clin. Carouge, Geneve)
Prof. Morel, Prof. Buehler, Prof. Ratib* (HCUGE, Geneve)
Prof. R. Jolivet ( CERN/UNIGE, Geneve )
Prof. D. Hanahan (ISREC, EPFL, Lausanne)
Prof. J. Prior (CHUV, Lausanne)
Prof M. Huyse, prof. P. van Duppen, prof. T. Cocolios (KUL, Univ. Leuven)
Prof. S. Lahiri (SINP, Kolkata)
Prof. A. Goncalves, Prof. A. Raucho (CT2N, Lisbon)
Prof. F. Haddad (ARRONAX)
Dr. F. Bruchertseifer, Dr. A. Morgenstern (JRC-ITU, Karlsruhe)
Prof. S. Judge, Prof P. Regan, (National Physical Laboratory, Surrey)
Dr. N. Vd Meulen,Dr. C. Mueller (Paul Scherrer Institut, Villingen)
Dr. U. Koester (ILL, Grenoble)
Prof. Siem (Univ. Oslo)
Prof. Wendt (Univ. Mainz)
FABIS (if grant)
EANM (under discussion)
ISOLDE GL (ex-officio)
CERN-MEDICIS partners

## Slide 11
Thank you
See you at 4pm for the visit

## Slide 12: RESERVE

## Slide 13: Phase II : New systems
3 collection points:
Electrostatic switchyard
Beam diagnotic box

## Slide 14: Phase II : remaining work packages
Total: 0.6MCHF
Presently not available
Pending decision from ATS sector management
Table edited from detailled discussions with WP holders
Included in Management Report EDMS 1572421
In circulation next week

## Slide 15: Phase I : Planning
Work Package/Planning | 16-I | 16-II | 16-III | 16-IV | 17-I | 17-II | 17-III | 17-IV
PHASE I |  |  |  |  |  |  |  | 
Ventilation |  |  |  | DSO t |  |  |  | 
Safety alarm systems |  |  |  |  |  |  |  | 
RP monitoring |  |  |  |  |  |  |  | 
Shielding, air locks |  |  |  |  |  |  |  | 
Access/interlock |  |  |  |  |  |  |  | 
Safety file |  |  | File | Review | Permit |  |  | 
Power converters |  |  |  | * |  |  |  | 
Cooling |  |  |  |  |  |  |  | 
Magnet |  |  |  |  |  |  |  | 
Target |  |  |  |  |  |  |  | 
Front End |  |  |  |  |  |  |  | 
Collection box |  |  |  |  |  |  |  | 
Beam Instr box |  | standard |  |  |  |  |  | 
Separator control |  |  |  |  |  |  |  | 
Vacuum |  |  |  |  |  |  |  | 
Lab equipment |  |  |  |  |  |  |  | 
Commissioning |  |  |  |  |  |  |  | 
Operation |  |  |  |  |  | Phase I |  | 
* Synergy with ELENA project
Table edited
from detailled discussions
with WP holders
Included in Management
Report EDMS 1572421
In circulation next week for
approval by GLs