## Slide 1: CREAM deployment Update on the deployment in production
Antonio Retico
Grid Deployment Board 2-Dec-09 - CERN

## Slide 2: Agenda
CREAM in the production system
Plans for the next month
Good afternoon!

## Slide 3: Monitoring
SAM tests available
  Problems followed-up “manually” with GGUS by Central Operators on Duty
~3/4 of the nodes now passing the tests
  Next step: enable alarms
  On the to-do list of SA1 these days

## Slide 4: MB milestones for CREAM CE (From GDB 10th Jun)
  June 1st:
  All European T1 + TRIUMF and CERN; at least 1 CREAM CE each.
  5 T2s supporting ALICE with 1 CREAM CE each
  August 1st:
  At least 2 T2s for each experiment providing 1 CREAM CE each
  October 1st:
  50 sites providing CREAM CEs in addition to the ones above

## Slide 5: CREAM in production (data 2-Dec-09)
Scope | # Sites |  | T1 |  | T2 |  | # Nodes |  | T1 |  | T2 |  | Notes
All PROD | 34 | (+7) | 8 | (+1) | 28 | (+3) | 43 | (+1) | 15 | (-1) | 28 | (+2) | 
CMS | 16 | (+2) | 5 | (=) | 11 | (+2) | 17 | (-2) | 6 | (-3) | 11 | (+1) | 
ALICE | 26 | (=) | 7 | (+2) | 19 | (-2) | 28 | (-3) | 9 | (=) | 19 | (-3) | 13 sites usable with VOBOX (=)
LHCb | 18 | (+3) | 6 | (+2) | 12 | (+1) | 22 | (=) | 10 | (+1) | 12 | (-1) | 
ATLAS | 22 | (+2) | 6 | (+1) | 16 | (+4) | 24 | (+1) | 8 | (-2) | 16 | (+3) | 
OPS | 38 | (+2) | 9 | (+1) | 28 | (+1) | 39 | (+1) | 12 | (-2) | 28 | (+3) | 
(n): difference wrt to last sampling) |  |  |  |  |  |  |  |  |  |  |  |  | 
N: less then expected by MB |  |  |  |  |  |  |  |  |  |  |  |  | 
N: equals or more than expected by MB |  |  |  |  |  |  |  |  |  |  |  |  | 
GlueCEStateStatus |  |  |  |  |  |  |  |  |  |  |  |  | 
Production |  | 36 (+20) |  |  |  |  |  |  |  |  |  |  | 
Special |  | 6 (-16) |  |  |  |  |  |  |  |  |  |  | 
Other |  | 0 (-4) |  |  |  |  |  |  |  |  |  |  | 

## Slide 6: Plans
More CREAM service in the infrastructure
  With Status= “Production”
Deployment of alarms and a/r metrics
Deploy CREAM on SL5
  Early Adopters Needed

## Slide 7: Questions?
?