## Slide 2: HIE-ISOLDE Report
Jose Alberto Rodriguez on behalf of Yacine Kadi and the HIE-ISOLDE project team

## Slide 3
Outline:
HIE-ISOLDE Phase 2A
Installation
Highlights of the Commissioning
First Operation with Stable Beam
Status and Schedule for Phase 2B
Summary
56th Meeting of the INTC – Jun. 28th 2017

## Slide 4
HIE-ISOLDE Phase 2A:
56th Meeting of the INTC – Jun. 28th 2017
CM3 and XT00 modifications
XT03
XT02 extension and ISS
Phase 2A HIE-ISOLDE project:
Additional cryomodule (CM3)
Additional HEBT line (XT03)
Modification of the XT02 HEBT line
Chart: A/q
| 2.5 | 3 | 3.5 | 4 | 4.33
6.0 MV/m | 11.4493 | 10.0424 | 9.0131 | 8.2282 | 7.8052
5.5 MV/m | 10.7509 | 9.4444 | 8.491 | 7.7656 | 7.3754
5.0 MV/m | 10.0424 | 8.8396 | 7.9642 | 7.3 | 6.9404
4.5 MV/m | 9.324 | 8.2282 | 7.4333 | 6.8318 | 6.507
4.0 MV/m | 8.5958 | 7.6107 | 6.8988 | 6.362 | 6.0751

## Slide 5
Outline:
HIE-ISOLDE Phase 2A
Installation
Highlights of the Commissioning
First Operation with Stable Beam
Status and Schedule for Phase 2B
Summary
56th Meeting of the INTC – Jun. 28th 2017

## Slide 6
Installation: CM3 and XT00 Modification
56th Meeting of the INTC – Jun. 28th 2017
XLN5 intertank sector in place and vacuum closed. BCAM cameras in place
All elements connected and aligned beginning of March
Cryo tubing on the top-plate and outside on the tunnel roof finished. CM cabling all done
Courtesy of E. Siesling

## Slide 7
Installation: Third HEBT line (XT03)
56th Meeting of the INTC – Jun. 28th 2017
February – May:
XT03 supports and tables in place and re-aligned immediately after the installation of ISS
Installation of the dipoles followed by the Dbox units
Quadrupole vac chambers arrived with a delay: Welding in the hall to avoid more delay
All elements aligned
Vacuum connections, gauges and valves in place. Sectors leak tight
All DC, water, interlocks and instrumentation connected
Courtesy of E. Siesling

## Slide 8
Installation: ISS and XT02 Extension
56th Meeting of the INTC – Jun. 28th 2017
Courtesy of E. Siesling

## Slide 9
Outline:
HIE-ISOLDE Phase 2A
Installation
Highlights of the Commissioning
First Operation with Stable Beam
Status and Schedule for Phase 2B
Summary
56th Meeting of the INTC – Jun. 28th 2017

## Slide 10
Hardware Commissioning: SRF cavities
All cavities conditioned and RF measurements done
Only one cavity in CM3 and one in CM1 limited by field emission at gradients lower than 6 MV/m
56th Meeting of the INTC – Jun. 28th 2017
Courtesy of W. Venturini

## Slide 11
Thermal short in cryoline found and temporarily fixed
Full repair planned for the 2017/18 technical stop
Operation successful for LHe 4.5 K process pipe
Not fully for GHe 4.5 K process pipe (requires too much force -> risk of breaking)
Hardware Commissioning: Cryoline
Courtesy of O. Pirotte
56th Meeting of the INTC – Jun. 28th 2017

## Slide 12
Beam Commissioning: Low Energy Tunes
Tunes for beams with A/q = 3.5 to the end of XT01 after each REX RF structure was set-up
Precise energy measurement using the dipole for each tune
Transverse beam profiles at each diagnostics box measured (data not yet analysed)
Conclusions:
Low-energy beams can be transported without additional losses
Beam losses in HIE-ISOLDE (ie. XLN2 to end of XT01) negligible or at the very least small
Differences between different types of FC noticeable
56th Meeting of the INTC – Jun. 28th 2017

## Slide 13
The method works very well
  Can be used for low-intensity beams
  Can be completed in ~ 1 hour
  However, as with all measurements with Si detectors, special attention is required to avoid damaging it
We will need to consider installing them in the other two HEBT lines next year
1 mm vertical slits
All quads and steerers off
Silicon detector
Beam Commissioning: Energy Measurement
Energy and energy spread of the beam can be carried out using the count rate measured at the Silicon detector at XT01.0400 after the first dipole magnet
Energy Scan after set-up of 7gap3 was completed
Energy Scan after set-up of 9gap was completed
56th Meeting of the INTC – Jun. 28th 2017

## Slide 14
Beam Commissioning: Remaining Activities
Week 26:
Phasing of cavities in CM2 and CM3 with 14N4+ (Efinal = 6.5 MeV/u)
Scaling to A/q = 3.67 and 4.0
REX-TRAP and REX-EBIS synchronization with 39K from the pilot ion source
Scaling to A/q = 3.9
Week 27-28:
Set-up for first RIB and Physics
Week 29:
Scaling to A/q = 4.33
Week 30-32:
Set-up and Physics
Week 33:
First beam to XT03
Commissioning of all diagnostics devices
Commissioning of the stripping foils
56th Meeting of the INTC – Jun. 28th 2017

## Slide 15
Outline:
HIE-ISOLDE Phase 2A
Installation
Highlights of the Commissioning
First Operation with Stable Beam
Status and Schedule for Phase 2B
Summary
56th Meeting of the INTC – Jun. 28th 2017

## Slide 16
First Operation with Stable Beam:
22Ne beam requested by Miniball users for testing and calibration last weekend
RF structure | REX |  | HIE | 
 | RFQ | 7GP3 | SRF02 | SRF04
# Trips | 1 | 3 | 2 | 8
Downtime [mins] | 15 | 0 | 10 | 40
Downtime [%] | 0.4 | 0 | 0.3 | 1.1
Ion | 22Ne6+
A/q | 3.667
HEBT | XT01
Transmission | ~ 72 %
E | 3.955 MeV/u
dEFWHM | 0.25 %
Length | ~ 60 hours
Rep. rate | 20 Hz
Both REX and the SRF cavities quite stable (1.5 trip/shift)
Cavity | E [MV/m]
SRF01 | 4.14
SRF02 | 4.14
SRF03 | 4.14
SRF04 | 4.14
SRF05 | 3.22
Cavity | Pf [kW]
RFQ | 32.8
Buncher | 1.45
IH | 38.0
7GP1 | 51.0
7GP2 | 50.2
7GP3 | 46.2
9GP | 61.5
However, note that 40% extra power will be needed at REX for beams with A/q = 4.33 and that the gradient of the SRF cavities was not pushed to 6 MV/m
56th Meeting of the INTC – Jun. 28th 2017

## Slide 17
Outline:
HIE-ISOLDE Phase 2A
Installation
Highlights of the Commissioning
First Operation with Stable Beam
Status and Schedule for Phase 2B
Summary
56th Meeting of the INTC – Jun. 28th 2017

## Slide 18
Status and Schedule for Phase 2B
Accelerating structures for CM4:
56th Meeting of the INTC – Jun. 28th 2017
Courtesy of W. Venturini
Four cavities tested and ready for installation
Additional cavity just coated with Niobium. Vertical RF test next week

## Slide 19
Same assembly team as for CM1, CM2 and CM3
Same duration as for CM3 (27 weeks in clean room + 2 weeks qualification tests outside)
Planning is shifted by 7 weeks to ensure the best set of active elements:
  Solenoid #5 ready for installation in w29
  5 cavities ready for the installation in w33
CM4 finished and tested at warm in w42
Status and Schedule for Phase 2B
56th Meeting of the INTC – Jun. 28th 2017
SM18 cryo shutdown
Solenoid installation
cavity installation
Plan for assembly of CM4:
Courtesy of Y. Leclerq

## Slide 20
Status and Schedule for Phase 2B
Installation of CM4 after refurbishing of cryoline starting in February
Hardware commissioning and cryomodules cool-down starting in March
Beam commissioning starting in May
Physics starting in July
56th Meeting of the INTC – Jun. 28th 2017
Plan for 2018:
Courtesy of W. Venturini and Y. Kadi

## Slide 21
Outline:
HIE-ISOLDE Phase 2A
Installation
Highlights of the Commissioning
First Operation with Stable Beam
Status and Schedule for Phase 2B
Summary
56th Meeting of the INTC – Jun. 28th 2017

## Slide 22
Summary:
Hardware commissioning completed:
  All power converters/magnets circuits tested
  All SRF cavities conditioned and tested
  Source of the cavity trips identified and mitigated
  Source of thermal loss in cryoline identified and mitigated
Installation and hardware commissioning of HIE-ISOLDE Phase 2A completed (3 cryomodules with 5 QWR each, 3 HEBTs lines)
Beam commissioning on-going:
  Low energy tunes to the end of XT01 prepared (80% transmission)
  Cavities in CM1, CM2 and part of CM3 phased
  New low and high level control software tested
  Commissioning of XT03 on week 33
Operations:
  First stable beam (22Ne at 4 MeV/u) delivered to the Miniball Spectrometer
Phase 2B status and plan:
  Four cavities ready for installation in CM4, one more will be tested on wk. 27
  Assembly of CM4 will be completed before the end of 2017
  Installation in tunnel in February 2018
  Physics campaign in July 2018
56th Meeting of the INTC – Jun. 28th 2017