## Slide 1: Linac4-status update
Updated with comments 22 may 2017
Updated again 29 June 2017

## Slide 2: Aim at tunnel closed 26 may
HST is already out, de-buncher to be installed soon
Some BI equipment is late, not critical for the RR, will be installed at later stage (collect all the late-comers and grant 3 days of access mid-july).
Alignment of the low energy end (LEBT to DTL) is important and strategy to be put in place.
RF work to be done is planned and followed up (S. Ramberger presentation at IEFC 7th April )
Detailed plan with stops and milestones is being worked out by AL.
To be discussed today – we have a small vacuum leak

## Slide 3: Rough planning
JUNE : RF work, Bunch Shape Monitor tune-up, debuncher commissioning.
JULY –SEPTEMBER : test-run, identify the weak points. Fault tracker in place. ABP running the linac. Involvement of OP to the extend of their availability. Stop of 3 days mid july
OCTOBRE : RF work + addressing weak points identified in july-septembre+ possibly change of source.
from end OCTOBRE: OP driving the daily operation and start the mock-up period. ABP as “linac supervisor”, RF and ABP piquet during working hours.
Winter stop : 14 dec – tbd by Rende and OP
IMPORTANT : OP involvement is one of the goals of the reliability run but it doesn’t drive the schedule.

## Slide 4: Update 29 June 2017
JUNE : RF work, Bunch Shape Monitor tune-up, debuncher commissioning.
1 JULY –30 SEPTEMBER : test-run, identify the weak points. Fault tracker in place. ABP running the linac. Involvement of OP to the extend of their availability.
  Stop for completing debuncher installation/ BI installation / any other missing items : 24-28 July
  ADAM experiment either 20-21 July or 31july-1augst
1-30 OCTOBRE : RF work + addressing weak points identified in july-septembre+ possibly change of source.
31 OCTOBRE-18 decembre: OP driving the daily operation and start the mock-up period. ABP as “linac supervisor”, piquet service during working hours.
    Winter stop 18 decembre-26 February
    Linac closed 1 february
26 February – 30 April : : OP driving the daily operation and start the mock-up period. ABP as “linac supervisor”, piquet service during working hours.
This schedule will be integrated in the injector schedule and presented at the IEFC

## Slide 5: OP involvement
Software development
Autopilot for the source
Daily running

## Slide 6: Reliability Run -phases
Phase | When |  | 
0-Finalisation | By end June 17 | Consolidation of LLRF and BI instrumentation. | CRUCIAL to respect the schedule
1-make the linac4 reliable by addressing weak points | July – end of septembre | Short runs followed by repairs/optimisation | Accelerator Fault Tracker in place; OP involved with Linac team still leading.
2-Mock-up of operation as after the connection | End of octobre- april 18 | Daily preparation of different beams, continuous operation for weeks, exploitation of the LINAC4 flexibility) | OP leading the run with linac team as support. Call-out list during working hours.

## Slide 7: Responsibilities
A. Lombardi (ABP) responsible for the reliability run , Bettina Mikulec is the OP representative

## Slide 8: Reliability run – details
Keep in place HST dump , to have the possibility to have multiple destinations/users and verify the energy.
Beam-on time calculated from the logbook entries keeping into account that there is not a piquet service.
Software to facilitate running from the CCC should be transferred to OP or written by OP. Needs have been identified.
Main dump
HST temporary dump