## Slide 1: MAGNET TEST PLAN INCLUDING COLLABORATIONS, STRING AND TEST STAND
M. Bajko on behalf of the testing team of CERN and the collaborators
G. Chlachidze (FNAL), H. Felice(CEA), T. Nakamoto (KEK), J. Muratore (BNL), M. Sorbi (INFN), R. Ruber (FREIA), M. Pojer (CERN), L. Fiscarelli (CERN),
7th Collaboration Meeting HL-LHC Madrid Nov 2017
Special thanks for M. Barberan for the Master Plan

## Slide 2
Testing for HiLumi WPs
Test Catalogue for cold powering with planning
Test plan and considerations for planification
Status of the test facilities
Conclusions
CONTENT

## Slide 3: Testing for HL-LHC WPs

## Slide 4: Testing WP3
Sextupole
Triplet [G. Ambrosio, P. Ferracin et al.]
D1[T. Nakamoto, et al.]
MQYY [H. Felice, et al.]
D2 [P. Fabbricatore, S. Farinon, et al.]
MCBXF [F. Toral, et al.]
Skew quad
[M. Sorbi, M. Statera, et al.]
Octupole
Decapole
Dodecapole
D2 correctors [G. Kirby]

## Slide 5: MQXFA test stand: BNL
LQXFA(Q1) LQXFB(Q3)
Test Responsible: Joseph Muratore
Back up solution:
CERN Cluster D
20 + 3 prototype magnets to be tested
5 Models test at CERN D/BNL

## Slide 6: LQXFA/B (Q1/3) test stand: FNAL
MQXFA MQXFA
Test Responsible: Guram Chalchidze
Back up solution:
CERN Cluster A/F
10 + 1 proto cold masses to be tested

## Slide 7: MCBXFA/B test stand: CERN / FREIA
LQXFC(Q2a) LQXFD(Q2b) CP
Test Responsible: Marta Bajko (CERN)
Roger Ruber (FREIA)
50 % CERN and 50% FREIA
18 + 3 prototype magnets to be tested

## Slide 8: MQXFB test stand: -
LQXFC(Q2a) LQXFD(Q2b)
12+ 2 prototype magnets will be NOT tested
4 short models test at CERN

## Slide 9: LQXFC/D (Q2a/b) test stand: CERN
MCBXFB MQXFB
Test Responsible: Marta Bajko
Back up solution:
CERN Cluster F
10 cold masses + 2 prototypes to be tested
Installations
on going
Complete by end 2019
No EE

## Slide 10: HO Correctors test stand: LASA
LCXF (CP)
Test Responsible: Massimo Sorbi
54 magnets + 5 prototypes to be tested
Models test at CERN Siegtal

## Slide 11: LCXF (CP) test stand: CERN
MCBXFA/MQSXF/MCTXF/MCTSXF/MCDXF/MCDSXF /MCOXF/MCOSXF/MCSXF/MCSSXF/MBXF /MQXFA
Test Responsible: Marta Bajko
6 cold masses to be tested
Modification of existing to be done

## Slide 12: MBXF test stand: KEK
LBXF (D1)
Test Responsible: Tatsu Nakamoto
1 prototype + 5 series magnets to be tested
3 Model test at KEK/CERN

## Slide 13: LBXF (D1) test stand: CERN
MBXF
Test Responsible: Marta Bajko CERN
1 proto+ 6 series cold masses to be tested

## Slide 14: MBRB test stand:
LBRD (D2)
6 magnets NOT TESTED
Model test at CERN D

## Slide 15: MCBRB test stand: CERN/FREIA
LBRD (D2)
50 % CERN and 50% FREIA
1 Model test at CERN D
Test Responsible: Marta Bajko (CERN)
Roger Ruber (FREIA)
1 proto + 12 series magnets to be tested

## Slide 16: LBRD (D2) test stand: CERN
MBRD MCBRD MCBRD
Test Responsible: Marta Bajko CERN
1 proto+ 6 series cold masses to be tested

## Slide 17: MQYY test stand: CEA
LQYY (Q4)
Test Responsible: Helene Felice
2 proto magnets to be tested: CEA
Existing test stand modification planned.

## Slide 18: LQYY (Q4) test stand: CERN
MQYY MCBYY MCBYY
Test Responsible: Marta Bajko CERN
4 cold masses to be tested

## Slide 19: MCBY/MQY test stand: CERN
LQYY (Q4)
Magnets tested
Test Responsible: Marta Bajko

## Slide 20: LQ (Q10) test stand: CERN
MQ MCBY MCBY
Test Responsible: Marta Bajko CERN
4 cold masses to be tested

## Slide 21: Testing for HL-LHC WPs

## Slide 22: Testing WP11: magnets test stand:-
Test Responsible: Marta Bajko CERN
Magnets will be not tested
Model test at CERN LONG

## Slide 23: Testing WP11 cold mass test stand: CERN
Test Responsible: Marta Bajko CERN
4 +2 cold masses to be tested
LMBHA

## Slide 24: Testing for HL-LHC WPs

## Slide 25: Testing WP6A test stand: CERN
Cluster G 20 kA
- 18 kA
 75 mm
+ 18 kA
62 kA
62 kA
3 2 kA (7 kA)
+ 13 kA
- 13 kA
Instrumentation wires
(twisted and cabled)
Including insulation
Protective insulation (outer layer)
Cluster F 20 kA,7 kA, 2kA, 0.6 kA, 0,12 kA
Specification under revision
PC 20 kA and leads for 2 kA for end 2018
Test of 60 m long cryostats on going

## Slide 26: Magnet test plan
Magnet arrives at SM18
Installation in cryostat
Cooldown
Cold powering tests
Warmup
Magnet leaves SM18
Installation in cryostat
Cooldown
Cold powering tests
Warmup
Magnet arrives at SM18
Magnet leaves SM18
TRAINING
TRAINING

## Slide 27: Planning of test
Every single magnet will be tested at cold and up to Iultimate= 108% Inom in nominal cooling conditions (1. 9K)
Systematic Powering at Inom for 8 h
High Voltage test will be performed according to individual magnet electrical insulation and design values up to 3400 V for 120 s, <20 mA
Magnet protection will be done following the individual design CLIQ, QH, EE
Magnet protection is based on quench detection at 50-100 mV, verification time of 10 ms and protection simultaneously with all systems
Splice resistances measured individually and < 2 nOHM
Quench localisation with Vtaps and quench antenna
Magnetic measurement with shaft
Typical test is over 7 weeks and systematically includes a thermal cycle (TC) unless is produced in the USA and tested before sent to CERN. In that case no TC is considered so a total of 5 weeks for series and 6 weeks for prototypes.
The global SM18 magnet test planning contains apart of the HL LHC test requirements: 30 magnet test for LHC ( to be changed in LS2) and other 34 without name for the moment eventually to be changed in LS3. For those magnets there is no TC foreseen. The planning does not contain any re-test of those and is 6 weeks long.
PERFORMANCE TEST CAPACITY estimated to :
20 quench /magnet
+ Corrector test, Splice resistance, Magnetic measurement, High Voltage test

## Slide 28: Magnetic Measurements @CERN
At room temperature: rotating-coils (TF and field quality)
At 1.9 K vertical station: rotating-coil shaft in helium bath
Short models and correctors
At 1.9 K horizontal bench: rotating-coil long shafts + stretched wire
Anti-cryostat is required
https://lhc-div-mms.web.cern.ch/lhc-div-mms/tests/MAG/docum/hilumi/Magnets/sharing.jpg
reception
At room temperature: rotating-coil (TF, field quality, angle, center)
By L. Fiscarelli

## Slide 29: Testing for HL-LHC WPs

## Slide 30: WP16 STRING plans
P5
D1
CP
Q3
Q2b
Q2a
Q1
DFX
QRX
Q2a
Q1
Q2b
3rd Q 2019
2020
D1
2021
CP
HL LHC IT STRING
3rd Q 2021
Q3
This installation order seems to be the more difficult and have more interest for the WP15 and for Vac as allows instrumenting the beam screen of Q1 ( the tick version)
We consider that each medium or high current quench is recovered in 12h. This is to be verified with the presently planned infrastructure and magnet + cavity test plan.
P5L is the most complicated and coherent set up with the Sm18 installations and the tunnel is the smallest .
We plan to reproduce the space allowed in that place of the tunnel for the interventions
The SLOPE of the tunnel will be NOT REPRODUCED in the STRING
Iultim is considered
In the phase of HWC of the STRING 120 quenches were estimated to be done till I nom. An other 50 quenches are planned to do with the goal of “special test” not done in the shadow of the HWC.

## Slide 31: STATUS of FACILITIES
To be remarked that there is NO PLAN TO TEST individually the :
7.2 m long MQXFB ( Q2a/b)
5.5 m long MBH 11T dipole ( LBH)
8.2 m long MBRB (D2)
before their integration into the cold masses

## Slide 32: BNL STATUS
6 m-deep vertical test cryostat to accommodate 5 m-long MQXFA testing at 1.9 K and 1 bar, and powering to 24 kA.
Energy extraction system 30-150 mΩ and fast switching with IGBTs
Anti-cryostat for “warm” measurements with quench antenna and magnetic field measuring systems
Quench antenna with 16 dual-winding sensing elements
Magnetic field rotating probe with two sets of windings using PCB technology
New data acquisition system for fast and slow data logging
Dual quench detection system for both fast and slow discharges
12 independent firing units for quench protection heaters
500 V CLIQ quench protection system
Vertical Test Facility at BNL, showing two of the five test cryostats and the backup refrigerator. Arrow points to Vertical Test Cryostat 2 (1.9K and 24kA).
Each magnet must meet the requirements set forth in US-HiLumi-doc-137 before shipping to FNAL for assembly into LQXFA cold masses.
27 MQXFA magnet tests (including prototypes at BNL Vertical Test Facility
BNL Vertical Test Facility has been upgraded to accommodate the testing of 5 m-long MQXFA magnets at 1.9 K and 1 bar and powering up to 24kA, more than meeting the requirements of US-HiLumi-doc-137.
The test facility has been commissioned with the successful test of the first full length MQXF coil in a mirror configuration. The quench plot below demonstrates the capability of the facility to provide the necessary superfluid He and the required test currents.
By Joseph F Muratore

## Slide 33: CERN STATUS
By Marta Bajko
SC link . Test of 60 m long items
I=18 kA
Duration: 1 hour
Test performed on A1 aswell with nominal cooling parameter!!!
Qualification to 20 kA of Cluster A
Aprox. 90 magnets/cold masses to be tested for HL-LHC in vertical or horizontal test benches + SC link and STRING
Test facilities are operational, but still optimisation is ongoing. He pumping capacity under revision.
For 2018:
2 x +/- 2kA PC and EE for Cluster D
2 x 2kA PC and 2 kA CL for Cluster A/F in 2018 and + 20 kA PC for Cluster F
Interface for SC link on Cluster F and all magnets in discussion or production
Cluster G
Cluster D
Cluster A
Cluster F
Model magnets and SC link
Model magnets and MCBXF/MCBRD
Q1/Q2a/Q2b/Q3/D2
Q1/Q2a/Q2b/Q3/D2
SC link 120 m
Cluster B-C/E
Other cold masses
30 kA EE IGBT+ Dump
20 kA EE Thyristor based switch
20 kA+ 2x 2 kA

## Slide 34: CEA STATUS
Vertical Test Facility at BNL, showing two of the five test cryostats and the backup refrigerator. Arrow points to Vertical Test Cryostat 2 (1.9K and 24kA).
By Helene Felice
Magnetic measurement
CERN probe (47 mm diameter)
rotatiing in LHe and DAQ
Adaptation (seal) (saturated bath)
Operation by CEA
Test plan
Under discussion
CEA Team: J.M. Gheller, D. Bouziat, D. Simon, H. Felice, J.C. Barriere, J. Belorgey, F. Molinié, J. Relland
Target date for operation: Summer 2018
Cryogenic facility
CEA 8 m vertical cryostat equipped with a 3 m long « sock » (tank)
Adaptation of an existing top plate
Saturated LHe bath at 1.9 K 23 mbar
Data acquisition and magnet protection
Based on existing infrastructure
Max Dump resistor: 100 mohm
Power supply: 20 kA
Resistive current leads 10 kA
1 MQYYM: NbTi
90 mm single aperture quadrupole
360 mm OD
1.2 m magnetic length
2 MQYYP: NbTi
90 mm double aperture quad
614 mm yoke OD
3.6 m magnetic length
Manufactured within Quaco for HL-HC
6 MQ: NbTi
56 mm double aperture quad
452 mm yoke OD
3.1 m magnetic length
Spare magnets for LHC
CEA Team: J.M. Gheller, H. Allain, H. Felice,C. Lorin, D. Simon, J.C. Barriere, J. Belorgey, F. Molinié, J. Relland
Target date for operation: End of 2019
Cryogenic facility
Design and fabrication of an inner cryostat to be inserted in the 8 m vertical cryostat
Pressurized LHe bath at 1.9 K
Introduction of Lambda plates in the main Lambda plate to accomodate the anticryostats and bus bars
Connection to a liquifier
Data acquisition and magnet protection
Upgrade under discussion
Max Dump resistor: 100 mohm
Power supply: 20 kA
HTS current leads under investigation
Effort to find synergy to minimize cost and down time
Rods
Heat exchanger 4.2 K /1.9 K
J-T valve
Lambda plate
Anti-cryostat for magnetic measurements
Quench relief valve
4.2K bath
Filling cord
Saturated He II

## Slide 35: FNAL STATUS
Vertical Test Facility at BNL, showing two of the five test cryostats and the backup refrigerator. Arrow points to Vertical Test Cryostat 2 (1.9K and 24kA).
By Guram Chlachidze
One prototype and ten production Q1/Q3 cryo-assemblies for the HiLumi LHC upgrade will be tested at Fermilab’s Horizontal Test Stand
  Q1/Q3 are part of the final focusing triplet magnets before the interaction point
  Each cryo-assembly comprises two 150 mm aperture 4.2 m long Nb3Sn low-β quadruples inside the cryostat
  Test requirements for Q1 and Q3 elements are the same
Test stand previously was used for testing the existing LHC inner triplet quadrupoles
All major test facility components are available
  Refurbishment is necessary to meet new test requirements
Primary test objective is full qualification and acceptance of LQXFA (Q1) and LQXFB (Q3) cryostat assemblies
  Quench performance checkout at 1.9 K up to the ultimate current of 17.9 kA
  Alignment measurements
  Field quality measurements: Integrated gradient and harmonics
Refurbishment of the test stand components already started
  Upgrade of the top plate and the feedbox assembly
  New quench recovery & pumping lines
  Design of transfer lines to the cryostat
  Design of the quench protection and detection systems
The prototype cryo-assembly test is expected in summer 2019, the first production test in about 1 year afterwards
  Peak production rate is 3 tests per year

## Slide 36: KEK STATUS
By Tatsu Nakamoto
Cryostat
Operating Temp. of 4.4K to 1.9K, HeII Sub-cooler (55W)
Capacity: 1.9 K bath: 7524 mm deep, 700 mm in a diameter.
  Weight: 8.6 ton (MQXA). Need to check for D1.
New header for the D1 (MBXF)
  Anti-cryostat for MFM (O.D. 141.3) w/ Quench Antenna
  15 kA Current Leads (nominal of D1: 12 kA)
Refrigerator/Liquefier for Test Stand
Main: 160 L/h, 2400 L dewar + Sub: 350 L/h, 5000 L dewar
  In linkage operation: 510 L/h max.
Power Converter
15 kA, 15V, thyristor switch for prompt shutoff.
Dump resistor (0, 12.5, 25, 50, 75 or 100 mW)
Concern: accuracy and stability of DCCT output
  New DCCT will be installed in early 2018.
Measurement system
Isolation Amp: NF P-62A, 76 ch
NI PXI 1643 (16bit, 250 kS/s/ch), 88 ch
KEYSIGHT 3458A multimeter (8.5 digit) x 3
Kyowa UCAM-60B for strain gauge measurement, currently 30 ch (80 ch max.)
Labview (& KEYSIGHT VEE only for field measurement)
Vertical Measurement
Rotating coil in anti-cryostat (I.D. 108.3mm) at “warm” temperature.
  Printed-circuit board
  3 radial coils: B1 and analogue bucking
  Long (350mm) and short (80mm) arrays
  GN2 flow from the end to suppress thermal shrinkage of the pipe
7 m long GFRP shaft
  not long enough for the full-scale magnet, but it can be extended.
Encoder: HEIDENHAIN RON 255
Integrator: MetroLAB PDI-5025 x 3
Magnet scale: SONY LY51
Full-scale magnets:
Japanese in-kind contribution is under discussion in the meantime.
  Deliverables should be defined by HL-LHC C&S review (March 2018).
  * The following is based on the initial plan (not approved yet).
A full-scale prototype (7-m long) will be produced by the end of 2020:
  In time for String Test at CERN in 2021.
  Vertical test to be done at KEK, horizontal test at CERN.
A series magnet production: 6 units including 2 spares.
  From 2021 to early 2024.
  Vertical tests at KEK, horizontal test at CERN.
For 2-m models:
Cold tests for MBXFS1 & MBXFS1b completed.
2nd model (MBXFS2) will be tested in May 2018.
  New design features: higher pre-stress, coil ends, HX holes, QPH, etc.
  Test item:
    Training quench at 1.9 K, QPH quench, ramp rate dependence, excitation at 4.4 K.
    Field measurement: DC loop at magnet center, Z-scan by 80-mm long coil.
    Strain gages: collar (pole), axial
  Afterward, shipping to CERN for further cold test (beam tube insertion).
3rd model (MBXFS3) in Dec. 2018 (…maybe with some delay).

## Slide 37: FREIA STATUS
Vertical Test Facility at BNL, showing two of the five test cryostats and the backup refrigerator. Arrow points to Vertical Test Cryostat 2 (1.9K and 24kA).
By Roger Ruber
Dipole orbit corrector testing
  2 circuits up to 2 kA each
  (pressurized) liquid bath
Vertical cryostat
  2645 x ø1100mm below lambda plate
  design includes joint for lambda plate
  two inserts will be available (start) : a. liquid bath b. pressurized bath with 2K heat exchanger
Powering system
  2x 2kA CERN type power converters
  switch and power extraction unit
Control system
  cryostat: PLC, EPICS
  magnet: CERN type quench monitoring
µGersemi simulator
Vertical cryostat top flange and inner vessel
26-Oct-2017
Opened valve box & electrical cabinet
26-Oct-2017
Vertical cryostat vacuum vessel
28-Apr-2017
Under construction
  December  factory test valve box & controls with µGersemi simulator
  February  installation in Uppsala
  April  commissioning
Training of personnel “ CERN is planned from February 2018
Gersemi test stand at FREIA

## Slide 38: INFN STATUS
Vertical Test Facility at BNL, showing two of the five test cryostats and the backup refrigerator. Arrow points to Vertical Test Cryostat 2 (1.9K and 24kA).
By Massimo Sorbi
New cryostat for testing MCTXFP1 (12P), MCQSXFP1 (4P) and then for HO series magnets
New power supply for magnet test (200 A, 50 V)
New main switch for power supply (fast solid state switch, Dt<1 ms)
New acquisition system for test monitoring
Installation of system for magnetic measurement at low/room temperature (supplied by CERN)
Ordering started in 2017
Installation to be completed in 2018
In production are necessary 3 batches:
  18 magnets
  2X4P 2X12P
  5 cooldowns
Different possible configurations for housing the magnets of each batch
The flange is designed for housing the magnetic measurement system
The tests will be performed at 4.2 K
600
2350
12P
4P
HE inlet
Mag.meas.
Safety
Valve and disk
Connections X3
CL : 2+4

## Slide 39: Testing for HL-LHC: Conclusions
Test facilities for model testing are operational at CERN , KEK, BNL, and for series at LASA .
The horizontal test stands are quite well advanced as we are ( FNAL and CERN) are re-using existing facilities with modifications
Uppsala is preparing a complete new test stand: installations are well advanced and in time
Important to work out QA/QC together and implement accessible platforms for good data exchange
2nd Workshop on Superconducting Magnet Test Facilities is foreseen in BNL in Spring 2018