## Slide 1: HL-LHC Status on RFD Cryomdule Development
Shrikant Pattalwar,
on behalf of Crab Cavity collaboration
7th HL-LHC meeting, 13-16 November, 2017, Madrid

## Slide 2
Outline
UK ‘s Role in the project
Tasks and Status
Plans and Goals

## Slide 5: Additional Requirements
First draft of requirement was created in March 2017
DQW-CM will be used as a baseline reference
RFD-CM to be compatible with SPS and LHC
……..
Sector Valves
Vacuum Instrumentation to be a part of the Cryomodule
Two beam pipes, one with beam screen
………
5K – 20K cooling circuit for beam Screen cooling
PRVs to be moved from Service module to cryomdule
Specification for removable level probes
Vacuum barrier between service module and the cryomodule
……………..
RF requirements ( Couplers, tuners, etc…)
Lessons learnt from DQW-SPP-CM

## Slide 6
Plan, Targets and Milestone
Release Drawings for Manufacturing
Design and manufacturing and testing of cavities, tuners, couplers etc. by CERN
Y2
Y3
Y4
1
4
3
2
Activities divided into 4 main Tasks
Project Plan

## Slide 7
Cross section DQW Cryomodule
vacuum system in non-crab beamline
Beam screen
assembly
Cavities module
interconnection
Plug-in
module
Vacuum
instrumentation
Beam screen
assembly
Plug-in
module
Cold warm transition
Cold warm transition
Crab beam line has the same configuration but without beam screen assembly. In consequence, its mechanical aperture is circular.
Vacuum
instrumentation
Thermal shield
Cryomodule

## Slide 8
Vacuum requirement- Instrumentation Ports
The CC cryostat is equipped with 4 sector valves.
The 4 instrumentation ports are equipped with vacuum gauges and roughing valves for monitoring and maintenance of the cryomodule.
P. Santos Diaz
Mobile pumping system
Blue: crabbed beam
Red: non-crabbed beam

## Slide 9
The CC CM will be equipped with 2 sector valves on cavity beam pipe.
Other beam pipe ports will be flanged off and sector valves will be added later
CM will be equipped with Only 2 instrumentation ports ( inside) and the other 2 ports will move outside the CM after flange.
Mobile pumping system
Blue: crabbed beam
Red: non-crabbed beam
Vacuum requirement - Instrumentation Ports

## Slide 10: Cavity String (Preliminary Design)
Led by
Nik Templeton
Vacuum
Instrumentation to be moved here
Two Beam Pipes

## Slide 11
2653
Beam Screen Interconnection
Beam Screen
Stainless Steel - Cu & A-C coating
Sliding Beam Screen Connection
Plug-in Module
Cavity Warm Module (Shielded) Bellows
Cavity String length optimisation

## Slide 12
3334
Cold-Warm Transition
Overall dimensions - to be optimised
Cavity String length optimisation

## Slide 13
Beam Screen Active Cooling
Active cooling for beam screen

## Slide 14: DQW-SPS HOM cooling
16 litres in reservoir
Nominal LHe Level: 724mm (1/2 Full)
Ensures 30mm above HOM Cooling
60
109
30
355
724

## Slide 15: Parallel 2-Phase Line LHC (-1.24%) – Modified HOM Cooling
~16 litres in reservoir
New HOM cryo-circuit ensures cooling
Alternative Option: Separate LHe Inlet & GHe Outlet lines for HOM cooling

## Slide 16: Vacuum barrier between Cryo-Service Module and CM
Thermal shield return gas used to thermalise vacuum break
Thermal shield Input gas
5k in 10k out gas for intermediate HOM
Outer tubes provide long thermal path
Vacuum break
Cryomodule vacuum
Service module vacuum

## Slide 17
Nik Templeton
CM design (work in progress)

## Slide 18: Engineering Technology Centre 3D Layout
Task 2 – Facility reconfiguration ( Ed Jordan)
ISO – 4
Clean Room
CM Assembly
area

## Slide 19: Cavity string travel route
Cleanroomm
Lifter Location
Route A
Route B
Route C
Cryomodule Integration (2019-20)
Jan-April Preparations
May-Dec Mock-up/ Qualify/Pre-assembly
Jan -March CM Integration
Clean Room (2019)
Jan-April Preparations
May-Sept Mock-up/ Qualify
Oct-Dec String assembly
Large assembly area needed to store thermal shield, OVC, tooling etc.

## Slide 20
Cleanroom
Lifter Location 1
Path shown is to Lifter location 1 using route A – but considerations still apply to other routes and locations.
ISO4
ISO5
ASSEMBLY
Cavity string travel route

## Slide 21: Cavity String Mobile (Trolley)
Cavity String Mobile 1
Cavity String Mobile 2
4.6m
3.5m
1.1m + XX
Two Separate frames connected during clean room assembly – 1.1m frame detaches before transit.
Assembly Interface required

## Slide 22
Goals for 2018
Complete specification document - Feb 2018
Agree on the responsibilities for design, procurements and logistics - Feb 2018
Preliminary CM design (Internal design review) to facilitate procurement of long lead items - April 2018
Final CM design ( External design review) – June 2018
Launch development of assembly procedures and acceptance criteria - Jan 2018

## Slide 23
Summary
Plans are in place to design and assemble RFD CM compatible with SPS and LHC.
Efforts will be shared between UK and CERN and CM will be assembled at STFC Daresbury Laboratory ( by March 2020)
At Daresbury the project activities are divided 4 tasks: ( technical lead by Tom Jones)
- CM design ( Nik Templeton)
- Facility Reconfiguration, tooling (Ed Jordan)
- Clean room assembly
- and final integration
Current focus is on developing preliminary design to meet the vacuum and Cryo requirements as well as on the design of the tooling
Goals have been set for 2018 and ……beyond

## Slide 24: Thank you

## Slide 25
Additional Slides

## Slide 26
Cavity String - Sections

## Slide 27: Cryomodule

## Slide 30: RFD LHC/SPS Prototype: Cavity String
Fixed:
FPC Distance - 1050 mm?
To Be Updated:
CWTs
Cryolines
Valves & Valve Box
Support & Alignment System
Top Plate Integration
New Conditions:
2nd Beamscreen
No BCAM
LHC Slope (1.24% ≈ 0.71°)
Internal Vacuum Instrumentation*
New Cryo Pressure Relief Valve
RFD SPS Concept Design

## Slide 31: RFD LHC/SPS Prototype: Cryomodule
Fixed:
Trapezoidal / Top Loaded Configuration ?
To Be Updated:
Vacuum Vessel Design
Cryomodule Limits
Cryo-Service / Jumper
FSI
RF Lines
Thermal Shield & MLI
Warm Magnetic Shield
New Conditions:
No Gaskets / O Rings in LHC – Welded Vessel - No Windows
LHC Slope & Space Constraints
Split insulation vacuum
Level Gauge
RFD SPS Concept Design

## Slide 33
Progress To date - Finance
September 2017

## Slide 35
Vacuum Instrumentation

## Slide 36: HL-LHC UK ( WP 2.2 Responsibilities)
Courtesy: M. Garlaschè
STFC Deliverable
Support SPS-CM
Long Term Vision – to build and supply series cryomodule for HL-LHC
LS2
Activities
Y1 Support CERN design and construction of SPS-CM1
Y2 to Y4 Design and deliver SPS+ CM2

## Slide 37: Vacuum Integration Proposal
All Metal Gate Valve
Valve Box – Geometry TBD
Welded OVC Interface (no O-Ring)
DN100CF Beam Vac. Connection
DN160CF Valve Box Connection
DN63 Vacuum Instrumentation

## Slide 38: LHC Point 5
No Additional Constraints
Design for SPS
(+ 190 mm floor-beam height requires adjustment or additional frame)