## Slide 1: B.311 Financial Review – 17/07/2017 HE group
D. Lafarge, R. Rinaldesi, EN-HE

## Slide 2: Items included in HE work package
Item | Budget [kCHF] | Actual value [kCHF]
Main hall overhead crane | 300 | 296
Measuring room overhead crane | 80 | 68
Lift | 100 | 145
Transport and handling operations | 100 | ?
total | 580 | -

## Slide 3: Situation as of 17/07/2017
Item | Status
Main hall overhead crane | Order in September 2016 (DL 6496389) Installation and acceptance tests in June 2017 100% paid
Measuring room overhead crane | Order in February 2017 (DL 6667792) Installation and acceptance tests in June 2017 0% paid (formal problems with bank warranty to be solved soon) -> payment expected by end of August 2017
Lift | Order in April 2017 (DL 6740238) Installation ongoing Expected completion 31/07/17 and tests in Sept. 17 with final power supply 0% paid (bank warranty) -> 70% payment by 30/09/17 (100% by 31/07/18)
Transport and handling operations | Only some transport assistance needed so far Most of the operations will be needed after the handover as per user’s request

## Slide 4: Commitments and Payments
Item | 17/07/2017 |  | Forecast (handover 31/10/2017) | 
 | Open committ. [kCHF] | Paid [kCHF] | Open committ. [kCHF] | Paid [kCHF]
Main hall overhead crane | 0 | 296 | 0 | 296
Measuring room overhead crane | 68 | 0 | 0 | 68
Lift | 145 | 0 | 44 | 101
Transport and handling operations | 0 | < 1 | 0 | < 1
total | 213 | 296 | 44 | 465