## Slide 1: Fabrication Status of the first 802 MHz Prototype Cavities for PERLE
F. Marhauser
LHeC Workshop CERN
11-13 September 2017

## Slide 2: Overview
Jefferson Lab has a contract with CERN to build
  One single-cell fine-grain niobium 802 MHz cavity (manufactured)
  Two single-cell OFHC 802 MHz cavities
  One 5-cell fine-grain 802 MHz cavity
  The remaining cavities are advancing rapidly
In addition, Jefferson Lab has looked into:
  Higher Order Mode (HOM) coupler design
  Cryomodule design
  This design work is preliminary
    Funding is required to make more progress
LHeC and FCC-eh Workshop
CERN 11-13 September 2017

## Slide 3: Deliverables (based on SOW with CERN)
- First 802 MHz Niobium single-cell cavity has been completed at JLab, the cavity is now being post- processed prior to vertical RF testing
2 copper 802 MHz cavities will be produced for R&D purposes and will be sent to CERN
One bare Niobium five-cell 802 MHz design is being fabricated, completion expected by end of Sept. 2017
Frank Marhauser
LHeC and FCC-eh Workshop
CERN 11-13 September 2017
Notes: Red Interior Page Design 1

## Slide 4: Status of Deliverables
Cavity | Qty. | Material | Half cells deep- drawn | Beam Tubes deep-drawn/ rolled | Flanges machined | End group EBW (end cell + tube + flange) | Dumb- bells EBW | Machining/ Trimming | Cavity EBW
1-cell | 1 | FG Nb | 2/2 | 2/2 | 2/2 NbTi flanges | 2/2 | n/a | done | done
1-cell | 2 | OFHC Cu | 4/4 | 4/4 not EB-welded and machined | 4/4 SS 316 LN | not yet started | n/a | equator trimming after EBW | -
5-cell | 1 | FG Nb | 10/10 | 2/2 | 2/2 NbTi flanges | 2/2 | 4/4 | in progress | -
Frank Marhauser
LHeC and FCC-eh Workshop
CERN 11-13 September 2017

## Slide 5: Which HOM-Coupler Technology ?
Main coupler
HOM end group 1
HOM end group 2
First approach should be to utilize existing coupler technology, but this needs scaling to new frequency and tube ID
For instance: scale LHC HOM couplers (and FPC)
4 HOM couplers per cavity ?
  LHC-type coaxial loop coupler is narrowband coupler for dipole modes
  LHC-type coaxial antenna/capacitive coupler is more broadband
Frank Marhauser
LHeC and FCC-eh Workshop
CERN 11-13 September 2017
Notes: Red Interior Page Design 1

## Slide 6: Which HOM-Coupler Technology ?
Main coupler
HOM end group
A better solution would be utilizing 3 couplers for HOM end group
Minimizes dependence on mode polarization
Scaled JLab-type couplers
Scaled TESLA-type coaxial couplers
Frank Marhauser
LHeC and FCC-eh Workshop
CERN 11-13 September 2017
Notes: Red Interior Page Design 1

## Slide 7: Which HOM-Coupler Technology ?
Main coupler
HOM end group
Scaled JLab High Current (HC) waveguide couplers
1.5 GHz HC cavity prototype
750 MHz HC cavity prototype
Frank Marhauser
HOM waveguides only required if beam current increases significantly
LHeC and FCC-eh Workshop
CERN 11-13 September 2017
Notes: Red Interior Page Design 1

## Slide 8: JLab/PERLE
On axis |Ez|
For the prototype PERLE cavity we have chosen a single-die design (end cells are trimmed shorter)
Frank Marhauser
PERLE cavity identical to CERN FCC prototype under construction
Optimized for high current operation
LHeC and FCC-eh Workshop
CERN 11-13 September 2017
Notes: Red Interior Page Design 1

## Slide 9: Summary
CERN FCC cavity prototypes are progressing well
  Expected completion in September 2017
  Cutting off the beam tubes from the bare 5-cell cavity and welding new end groups to the cavity to investigate HOM-damping scenarios would be a good next step
Preliminary evaluation of HOM’s has been carried out
  Either coax or waveguide would work (waveguide is probably overkill)
  Three couplers should be sufficient (needs to be checked)
  Strong cell-to-cell coupling is good for HOM damping
Design for PERLE cavity is identical to CERN FCC cavity
  Ready for detailed end group design work
  Prototype cavity could be built 6 months after funding becomes available if CERN 5-cell prototype cavity is modified
    One year would be required starting from scratch
Jefferson Lab will provide a budgetary estimate for an SNS-type cryomodule for PERLE
LHeC and FCC-eh Workshop
CERN 11-13 September 2017
Notes: Red Interior Page Design 1