## Slide 1
Outline:
Introduction
Why to coat Q5R2 in YETS
The technology is mature enough
Schedule & Resources
Risk assessment
Conclusions
a-C coatings beyond the ITs
part 1: coat Q5R2 in YETS
P. Costa Pinto on behalf of (TE-VSC)
With contributions from B. Di Girolamo (ATS-DO), G. Ferlin and S. Claudet (TE-CRG) S. Le Naour (TE-MSC) and C. Adorisio (HSE-RP)

## Slide 2
1. Introduction
ITs for IP1 and IP5 have new design and the coating is integrated (deployed in the lab).
ITs for IP2 and IP8 have to be coated in-situ.
a-C coatings are in the HiLumi baseline to reduce heat load to the beam screens of the Inner Triplet magnets.
The in-situ coating technology is mature to go in the tunnel.
VSC proposes to coat Q5R2 during YETS. (with CRG support)

## Slide 3
2. Why to coat Q5R2 in YETS
it is the last opportunity before LS2;
allows to measure the heat load reduction;
disentangle photoelectron emission from electron multipacting.
It’s a stepping stone before the large scale deployment of a-C in the Triplets in LS2 (16 magnets + 4 DFBX) :
The technology is mature enough.
Schedule & resources cope with YETS (CRG & VSC).

## Slide 4
3. The technology is mature enough
Coated e-cloud detector installed since 2008 maintains the initial performance (no e-cloud).
~ 300 meters of the SPS already coated. (Half coated in the laboratory during LS1 and half done in-situ during EYETS)
COLDEX confirms performance at low temperature
(no e-cloud, good vacuum behaviour)
Tested in the SPS

## Slide 5
3. The technology is mature enough
Maximal SEY remains below 1.1 along 10 meters of BS
Laboratory tests

## Slide 6
3. The technology is mature enough
Maximal SEY remains below 1.1 along 10 meters of BS
Laboratory tests
Ti ~500 nm
C ~90 nm

## Slide 7
3. The technology is mature enough
Maximal SEY remains below 1.1 along 10 meters of BS
Laboratory tests
Yield strength of annealed copper ~50 MPa
Oxidized Cu
Fresh
clean Cu
Passivated Cu
Heavily contaminated
5 MPa =
50 Kgf/cm2
Good adhesion: peel-off never observed even after 10 thermal quenches from RT to 77K (dipping in LN2)
coating
10 x quench to 77K
Glue dollies
Cure 2h@150oC
pull test

## Slide 8
4. Schedule & Resources
Tasks
Cool coated Mag to 20 K
7 days
Open beam vac
1 day
Coating
10 days
Close beam vac
1 day
Pumpdown
7 days
Cool sector to 20 K
7 days
68 days
+ 9 contingency ~ 11 weeks
Remove He
6 days
Warm up
21 days
Cooldown to 1.9 K
14 days
ELQA tests
1 day

## Slide 9
4. Schedule & Resources
Planning & resources
w50 | w51 | w52 | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W9 | W10 | w11 | w12
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 
2017 | 2018
Dec | Jan | Feb | March
Warmup
CRG+VSC
Coating
VSC
remove He
CRG
Pump Mag
VSC
cool coated Mag 20K
CRG
cool sector 20K
CRG
cool all 1.9K
CRG
ELQA
Start hardware commissioning
Working
during
Annual closure

## Slide 10
4. Schedule & Resources
Planning & resources
w50 | w51 | w52 | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W9 | W10 | w11 | w12
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 
2017 | 2018
Dec | Jan | Feb | March
Warmup
CRG+VSC
Coating
VSC
remove He
CRG
Pump Mag
VSC
cool coated Mag 20K
CRG
cool sector 20K
CRG
cool all 1.9K
CRG
ELQA
Start hardware commissioning
Working
during
Annual closure
CRG & VSC can ensure the required manpower

## Slide 11
5. Risk assessment
Bad SEY (>1.2): the coating will condition faster than the Cu surface.
V. Baglin
LHC report 471
CERN 2001
R. Larciprete
ECLOUD12
2012
“bad SEY”
a-C
Threshold for the IT

## Slide 12
5. Risk assessment
Bad SEY (>1.2): the coating will condition faster than the Cu surface.
Real size deployment on a BS already exposed to the beam is scheduled for October 2017 (MB1007).
MB1007
removed from LHC in LS1 and kept in air since then.

## Slide 13
5. Risk assessment
Bad SEY (>1.2): the coating will condition faster than the Cu surface.
Real size deployment on a BS already exposed to the beam is scheduled for October 2017 (MB1007).
21 days for warming up to be confirmed.
No concerns with the RF fingers.

## Slide 14
6. Conclusions
To coat Q5R2 is an important stepping stone to go for the Triplets. (Do it in 1 before going for 20)
YETS 2018 is the last opportunity before LS2.
The technology is mature enough.
Mandatory tests before going to the tunnel: coat & test MB1007 and verify warmup in 21 days.
Still hard work ahead but we’re confident.

## Slide 15
6. Conclusions
Still hard work ahead but we’re confident.

## Slide 16
6. Conclusions
To coat Q5R2 is an important stepping stone to go for the Triplets. (Do it in 1 before going for 20)
YETS 2018 is the last opportunity before LS2.
The technology is mature enough.
Mandatory tests before going to the tunnel: coat & test MB1007 and verify warmup in 21 days.
Still hard work ahead but we’re confident.

## Slide 18
Resistance to radiation

## Slide 19
3. The technology is mature enough
Resistance to radiation & adhesion
Doses calculated by F. Cerutti (whole life of HiLumi):
1 GGy for triplets in IP1 and IP5
100 MGy for IP8 (and negligible for IP2)
Copper
a-C coating for SPS
C / Cu oxidised
C ~ 400nm
At the time, a-C for LHC was not available => tests in SPS type a-C coating

## Slide 20
3. The technology is mature enough
Resistance to radiation & adhesion
Doses calculated by F. Cerutti (whole life of HiLumi):
1 GGy for triplets in IP1 and IP5
100 MGy for IP8 (and negligible for IP2)
At the time, a-C for LHC was not available => tests in SPS type a-C coating
5 MPa = 50 Kgf/cm2
200 MGy
1GGy
1GGy
IP1 & IP5
Test 1 @ TRAD
Test 2 @
Uni Padova
IP8

## Slide 21
3. The technology is mature enough
Resistance to radiation & adhesion
Doses calculated by F. Cerutti (whole life of HiLumi):
1 GGy for triplets in IP1 and IP5
100 MGy for IP8 (and negligible for IP2)
Copper
Ti
~ 500nm
a-C coating for LHC
2 interfaces
C / TiM
Ti / Cu oxidised
Gradient of composition and carbide bonding:
Good adhesion and stable.
C ~ 50nm
Ti mixes with Cu oxide: good.
Thinner is the Ti, lower the stresses, better the adhesion
What is different for LHC type a-C?

## Slide 22
SEY along 10 meters

## Slide 23
3. The coating process
10 meters
1 spool for mechanical cable
+
2 spools for electrical cables
1 spool for mechanical
cable
Cold bore + beam screen
Ar injection
Turbo molecular
pump
1st step: Ti pre-coating

## Slide 24
3. The coating process
10 meters
1 spool for mechanical cable
+
2 spools for electrical cables
1 spool for mechanical
cable
Cold bore + beam screen
Ar injection
Turbo molecular
pump
1st step: Ti pre-coating
2st step: carbon coating ~90 nm (with Ti flashes)

## Slide 25
3. The coating process
With bakeout: Ti 100 nm + 200 nm (flashes)
No bakeout: Ti 400 nm + 200 nm (flashes)
Required by HL-LHC
Results from runs in 10 m BS
To Bake is excluded for YETS but under study for LS2

## Slide 26
Particle generation

## Slide 27
2- State of the art of the in-situ a-C coatings
Particle generation
Particle counter:
2 StSt tubes measured in clean-room
1 coated with carbon
1 reference (in the lab. with plastic covers)
both measured again in clean-room
No increase after shaking and gentle hammering the chamber.
Tests for the SPS: no difference between coated and uncoated beam pipes.
New particle counter setup and procedure being implemented: the goal is to measure in beam screens.
No increase for a chamber left in air for months. (flanges closed)

## Slide 28
COLDEX

## Slide 29
2- State of the art of the in-situ a-C coatings
a-C carbon tested in COLDEX
By R. Salemme

## Slide 30
Sputtering source

## Slide 31
Development of the coating source
Displacement of the sputtering source.
Magnetron sputtering
3. Application to accelerators: LHC

## Slide 32
Scenarios for LS2&LS3

## Slide 33
4- Planning & resources
Coat BS already exposed to LHC beam (MB1007)
10/2017
Ion etching
UV lamps
LS2
or
LS3?
25 weeks
(1 physicist + 1 technician + 2 coating setups)
20 weeks
(1 physicist + 1 technician + 2 coating setups)
Possible to warmup Q2R2 in 21 days?
CRG
MSC
VSC
CRG
VSC
Implement in-situ surface pre-processing
Not OK
Coat Q5R2 (?)
YETS 2018
OK
Are the 2 coating setups ready on time?
Beyond ITs
ITs
OK
CRG
VSC

## Slide 34
4- Planning & resources
LS2
LS3
ITs
BITs
1
1 team => 6 mSv
ITs
BITs
2
team 1 => 2 mSv
team 2 => 4 mSv
ITs
BITs
3
1 team => 4 mSv
1 team => 10 mSv
ITs
BITs
4
1 team => 30 mSv
ITs
BITs
5
team 1 => 10 mSv
team 2 => 20 mSv

## Slide 35
Choice of the magnet

## Slide 36
5. Choice of the magnet to coat
Outcome from VSC and CRG iterations
Standalone
(Q6 or Q5)
Doublet
(Q4/D2 pair)
Disadvantages:
requires opening of interconnect, cutting of PIM, addition of cryo instrumentation.
PIM welding & cryostat closure cannot be started until aC coating is compete;
more beam screens to coat (in series).
Advantages:
no opening of interconnects required;
degraded insulation vacuum can be repumped to avoid cold spots on QRL jumper vacuum barrier.
Advantage:
Can observe results in dipole and quad;

## Slide 37
5. Choice of the magnet to coat
Outcome from VSC and CRG iterations
Standalone
(Q6 or Q5)
Sector 7-8 & 2-3 are targeted by CRG for heat load balancing strategy.
Q6L8, Q6R2 attached to arc cryostat so insulation vacuum cannot be degraded for cryo warmup.

## Slide 38
5. Choice of the magnet to coat
Outcome from VSC and CRG iterations
Standalone
(Q6 or Q5)
Q6L8, Q6R2
Q6R7, Q6L3 difficult access.
Sector 7-8 & 2-3 are targeted by CRG for heat load balancing strategy.

## Slide 39
5. Choice of the magnet to coat
Outcome from VSC and CRG iterations
Standalone
(Q6 or Q5)
Q6L8, Q6R2
Q6R7, Q6L3
Sector 7-8 & 2-3 are targeted by CRG for heat load balancing strategy.
Q5L8 has cryo instrumentation problem and a non-conformity with missing cryosorber on beamscreen.

## Slide 40
5. Choice of the magnet to coat
Outcome from VSC and CRG iterations
Standalone
(Q6 or Q5)
Q6L8, Q6R2
Q6R7, Q6L3
Sector 7-8 & 2-3 are targeted by CRG for heat load balancing strategy.
Q5L8
Q5R2 chosen as baseline (for now… CRG still inquiring)

## Slide 41
5. Choice of the magnet to coat
Outcome from VSC and CRG iterations
Q5R2 layout

## Slide 42
5. Choice of the magnet to coat
Outcome from VSC and CRG iterations
Q5R2 layout
320 mm
320 mm