## Slide 1: WPO – ITN management & HR
Seamus Hegarty
HR-RPM
12-month review, 1.10.09

## Slide 2: Deliverables
WP0 deliverables defined in Annex I :
  Annual S&T and management/financial reports to the Commission
  Prepare workshops & training events indicated in tables 7 & 8 in sections 2.3.1 & 2.3.2.
  Final S&T and management/financial report to the Commission
Other actions which we consider as deliverables but not in Annex I

## Slide 3: Budget / Monitoring
25% of ACEOLE contract run so far
30% of training budget spent
Individual expenditure follow-up tool coming
1st full periodic report not due until 2010
Progress report for 1st year being compiled now

## Slide 4: Workshops & training events
Funding so far to :
  CHEP, Prague, April 09
  TWEPP, Paris, September 09
Other events to follow in years 2-4

## Slide 5: Recruitment
Researchers
  15 recruited : 12 ESRs + 3 ERs
  2 ERs have already finished
  recruitment in 2 main batches July 08 & March 09
  good nationality spread
  2 ERs still to be recruited
Visiting Scientists
  work in progress

## Slide 6: Management meetings
Kick Off – 2 October 2008
6 month – 2 April 2009
12 month – 1 October 2009
Other meetings with WP Leaders

## Slide 7: Secondment
A few secondments done – more coming
Some challenges at practical level – European Commission informed

## Slide 8: CDP & follow-up
CDPs done on time 
Good guidelines to help plan work, training and expenditure
Activity logs – common tool

## Slide 9: Awareness of rights
European Commission reminding us that recruited researchers should know their rights / entitlements
Salary at CERN as Fellow equates to EC’s :
  Living Allowance
  Mobility Allowance
  Travel Allowance
  Career Exploratory Allowance

## Slide 10: Extras delivered
Summer Review
Visits to Brussels / Project Officer
ACEOLE involvement in poster session being planned at CERN Dec 09
DAQ School in Ankara being planned Feb 10