## Slide 2: PS: Start up procedure and desiderata for 2018 as test case for post-LS2
Denis Cotte, Frank Tecker, Alexander Huschauer, Marc Delrieux, O.Hans, H.Damerau and the BE-OP-PS crew

## Slide 3: Draft 2018 Injectors schedule - Q1
HW test/commissioning + Cold Check-out : tight planning for PS-RF following EN/EL works.
No access in PS-SWY from the 27th March. (detailed planning next slide by O.Hans / M.Delrieux)
First beam expected Friday 9/03/2017 in PS.
Beam Commissioning : Setting up of MTE and LHCINDIV as first beam for SPS on the 16/03.
Check PS-MU realignment (14Gev Orbit) performed during YETS. -> MU73
Beam Commissioning : Setting up of AD, East Area, nTOF beams from the 23rd of March.
Pb in PS from the 30th of April 2017. Pb to SPS on the 4th of June.
HW Test
Beam Commissioning
Notes: Fermeture du PS le 16 Fevrier. -> shit 2p no night , no week-end
3 semaines des HW test Cold check-out.

## Slide 4: Draft 2018 Injectors schedule - Q1
HW test & Cold Check-out planning by O.Hans

## Slide 5: Draft 2018 Injectors schedule - Q1
From Week 10: play all cycle that will be used LHCPROBE, LHCINDIV, MTE and also everything that can be done w/o beam.
All 2017 operational cycles will be cloned (2018) with only 1 year of setting history.
Other cycles (ex : no-MHS) will be deleted or archived.

## Slide 6: MAIN YETS17-18 WORKS impacting HW COMMISSIONING
5 (+1 spare) power converters (C40/C80) will be upgraded to FGC3 – (TE-EPC/BE-RF)
Very special attention on Central Building equipment due to decabling/cabling campaign (all equipment in B353 & B359 can be impacted) .(EN-EL)
Extraction kicker FESA class upgraded (KFA71) + external condition + SIS interlock
Septum 16,23,42 replacement. (TE-ABT)
BE-BI equipment : new PI.BTVI42(one cable), new FWS54(electronic 09/18), new SemGrid48/52/54(electronic 10/18), SemFil277(repair), BGI82(chip3), exchange of FWS85V(calibrated)
Installation and test of PSC10 400W Driver amplifiers (BE-RF)
Replacement of 16 Magnets (QDN) in TT2.(TE-MSC, TE-VSC)
Interlock renovation via PLC for 200MHz(+power), 20MHz (BE-RF)

## Slide 7
Injection septum ER.SMH11
53 power converters in the ring
17 (old) power converters in transfer line
  Check control of the devices from CCC: working sets, Knobs, Makerules…
  Check acquisition AQN value, OASIS (+ samplers)
  Check PFW regulation  overshoots, ripples
  Check SIS protection for QFNs, QDNs
  For kickers check timings, fine delays, OASIS
  Check logging
Power converters (mainly POWM1553, FGC53, FGC61) :
EXISTING HARDWARE
Septum (STEP-V, ABT_SeptaMotion, Tps15RemMov) :
  Check control of the devices from CCC
  Check acquisition and motion
  Check logging
Kickers inj (KFA45, KFA28), ej(KFA71-79), MTE(KFA4,13,21, BFA9P) :
  Check control of the devices from CCC (spec app or Wset/knobs+Makerules)
  Check acquisition and OASIS
  Check logging

## Slide 8
Beam instrumentation: FWS, SemFil, SemGrids, BTV, BCT, BPMPS, BBQ, BSM, BLM (ACEM, IC, DIAMOND), BGI :
  Check control and applications from CCC
  Check logging
  Check OASIS
  Check BGI kick compensation
BGI82 H
BLMs + DIAMOND
Q meter
BPMPS (TMS)
BTV
SemGrids
WireScanners

## Slide 9
  Check control from CCC: working sets / Knobs
  Check OASIS
  Check Logging
Internal dump TDI47/48:
  Check control from CCC: working sets
  Check MakeRules / Samplers
  Check OASIS
RF system High Level and TFB :
Mechanism
Dump core
Dumping movement
Acceleration
2.8 – 10 MHz
200 MHz
Longitudinal blow-up
40 MHz
RF Manipulations
20 MHz
80 MHz

## Slide 10
  Check External condition
  Check Trains (B, C, RF, REV)
  Check Synchro
  Check SIS interlocks
  Check Applications:
    MTG Diag
    TGM Video
    CBCM
    TIMDiag
CO systems:
  Check Correctors : 50xPR.DHZ, 20xPR.DVT
  Check Low Energy Quads : 40xPR.QD/QF
    PR.QDW18 reverse polarity
  Check Skew Quads : 40xPR.QSK
  Check Multipoles : 10 circuits
  Check Bumpers/QKE : 15 circuits
  Check Transition DB/TR : 4 circuits
  Check also polarity on OASIS !
Polarity Tests:
40 MHz
Polarity check list
20 MHz
80 MHz
INCA/LSA cycle:
  Check Optics
  Check Incorporation Rules
  Check MakeRules

## Slide 11: PS 2018 commissioning part 1
Week 11
SFTPRO, and LHCINDIV
Re-commissioning of H8/H16 Beam Control with MHS-CRS.
Setting up of 2 MTE type beams requested by SPS.
Transverse feedback
needed
LHCINDIV:
Energy matching with PSB
Mar 09, 2018
Start beam commissioning
Mar 16, 2018
SFTPRO (MTE) to SPS Ip~200e10 (10us) island + core
Ip~50e10 (2us) core only
LHCINDIV
Mar 09, 2018
TOF-like cycle (or MTE H8)
LHCINDIV(H16Li)
Establish injection, acceleration to 14/20 and 26 Gev, fast extraction
Check all pick-up signals with beam (BPMOPS)
Mar 20, 2018
LHCPROBE (PILOT) to SPS
Week-end: Polarity checks of LEQ and DHZ/DVT with beam
TT2 kick response.
Test C40/80MHz
Week end 10-11 Mar
Check realignment performed during YEST with MU73. (@14Gev with YASP)
Do we need another iteration ?
Mar 12, 2018
Mar 13, 2018
Possible realignment
Mar 15, 2018
Mar 16, 2018
Phasing of 40MHz
Phasing of 80MHz
Complete longitudinal setting-up of LHCINDIV
LHCINDIV
Phasing of 200MHz
Blow-up operational
LHCINDIV:
Recommissioning of MHS-CRS for H16Li Beam control
SFTPRO(MTE)
Ip~1e13
Adjust and improve the Shadowing TPS15 - SMH16 with Diamond BLMs & High Energy orbit correctors DHZ_OC
Mar 14, 2018

## Slide 12: PS 2018 commissioning part 2
Mar 09, 2018
Start beam commissioning
Mar 26, 2018
LHC25ns standard 12b to SPS
Mar 23, 2018
Protons to EA, nTOF, AD targets
Mar 30, 2018
Start of nTOF, EA, physics
Setting up of TOF, EAST_Irrad, EAST_North, AD, LHC25ns12b
Mar 29, 2018
Start AD physics
Vacuum sublimation start
Apr 30, 2018
Start beam commissioning for Pb
Apr 30, 2018
Check new destination LEIRDUMP when we play spare cycles
Tuning of one C80MHz cavity for ions.
June 4, 2018
Pb beam to SPS
Setting up of EARLY/NOMINAL beams in PS
TOF-EAST-AD cycle
Establish injection, acceleration to 20/24 and 26 Gev
Basic setting-up by OP
Phasing of 20MHz cavities
LHC25ns(multi-bunches)
Mar 17/18 2018
AD:
Recommissioning of MHS-CRS for HSWP Beam control
Mar 19, 2018
Mar 20, 2018
LHC25#12b:
Recommissioning of MHS-CRS for LHC Beam control

## Slide 13
Milestone or improvement for 2018
New tools coming from Injector settings management WG :
  Cycle Generation : move the generation of PFW basic functions and drive tune and chromaticity directly into LSA. (high level parameter)
  Use the particle type, charge and mass to automatically generate settings dependent on charge to mass ratio; incorporate the Brho in the transfer line beam process type to get the settings automatically generated according to this. (like in SPS and LEIR)
Auto-Q : used in 2017 to stabilize the tune at low energy. -> to be done with PFW for high energy part.
New tools to be tried out together with PSB: injection steering with line optimisation between PSB and PS. (YASP)
LHC Beams : Last turn logging (need an extra WCM), BQM in PS ?, automatic energy matching measurement.
High level parameter showing the successive harmonic changes during the cycle -> then a stable phase calculation.
Framework to measure and store references for power converter. (already available in CTF)

## Slide 14
Summary
Tight HW test planning
  Constraint due to late lock-out, which prevents the equipment testing before the HW commissioning. Once the power is back it takes time to get back operational conditions (water, vacuum, etc.,.)
  In future, we must make sure to allocate sufficient time for equipment experts to test their equipment. (same as PSB)
Special attention on Central Building equipment EN/EL Cabling/Decabling campaign
  We will surely find several cables to be repair/pull. This extra work can delay the planning.
Much less migration from POWM1553 to FGC this year compared to 2017 and 2016.
Tight beam commissioning schedule.
  It mainly depends on the need to realign the PS machine.
Many new improvements foreseen in 2018 to facilitate operation, beam commissioning and HW tests.