## Slide 1
EP TSO Meeting
Electrical Work in EP Buildings
Gilles MAIRE EP/DI-SO
EP Electrical Safety Officer (ESO)

## Slide 2
Outline
EP Electrical Safety Officer (ESO) Function.
EP Buildings Electrical Inspection.
EP Buildings Appraisal.
Action Plan.
Summary.

## Slide 3
EP Electrical Safety Officer (ESO) Function
Part of the Safety Office, especially for the electrical safety aspects.
Electrical Inspection of experiments. Improvement of non-conformities.
AUL Improvement of experiments. This year upgrade for COMPASS, CAST and AD, work will be done during YETS.
Advice on request.
Electric accident analysis, study and implementation of improvement.
AUL Improvement of workshops. This year upgrade of Building 3 workshop.
EP Building non-conformities.
In case of doubt about your electrical installation.
In case of new electrical equipment on your experiment.
In case of problem with AUL or AUG.
Don’t hesitate to contact your Safety Correspondent OR EP Electrical Safety Officer.

## Slide 4
EP Buildings Electrical Inspection
Organization
Electrical Inspection for each building every year.
Performed by a specialized external company (APAVE, DEKRA, etc…).
Supervised by HSE.
Report stored in EDMS.
Electrical non-conformities have not been treated for several years.
For the safety of people, it was urgent to do improvements.
Type of Non-conformities
Labelling.
Earth.
Obsolete material (circuit breaker, electrical plug, electrical box, etc).
Safety Lights.
Etc…

## Slide 5
EP Buildings Appraisal & Action Plan
Status in June 2017
98 Buildings under EP responsibility.
1005 Electrical non-conformities.
Status end of 2017
Building 11, 40, 216, 222, 1, 2, 3, 4, 13 in progress.
213 non-conformities treated, in collaboration with HSE & SMB.
2018
Continue with priority order.
In function of human and financial resources of SMB.
Priority Order
Number of occupants / building.
Number of Electrical non-conformities / building.

## Slide 6
Summary
Very important work to insure the safety of people.
Have an electrical installation respecting the rules.
Lot of work to treat EP buildings non-conformities.
SMB dependence for resources.
Work with TSO in 2018 for some non-conformities.
Don’t hesitate to contact me for any electrical problem.

## Slide 7
Thanks for your attention.
Any questions