## Slide 2
225 GeV MD

## Slide 3
225 GeV injection into LHC
The main phases of the 225 GeV test have been identified as:
  1. SPS circulating beam: new 225 GeV dedicated cycle;
  2. Beam extraction and transfer lines (to downstream TEDs);
  3. LHC injection: threading and RF capture;
  4. LHC circulating beam: correction and measurement;
  5. LHC ramp: from 225 to >450 GeV.

## Slide 4
Systems impacted
SPS (new cycle, extraction, …)
TLs (new energy, aperture, trajectory)
Injection (kicker settings, BETS, …)
RF (capture, frequency, ramp functions, ...)
Power converters (functions, stability, new settings for optics, …)
Magnets (dynamic effects)
Interlocks (HW, BETS, SIS, …)
Instrumentation (dynamic ranges, BLM thresholds, …)
LHC feedbacks
Beam dump (BETS, energy tracking, MKD/B switch voltages, …)
Collimators (ramp functions, …)
Anything else??

## Slide 5
Main actions needed
Check of any urgent tests needed for YETS!!
Precise definition of:
  All systems and functionalities affected
  List of actions to be performed, including timing of each intervention/modification + List of corrective actions
Test all power converters at minimum stable current level (by specification) – done (TS#1)
New injection optics to improve requirements for critical magnets - (under discussion)
Extend all calibration curves according to new optics requirements with magnetic model/measurements
Procedure to be written, circulated and approved

## Slide 6
Main tunnel and remote interventions
Intervention | Need re-qualification after?
Modification (EXTENSION?) of BETS tables (extraction, injection, dump), FPGA coded in the control HW | YES, could it be done during the YETS?
LHC safety beam flag extension (SMP firmware modification) | Defined to 0 GeV, it’s maybe OK?
Set current interlock on main dipole PC | it prevents proper magnetic cycle
LHC energy flag (sent via extraction BIC) modification | ??
LHC injection kicker strength adjustment | YES
SPS extraction bump and kicker strength adjustment | YES
Creation and test of new SPS\LHC cycle | NO
LHC several interlock masking | NO
SPS extraction interlock masking | NO
BLM modification? | ???

## Slide 7
Technical stop option vs LS2
The technical validation implies activities normally not done after a TS, like re-validation of BETS tables, SMP flag, etc…
An additional 24h (??) should be considered to revalidate the interlocks (better estimate must be done)
This time would not be needed if the test is done just before LS2
At the end of the run:
  Increased risk of missing the opportunity
  Availability of p not clear. RF frequency range (400.765 MHz => 400.810 MHz) does not allow the test with IONS (400.767 MHz needed)

## Slide 8
Outlook and follow-up
Re-convene and update team who is already working on this subject
Endorsement @Chamonix?
Starting from March/April 2018, regular meetings to advance with the preparation, documentation, intermediate tests and deployment
Will be strong links to MPP at certain stages