## Slide 1: Summary of LS2 ECRs LIU-PSB Scope
T. Birtwistle (EN-ACE-CL)
LIU-PSB meeting 6th March 2018

## Slide 2: Information
The following slides cover only LIU-PSB scope. However, we do also require ECRs for other activities where a change impacts on “Form, Fit or Function”
Please use the correct template for ECRs, available here: https://quality.web.cern.ch/templates
Where relevant, integration studies must be done and contained within the ECR, in advance of the formal ECR approval process:
  Please contact the integration team (Jean-Pierre Corso)
  ICL (integration) meeting once every ~2 weeks (Wednesday)
If you have an LIU-PSB activity that is missing from the lists, and you think an ECR may be needed, please contact me
2018-03-06

## Slide 3
Description | Group | Responsible | ECR Reference | ECR Status
Upgrade of the BTP Line | All | Wolfgang Bartmann |  | Needed
Replace extraction kicker BEr.KFA14L1 (same size, but potential implications on impedance) | TE-ABT | Luc Sermeus |  | Needed
Add a new BPM on the BI line (upstream of BI.SMV10) | TE-ABT / BE-BI | Lars Soby / TE-ABT | SRR approved PSB-LJ-EC-0013 | Needed
Installation of Upgraded PSB Recombination Septa BT.SMV10 (BT1 and BT4) | TE-ABT | Michael Hourican | 1459318 PSB-MSMIC-EC-0001 | Released
Installation of Upgraded PSB Recombination Septum BT.SMV20 | TE-ABT | Michael Hourican | 1459320 PSB-MSMID-EC-0001 | Released
Exchange KSW magnet in 16L4, 1L1 and 2L1 | TE-ABT | Luis Coralejo | 1422350 PSB-MKKSW-EC-0001 | Released
New distributor BI.DIS10 | TE-ABT | Wim Weterings | 1518483 PSB-MSMIA-EC-0001 | Released
New Septum BI.SMV10 | TE-ABT | Michael Hourican | 1561343 PSB-MSMIB-EC-0001 | Released
New injection region in the Booster 1L1 | TE-ABT | Wim Weterings | 1422358 PSB-L-EC-0001 | Released
LIU-PSB LS2 ECRs
TE-ABT
TE-ABT will write this, but support needed from other impacted groups
2018-03-06

## Slide 4
Description | Group | Responsible | ECR Reference | ECR Status
BT Line magnet upgrades and consolidation (including BT.BHZ10 and BR.BHZ151) | TE-MSC | Antony Newborough / TE-VSC | SRR approved (BT.BHZ10) PSB-LJ-EC-0010 | Needed
Upgrade of the BHZ Main unit bending magnets (including injection bending magnets and reference magnet) | TE-MSC | Antony Newborough |  | Needed (in work)
Replace BTM.BHZ10 by a larger magnet | TE-MSC | Antony Newborough | SRR approved PSB-LJ-EC-0011 | Needed
Damping Resistors on PSB Bending and Quad Magnets | TE-MSC | Antony Newborough | 1817987 PSB-M-EC-0001 | Under Approval
Booster Injection Transfer Line Magnet Upgrades and Consolidation | TE-MSC | Antony Newborough | 1494503 PSB-LJ-EC-0001 | Released
LIU-PSB LS2 ECRs
TE-MSC
2018-03-06

## Slide 5
Description | Group | Responsible | ECR Reference | ECR Status
Upgrade of PS Booster Corrector and Quadrupole Power Supplies | TE-EPC | Louis De Mallac | 1874665 PSB-R-EC-0005 | Under Approval
Booster Power House (BHP) Converters Upgrade | TE-EPC | Serge Pittet | 1868992 PSB-R-EC-0003 | Under Approval
Consolidation and upgrade of the power converters of the LT and LTB lines | TE-EPC | David Nisbet | 1851780 PSB-R-EC-0006 | Under Approval
Installation of the power converters for BI.SMV10 magnets for LIU PSB injection | TE-EPC | Jean-Marc Cravero | 1887658 PSB-R-EC-0007 | Under Approval
Installation of new Power Converters for PSB injection Qstrip, Correctors, Quad. | TE-EPC | Serge Pittet | 1821166 PSB-R-EC-0004 | Under Approval
New MPS for LIU Booster (POPS-B) | TE-EPC | Fulvio Boattini | 1643409 PSB-LJ-EC-0008 | Released
LIU-PSB LS2 ECRs
TE-EPC
2018-03-06
ECR title is misleading and will be updated for the next version

## Slide 6
Description | Group | Responsible | ECR Reference | ECR Status
New BLMs Installation in the LT, LTB and BI Lines for H- exchange monitoring | BE-BI | Christos Zamantzas |  | Needed
Installation of new BLMs on the PS Booster extraction lines | BE-BI | Christos Zamantzas |  | Needed
Wire Scanners (x8) in the PSB 4L1 and 11L1 | BE-BI | Raymond Veness | SRR approved PSB-LJ-EC-0004 | Needed
Relocation of BI.BTV30 | BE-BI | Stephane Burger | 1572803 PSB-LJ-EC-0006 | Released
Relocation of BT2.BTV10 and BT3.BTV10 in the PS Booster | BE-BI | Stephane Burger | 1494819 PSB-LJ-EC-0002 | Released
LIU-PSB LS2 ECRs
BE-BI
2018-03-06
Plus contribution of information for the BT, BTP Line and the new BPM in the BI Line (with TE-ABT)
Description | Group | Responsible | ECR Reference | ECR Status
The New PS Booster RF System (Finemet Cavities) | BE-RF | Mauro Paoluzzi | 1733551 PSB-ACWFB-EC-0001 | Approval Closed
BE-RF

## Slide 7
Description | Group | Responsible | ECR Reference | ECR Status
Removal of 2 beam stoppers (BI.STPFA and BI.STPSW) on the BI line | EN-STI | Edouard Grenier-Boley | 1835875 PSB-LJ-EC-0012 | In Work
New PS Booster Absorber in Period 8 | EN-STI | Inigo Lamas Garcia | SRR approved PSB-LJ-EC-0007 | Needed
LIU-PSB LS2 ECRs
Description | Group | Responsible | ECR Reference | ECR Status
HVAC system in the PS Booster | EN-CV | Gabor Petrika |  | Needed
Booster chilled water cooling plant consolidation (b. 361) | EN-CV | Gabor Petrika |  | TBC
Consolidation of the cooling plant for the Booster (b. 237?) | EN-CV | Gabor Petrika |  | TBC
EN-STI
EN-CV
Description | Group | Responsible | ECR Reference | ECR Status
New ERD1*7A switchboard | EN-EL | James Devine |  | Needed
EN-EL
2018-03-06
To be discussed if they could be combined into one ECR

## Slide 8
Description | Group | Responsible | ECR Reference | ECR Status
New LBE line plus infrastructure | EN-ACE | Aurelio Berjillos | 1805620 CPS-LJ-EC-0005 | Under Approval
Partial dismantling of Linac2 | EN-ACE | Aurelio Berjillos | 1688400 CPS-LJ-EC-0003 | Under Approval
Connection of Linac4 to BHZ20 | EN-ACE | Aurelio Berjillos | 1688387 CPS-LJ-EC-0002 | Under Approval
LIU-PSB LS2 ECRs
EN-ACE
2018-03-06

## Slide 9
Thanks for your attention