## Slide 1: Summary of LS2 ECRs LIU-PSB Scope
T. Birtwistle (EN-ACE-CL)
LIU-PSB meeting 19th June 2018

## Slide 2: General information
The following slides cover only LIU-PSB scope. However, we do also require ECRs for other activities where a change impacts on “Form, Fit or Function”
Please use the correct template for ECRs, available here: https://quality.web.cern.ch/templates
If you have an LIU-PSB activity that is missing from the lists, and you think an ECR may be needed, please contact me
2018-06-19

## Slide 3: Integration information
Due to the integration / design workload, the ECR process has been modified slightly:
  ECRs can be sent out ‘under approval’ without fully completed integration, so long as they contain at least a minimum of information (e.g. total volume required by equipment)
  This allows all other teams to be notified sooner and perform their checks (e.g. safety, impedance etc.)
  An ECR cannot be finally approved without a completed / validated integration study(ies)
Please continue to follow integration activities:
  ICL (integration) meeting once every ~2 weeks (Wednesday)
  Contact is Jean Pierre Corso
2018-06-19

## Slide 4
Description | Group | Responsible | ECR Reference | ECR Status
Upgrade of the PS Booster extraction lines BT, BTM and BTP | TE-ABT (input from others) | Wolfgang Bartmann |  | Needed
Magnet modifications in BT, BTM and BTP (including BT.BHZ10 and BTM.BHZ10) | TE-MSC | Antony Newborough | SRR’s approved: PSB-LJ-EC-0010 PSB-LJ-EC-0011 | 
Beam instrumentation modifications in BTP line (LIU related BTV changes in BT line already covered by a separate ECR) | BE-BI | Lars Soby |  | 
Installation of new BLMs on the PS Booster extraction lines | BE-BI | Christos Zamantzas |  | 
EN-STI beam stopper in BTP | EN-STI | Edouard Grenier-Boley |  | 
All related vacuum changes | TE-VSC | Jose Somoza |  | 
Include reference to the ECRs for the BT Line Septa | TE-ABT | Wolfgang Bartmann |  | 
LIU-PSB LS2 ECRs
Multiple Groups
Various contributions needed from groups for the overall ECR
2018-06-19

## Slide 5
LIU-PSB LS2 ECRs
Description | Group | Responsible | ECR Reference | ECR Status
Add a new BPM on the BI line (upstream of BI.SMV10) | TE-ABT, BE-BI | Christoph Hessler Lars Soby | SRR approved PSB-LJ-EC-0013 | Needed
Multiple Groups
Description | Group | Responsible | ECR Reference | ECR Status
Modifications to the Booster extraction main unit and BT1/4.BVT10, BT2/3.DVT10 (upto the BPMs) | TE-MSC, TE-VSC, BE-BI | Antony Newborough Jose Somoza |  | Needed
Multiple Groups
2018-06-19

## Slide 6
Description | Group | Responsible | ECR Reference | ECR Status
Replace kicker BT.KFA10 (same size, but potential implications on impedance) | TE-ABT | Luc Sermeus, Wim Weterings | 1955039 PSB-MK-EC-0001 | Under Approval (Int. need 3D models)
Replace extraction kicker BEr.KFA14L1 (same size, but potential implications on impedance) | TE-ABT | Luc Sermeus | 1955075 PSB-MK-EC-0002 | Under Approval (impedance checks ongoing)
Installation of Upgraded PSB Recombination Septa BT.SMV10 (BT1 and BT4) | TE-ABT | Michael Hourican | 1459318 PSB-MSMIC-EC-0001 | Released
Installation of Upgraded PSB Recombination Septum BT.SMV20 | TE-ABT | Michael Hourican | 1459320 PSB-MSMID-EC-0001 | Released
Exchange KSW magnet in 16L1, 1L1 and 2L1 | TE-ABT | Luis Coralejo | 1422350 PSB-MKKSW-EC-0001 | Released
New distributor BI.DIS10 | TE-ABT | Wim Weterings | 1518483 PSB-MSMIA-EC-0001 | Released
New Septum BI.SMV10 | TE-ABT | Michael Hourican | 1561343 PSB-MSMIB-EC-0001 | Released
New injection region in the Booster 1L1 | TE-ABT | Wim Weterings | 1422358 PSB-L-EC-0001 | Released
LIU-PSB LS2 ECRs
TE-ABT
2018-06-19

## Slide 7
Description | Group | Responsible | ECR Reference | ECR Status
Upgrade of the BHZ Main unit bending magnets (including injection bending magnet and reference magnet) | TE-MSC | Antony Newborough |  | In work
Damping Resistors on PSB Bending and Quad Magnets | TE-MSC | Antony Newborough | 1817987 PSB-M-EC-0001 | Under Approval (studies ongoing)
Booster Injection Transfer Line Magnet Upgrades and Consolidation | TE-MSC | Antony Newborough | 1494503 PSB-LJ-EC-0001 | Released
LIU-PSB LS2 ECRs
TE-MSC
Plus contribution of information for the BT, BTM, BTP Lines
2018-06-19

## Slide 8
Description | Group | Responsible | ECR Reference | ECR Status
Booster extraction septa transformers modifications (in tunnel) | TE-EPC | Jean-Marc Cravero |  | S. Pittet confirmed no change to volume
Upgrade of PS Booster Corrector and Quadrupole Power Supplies | TE-EPC | Louis De Mallac | 1874665 PSB-R-EC-0005 | Under Approval (integration needed)
Booster Power House (BHP) Converters Upgrade | TE-EPC | Serge Pittet | 1868992 PSB-R-EC-0003 | Under Approval (integration needed)
Installation of the power converters for BI.SMV10 magnets for LIU PSB injection | TE-EPC | Jean-Marc Cravero | 1887658 PSB-R-EC-0007 | Under Approval (integration needed)
Installation of new Power Converters for PSB injection Qstrip, Correctors, Quad. | TE-EPC | Serge Pittet | 1821166 PSB-R-EC-0004 | Under Approval (integration needed)
New MPS for LIU Booster (POPS-B) | TE-EPC | Fulvio Boattini | 1643409 PSB-LJ-EC-0008 | Released
Consolidation and upgrade of the power converters of the LT and LTB lines | TE-EPC | David Nisbet | 1851780 PSB-R-EC-0006 | Released
LIU-PSB LS2 ECRs
TE-EPC
2018-06-19

## Slide 9
Description | Group | Responsible | ECR Reference | ECR Status
New BLMs Installation in the LT, LTB and BI Lines for H- exchange monitoring | BE-BI | Christos Zamantzas |  | Needed
8 Wire Scanners in the PSB 4L1 and 11L1 | BE-BI | Raymond Veness | 1962159 PSB-BWSRA-EC-0001 | Under Approval
Relocation of BI.BTV30 | BE-BI | Stephane Burger | 1572803 PSB-LJ-EC-0006 | Released
Relocation of BT2.BTV10 and BT3.BTV10 in the PS Booster | BE-BI | Stephane Burger | 1494819 PSB-LJ-EC-0002 | Released
LIU-PSB LS2 ECRs
BE-BI
Plus contribution of information for the BT, BTP Line, the new BPM in the BI Line, and extraction line BLMs
Description | Group | Responsible | ECR Reference | ECR Status
The New PS Booster RF System (Finemet Cavities) | BE-RF | Mauro Paoluzzi | 1733551 PSB-ACWFB-EC-0001 | Approved, but integration model to be updated
BE-RF
2018-06-19

## Slide 10
Description | Group | Responsible | ECR Reference | ECR Status
Removal of 2 beam stoppers (BI.STPFA and BI.STPSW) on the BI line | EN-STI | Edouard Grenier-Boley | 1835875 PSB-LJ-EC-0012 | Under Approval (vacuum chamber models/design needed)
New PS Booster Absorber in Period 8 | EN-STI | Inigo Lamas Garcia | Draft only so far | In work (visit on site this morning)
LIU-PSB LS2 ECRs
Description | Group | Responsible | ECR Reference | ECR Status
Ventilation system in the PS Booster | EN-CV | Gabor Petrika |  | Needed (delayed)
Consolidation of the Booster chilled water plant (b. 361) | EN-CV | Gabor Petrika | Draft only so far | In work (integration needed)
Consolidation of the Booster cooling plant | EN-CV | Gabor Petrika | Draft only so far | In work (integration needed)
EN-STI
EN-CV
Plus contribution of information for the stopper in BTP line
2018-06-19

## Slide 11
Description | Group | Responsible | ECR Reference | ECR Status
New LBE line plus infrastructure | EN-ACE | Aurelio Berjillos | 1805620 CPS-LJ-EC-0005 | Under Approval (integration needed)
Partial dismantling of Linac2 | EN-ACE | Aurelio Berjillos | 1688400 CPS-LJ-EC-0003 | Under Approval (final verification of equipment responsibilities ongoing)
Connection of Linac4 to BHZ20 | EN-ACE | Aurelio Berjillos | 1688387 CPS-LJ-EC-0002 | Ready, but to be approved at the same time as: CPS-LJ-EC-0003
LIU-PSB LS2 ECRs
EN-ACE
2018-06-19

## Slide 12
Thanks for your attention