## Slide 1: BA6 Crab cavity test-stand YETS sequencing
EDMS 1843665
SPS crab-cavity test stand activities in YETS2017-2018
Giovanna Vandoni

## Slide 2: Worksite in BA6
BA5
BA1
Helium pump zone
Cryogenic pipework
BA6 – surface area
Cryogenic compressor skid
Oil removal skid
TA6 - alcove
Cryogenic Cold-Box
ValveBox#1
LN2 phase separator
Connecting flexibles and pipework
61739 Crab zone
ValveBox#2
Transfer Table
SB + cryomodule
RF equipment and waveguides
Vacuum beamline
ODH and Alarms
From TS6- to TS6+

## Slide 3: Cryogenics layout
80m
Cryogenic transfer line
Warm pipework
ValveBoxes #1 and #2
CCCM + Service Module
VB#1
Cold-box = the “fridge”
VB#2
Compressor
Oil removal
LN2 tank
LN2 line

## Slide 4: Activity zones
He pump zone
Crab cavity zone
RAL
TA6

## Slide 5: Crab-cavity test-stand
Cryogenic distribution line
RF power waveguides
New handling rails
Cryogenic distribution line
Crab-cavity cryomodule
Y-chamber
RF power waveguides
Moving Transfer table

## Slide 6: Cryomodule and Service Box

## Slide 7: Crab cavity zone
Transfer Table
ValveBox#2
Heater tank
RF Circulator & Load skids
Y-chamber
Y-chamber

## Slide 8: Crab cavity zone

## Slide 9: Crab cavity zone
Transport Lane

## Slide 10: Crab cavity zone
Helium pump zone

## Slide 11: Crab cavity zone
ValveBox2 zone

## Slide 12: Crab cavity zone
Crab-cavity zone

## Slide 13: Crab cavity zone
RF-connections zone

## Slide 15
19-20 Dec : MAGNET TESTS
15 Jan, 5am to 10am: AUG Tests
27-28 Jan : Auto transfer tests EN/EL
22 Feb : Global Access test
8/1 Transfer Table arrival
17/1 Cryogenic Refrigerator
22/1 Cryomodule in tunnel
1/2 Flushing of cryolines
7/2 Start commissioning at 20K
28/2 Start cooldown of cryomodule
19 March Beam to SPS
Magnet transport week
Gaseous
Helium
Liquid
Helium
9/2 Demi water off 22/12
15/1
Raw water available

## Slide 16: 3 large blocks
CABLING
CRYOGENICS
TA6
Tunnel
BA6
TEST STAND
Transfer Table
RF equipment
CRYOMODULE
TA6
Tunnel
BA6 and ext
+ all the rest around this
ODH
Water, raw and demi
And of course, the rest of the SPS activities
Kickers
Magnet campaign
Lift maintenance
AUG tests
Access tests
D. Mcfarlane
Vacuum
A very important campaign with several clients
Priorities to be worked out together with EN/EL to distribute workload: new cables will NOT be available on day 1
Work partially at night to avoid coactivity and ensure efficient cabling activity

## Slide 17: Cabling for signals & power - DEADLINES
EN/EL/FC new cables and fibers |  | Deadline for use | 
Transfer Table | K.Artoos | 15/1 | week2
Mechanical instrumentation of CM | M.Guinchard | ? | ?
ODH | N.Broca | 14/2 | week 7
Cryogenics (to VB#2) | C.Fluder | 24/1 | week 4
Faraday cage LLRF | P.Baudrenghien | 9/2 | week 6
RF Powering | F.Killing | 9/2 | week 6
EN/EL/EIC Electrical distribution cabling and connections |  | Deadline for use | 
Energization of transformer | G.Velazquez | 15/1 | week2
Cryogenics | C.Fluder | 22/1 | week3
Transfer table | K.Artoos | 15/1 | week2
IOTs | F.Killing | 9/2 | week6
Faraday cage equipment | P.Baudrenghien | 15/2 | week7
….check, confirm, add

## Slide 18: Other Deadlines
SYSTEM | Contact | Commissioning
Transfer Table | K.Artoos | 17th Jan
Cryogenics refrigeration + distribution | S.Claudet | 1st Feb to 21st Feb
Cryomodule pumpdown | C.Pasquino/ J.Perez Espinos | 8th Feb
Faraday cage LLRF | P.Baudrenghien | 15th Feb
RF Power IOTs | F.Killing | 15th Feb
Cryomodule cooldown | S.Claudet | 28th Feb
EN/CV |  | 
Demi-water off | 22nd Dec 2017 | 9th Feb
Ventilation Faraday cage | Station arrives on | 8th Jan
Raw water | Needed in BA6 | 15th Jan

## Slide 19: Large Transports
DATES ARE INDICATIVE
Item | Contact | Date
Heater tank | J.Metselaar | 21st Dec
ValveBox#1 & VB#2 | J.Metselaar | 22nd Dec
Transfer Table | K.Artoos | 12th Jan
Circulator & Load skids | S.Calvo | 15th Jan
Service Box | G.Vandoni | 19th Jan
Cryomodule | G.Vandoni | 19th Jan
Cold-Box | J.Metselaar | 17th Jan
Compressor skid | J.Metselaar | 18th Jan
LN2 tank | J.Metselaar | 12th Jan

## Slide 23
Helium pump zone
In this zone, CRG manages all activities
Installation of heater tank
Installation and welding of pipework

## Slide 24
ValveBox#2 zone
61732
Installation of VB#2
and flexible lines
Connection to SB
Electrical racks
Vacuum lines
Cold Commissioning to 20K
is up to here

## Slide 25
ValveBox#2 zone
61732
Installation of VB#2
and flexible lines
Connection to SB
Electrical racks
Vacuum lines
Cold Commissioning to 20K
is up to here
Flushing 1st Feb
Cold Commissioning 20K starts 7th Feb

## Slide 26: TA6 alcove, cryogenic installation
Criotec
Rampower
Linde

## Slide 27: TA6 alcove, cryogenic installation
Criotec
Rampower
Linde
TE/CRG/ME Mechanics
TE/CRG/TE Controls
Criotec
Rampower
Linde
The LN2 line serves as reference for installation of phase separator and related lines
The LN2 phase separator is installed at height, in the shadow of the curb
This zone is entirely in the hands of TE/CRG
EN/EA: scaffold
EN/HE: cold box and VB#1
EN/CV: raw water
EN/MME X-rays
EN/EL/FC
EN/EL/EIC

## Slide 28: Scaffold on Day 1
Jos Metselaar

## Slide 29: BA surface buidling
Compressor skid and Oil removal skid
17th Jan 2018
LN2 tank
12th Jan 2018

## Slide 30: Cryomodule installation
…movie here…

## Slide 31: Transfer Table
8/1 | 9 | 10 | 11 | 12 | 13 | 14
Table delivery |  | VIC and trainings |  | Earliest start | Table installation | 
15/1 | 16 | 17 | 18 | 19 | 20 | 21
Cables & controls ready |  | Interlock tests | RF circulators and loads |  |  | 
22/1 | 23 | 24 | 25 | 26 | 27 | 28
CM + SB |  |  |  |  |  | 
Table movement under full load: 14-15 February

## Slide 32: Cryomodule installation
Access and presence only of required actors and experts: no bystanders
Procedure to be written

## Slide 35: Week 51
Joint VIC for EN/EL (distribution, cables, fibers)
VSC Dismounting vacuum line in crab zone
EN/EA Installation of scaffold in TA6
Connectors (RAL zone) /el. distribution (shaft)
Tunnel access only by keys
Priority to EN/EL, VSC, EN/EA for keys
No work under false floor in active cable zones
MONDAY
CONSTRAINTS
Patrol at 6h30 in the morning
Underground areas unaccessible
until Wednesday afternoon (~17h00)
TUESDAY to WEDNESDAY
Tunnel access now free
Work under false floor in active cable zones becomes possible
CONSTRAINTS REMOVED
(5 EN/EL/EIC)
10 EN/EL/FC
TE/VSC
EN/EA
4 EN/HE
Green light by J.Bauche for switching to open access
EN/EL/FC Connectors
EN/EL/EIC el. Distribution underground + 2 cables pulled under the false floors
WEDNESDAY
24 keys only

## Slide 36: Week 51
EN/EL/FC in the crab cavity zone
EN/EL/FC-fibers under the false floors and in crab cavity zone
Rampower in the TA6 alcove
Installation LN2 line in alcove
VIC Criotec
SMB/SE drilling of the wall for cryogenic pipework
Thursday: transport of the kickers for alignment & pumpdown Friday/ transport of heater tank
Friday: if kickers finished, installation of VB#1 and VB#2
THURSDAY -FRIDAY
If needed, can we install VB1 & VB2 on 4-5/1/2018?
THURSDAY -FRIDAY
EN/EL/FC in crab cavity zone and RAL
EN/EL/EIC continues underground

## Slide 37: Who’s Who
S.Mehanneche/ F.Galleazzi | Integration | 
J.Dalla-Costa | Field coordination | 
D.McFarlane | SPS Coordination | 
F.Bais | TSO SPS | 
J.Etheridge | EROS | 
G.Vandoni | Work responsible/ Field coordination | 
M.Garlasche | Cryomodule linkperson | 
C.Pasquino | Vacuum linkperson | 
J.Metselaar | Cryogenics linkperson | 
T.Slettestol/ G.Gros/ J.Blanc | EN/EL cabling (cabling & fibers) | 
K.Artoos | Transfer Table | 
S.Calvo | RF power and cables | 
S.Fumey | Transports for crab-cavity |