## Slide 1: EuCARD HFM
Task 3 : High Field Magnet

## Slide 2: Outline
Recall of Task content
Working group activities
Future work:
  Global planning
  Milestones
Conclusion

## Slide 3: Recall of task content
Design, build and test a 1.5 m long, 100 mm aperture dipole model with a design field of 13 T using Nb3Sn high current Rutherford cables. the model will afterwards be used to upgrade the superconducting cable test facility FRESCA at CERN from 10 T to 13 T
dipole model as a test bed for large high field accelerator magnets.
What | Who
Magnet design | CEA and CERN
conductor characterization | CERN
thermal design and thermal component tests | PWR , with CERN and CEA
Coils fabrication | CEA
Magnet assembly | CERN
Cryogenic tests | CERN

## Slide 4: Working Groups Activities
Specification Working Group
    Members : Ezio Todesco; François Kircher; Gijs De Rijk; Jean-Michel Rifflet; Jean-Pierre Koutchouck; Luc Oberli; Maria Durante
    No activity since june

## Slide 5: Working Groups Activities
Magnet Predesign Working Group
    Members : Ezio Todesco; Frank Borgnolutti; François Kircher; Françoise Rondeaux; Gijs De Rijk; Gleen Kirby; Jean-Michel Rifflet; Jean-Pierre Koutchouck; Maria Durante; Mélanie Bruchon; Pierre Manil
    At Saclay : P. Manil  “Search on documentation related to the project” This morning talk
    At CERN : 28/08/2009 : 1st EuCARD-WP7-Fresca2 magnet & conductor design meeting  “Dipole conceptual Design work at CERN” by Attilio Milanese
     “Options for coil ends” by Gijs de Rijk

## Slide 6: Working Groups Activities
Cable Design Working Group
    Members : « Acces denied »
    At CERN : 28/08/2009 : 1st EuCARD-WP7-Fresca2 magnet & conductor design meeting
     “Conductor Design and Procurement Strategy” by Luc Oberli

## Slide 7: Global Planning
 | 2009 |  |  |  | 2010 |  |  |  | 2011 |  |  |  | 2012 |  |  |  | 2013 |  |  |  | 
EuCARD HFM Task3 Start = 01/09/09 | T1 | T2 | T3 | T4 | T1 | T2 | T3 | T4 | T1 | T2 | T3 | T4 | T1 | T2 | T3 | T4 | T1 | T2 | T3 | T4 | Who
Annual Meeting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Analyse of Nb3Sn quad measurements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | CEA + …..
Collect existing documentation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | CEA + CERN
Fresca2 magnet specidfication |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | CERN +CEA
Comparative study of possible magnetic configurations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | CEA + CERN
Conceptual Design |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | CEA + CERN
Magnetic optimisation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | CEA + CERN
thermal studies |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | PWR + CEA
mechanical studies |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | CEA + CERN
Coils |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Coil components studies |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | CEA + CERN
Coil tooling studies |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | CEA + CERN
Coils components procurements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | CEA + CERN
Coils tooling procurements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | CEA + CERN
1st coil winding |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | CEA + CERN
2nd and 3rd coil winding |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | CEA + CERN
Magnet assembly |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Magnet assembly components studies |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | CERN + CEA
Magnet assembly tooling studies |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | CERN + CEA
Magnet assembly tooling procurements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | CERN + CEA
Magnet assembly components procurements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | CERN + CEA
Magnet assembly |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | CERN + CEA
Magnet test |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | CERN + CEA
 |  |  |  | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 |  | 
 |  | studies |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | porocurements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | realisation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | tests |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Milestones |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Planning Presented in June. End non consistant with Annex 1

## Slide 8: Global Planning revisited
New proposition
  End adjusted / Annex 1
  Studies reduced
  Shows interaction with French Special Contribution to CERN (Cex)

## Slide 9: Milestones
 | EuCARD HFM Task3 Milestones (Start = 01/09/09) | EuCARD deliverable | EuCARD Milestone
M6 | EuCARD HFM Task3 Start |  | 
M12 | Internal Review for confirmation of magnetic configuration |  | 
M12 | 1st EuCARD Annual meeting |  | 
M18 | Start of detailled studies |  | 
M24 | 2nd EuCARD Annual meeting |  | 
M24 | End of detailled studies |  | 
M36 | 3rd EuCARD Annual meeting |  | 
M36 | End of coil winding |  | 7.3.1
M42 | End of magnet assembly |  | 7.3.2
M48 | 4th EuCARD Annual meeting |  | 
M48 | Magnet Test results | 7.3.1 | 
Corrected to be in accord with Annex 1

## Slide 10: Conclusions (1/2)
It is mandatory to understand the bad behaviour of Nb3Sn Quad :
      Help for the analysis (Contacts with CERN, LARP ??, …)
Start of the task : 01/09/09
3 working groups are defined. started :
  Specification WG
  Cable Design WG
  Magnet Predesign WG
To help the WG, existing documentation should be collected (past studies). Started

## Slide 11: Conclusions (2/2)
Future work :
  Launch dedicated regular meetings for each working group (2 per month ?)  Video or phone conferences
  Launch task meetings (1 per month ?)  Video or phone conferences
  Prepare Design choice review ; comparison of the possible layouts ( electromagnetic and mechanic in 2D and 3D) (March 2010 ?)
  Procurement procedure nearly finished for 3 test length of 1 mm strand
  Procurement procedure nearly finished for furnace
  Discuss detailed planning with each laboratory
  Discuss ressources spending with each laboratory
  1rst interim report to be prepared before 10/10