## Slide 1: LIU EL-FC ACTIVITIES Updated on 17/01/2018
Patrick Lelong EN-EL-FC

## Slide 2
YETS17-18 PS cabling
N° PLAN | Action | OSVC (Provisional) | Contact | YETS 2017-2018 | DEC | N0 cables to be removed | DIC | N0 cables to be pulled | DIR | N0 of racks to be installed | DIF | N0 fibres to be pulled | Observations
10362 | New Power converters for 40-80 MHz cavities | C213AFB129 | Louis de Mallac | yes |  |  | Received | 6 |  |  |  |  | Installation ongoing
10362 | Ethernet for 40-80 MHz cavities (PC6) | C213AFB212 | J.Gomez Costa |  |  |  | Received | 1 |  |  |  |  | ~40m
10921 | PS Longitudinal Damper | C213AFB155 | Matthias Haase | yes | DEC Received | 12 | DIC Received | 30 |  |  |  |  | ~4km
10967 | Cabling for RF Sources | C213AFB122 | Heiko Damerau | yes |  |  | Received | 44 |  |  |  |  | ~1km No cabling in Bld 353 during Decabling!!! To be done in Week8
Postponed to LS2 (M. Haase on 13/10/2017)

## Slide 3
LS2 PS cabling (1/3)
N° PLAN | Action | OSVC (Provisional) | Contact | LS2 2019-2020 | DEC | N0 cables to be removed | DIC | N0 cables to be pulled | DIR | N0 of racks to be installed | DIF | N0 fibres to be pulled | Observations
10920 | RF-HP: 10 MHz System renovation baseline, upgrade of feedback amplifiers. (New gap relay development ) | C213AFB166 | Carlo Rossi | yes | Not Received |  | PRE-DIC Received | 44 |  |  |  |  | ~11km
11155 | PS 40/80 MHZ New Feedback Amplifiers | C213AFB173 | Carlo Rossi | yes |  |  | DIC Received | 45 |  |  |  |  | DIC Received 14/12/17 ~3.5km
10924 | PS 80 MHZ Fast Tuner | C213AFB167 | Carlo Rossi | yes |  |  | DIC Received | 9 |  |  | Not Received | 3 | DIC Received 14/12/17 ~600m(control)
10025 | PS internal dump SS47 or SS48 | C213AFC100 | F.X. Nuiry | yes |  |  | DIC Received | 6 |  |  |  |  | DIC Received 20/12/17 ~600m
11486 | PS ralentisseur upgrade SS12 or SS75 | C213AFB144 | F.X. Nuiry | yes | DIC Received | 1 | DIC Received | 3 |  |  |  |  | DIC Received 20/12/17 ~1km
10967 | Replace existing beam control by fully digital beam control | C213AFB168 | Heiko Damerau | yes |  |  | PRE-DIC Received | 256 |  |  | PRE-DIF Received | 25 | ~10km (Control cables) ~1.5km (Optical Fiber) Final DIC not before April (Heiko)
10437 | Renovation of BWS (including turn-by-turn). Prototype installed in PSB | C213AFB205 | J. Emery | yes | Not Received |  | DIC Received | 45 |  |  | PRE-DIF Received | ~32 | DIC Received 15/12/17 ~9km (Control cables) ~3km (Optical Fiber)
10349 | Manufacture and commission PI.SMH42 Power Converter BC 99270 | C213AFB206 | Jean-Marc Cravero | yes |  |  | EN-EL preparation Waiting for ECR | 1 |  |  |  |  | ~200m
10349 | Ethernet PI.SMH42 Power Converter | C213AFB165 | J.Gomez Costa | yes |  |  | DIC Received | 2 |  |  |  |  | DIC Received 15/12/17 ~150m
10349 | Interlock PI.SMH42 Power Converter | C213AFB169 | Richard Mompo | yes |  |  | PRE-DIC Received | 1 |  |  |  |  | Included in PS Interlock Renovation
10350 | Manufacture and commission PI.BSM42 Power Converter BC 99274 | C213AFB207 | Jean-Marc Cravero | yes |  |  | EN-EL preparation Waiting for ECR | 1 |  |  |  |  | ~100m
10350 | Ethernet PI.BSM42 Power Converter | C213AFB165 | J.Gomez Costa | yes |  |  | DIC Received | 1 |  |  |  |  | DIC Received 15/12/17 ~50m
10350 | Interlock PI.BSM42 Power Converter | C213AFB169 | Richard Mompo | yes |  |  | PRE-DIC Received | 1 |  |  |  |  | Included in PS Interlock Renovation

## Slide 4
LS2 PS cabling (2/3)
N° PLAN | Action | OSVC (Provisional) | Contact | LS2 2019-2020 | DEC | N0 cables to be removed | DIC | N0 cables to be pulled | DIR | N0 of racks to be installed | DIF | N0 fibres to be pulled | Observations
10351 | Upgrade and commission PI.BSM40, 41, 43 & 44 Power Converters BC 99275 | C213AFB208 | Jean-Marc Cravero | yes |  |  | EN-EL preparation Waiting for ECR | 4 |  |  |  |  | ~500m
10351 | Ethernet PI.BSM40, 41, 43 & 44 | C213AFB165 | J.Gomez Costa | yes |  |  | DIC Received | 5 |  |  |  |  | DIC Received 15/12/17 ~300m
10351 | Interlock PI.BSM40, 41, 43 & 44 | C213AFB169 | Richard Mompo | yes |  |  | DIC Received | 1 |  |  |  |  | Included in PS Interlock Renovation
10352 | low beta quadrupole PC BC 99269 | C213AFB209 | Jean-Marc Cravero | yes |  |  | EN-EL preparation Waiting for ECR | 1 |  |  |  |  | ~500m
10352 | Ethernet low beta quadrupole PC | C213AFB165 | J.Gomez Costa | yes |  |  | DIC Received | 2 |  |  |  |  | DIC Received 15/12/17 ~100m
10352 | Interlock low beta quadrupole PC | C213AFB169 | Richard Mompo | yes |  |  | DIC Received | 1 |  |  |  |  | Included in PS Interlock Renovation
10329 | TT2 renovation | C213AFB210 | K. Papastergiou | yes |  |  | EN-EL preparation | ~50 |  |  |  |  | EDMS: 1519674 ~7km
10329 | Ethernet TT2 Renovation | C213AFB164 | J.Gomez Costa | yes |  |  | PRE-DIC Received | 42 |  |  |  |  | ~3km
10809 | Renovation of the PS interlock system | C213AFB169 | Richard Mompo | yes | Not Received |  | PRE-DIC Received | 136 |  |  |  |  | ~10km
10811 | WIC machine protection TT2 | C213AFA132 | Richard Mompo | yes | Received | 117 | DIC Received | 114 |  |  |  |  | DIC Received 29/10/17 ~8km
11110 | Supply new converter for PS vertical IPM Magnets | C213AFA211 | Serge Pittet | yes |  |  | EN-EL preparation Waiting for ECR | 1 |  |  |  |  | ~500m
11110 | Ethernet for PS vertical IPM Magnets | C213AFB180 | J.Gomez Costa | yes |  |  | PRE-DIC Received | 2 |  |  |  |  | ~200m
11110 | Interlock for PS vertical IPM Magnets | C213AFA169 | Richard Mompo | yes |  |  | DIC Received | 1 |  |  |  |  | Included in PS Interlock Renovation

## Slide 5
LS2 PS cabling (3/3)
N° PLAN | Action | OSVC (Provisional) | Contact | LS2 2019-2020 | DEC | N0 cables to be removed | DIC | N0 cables to be pulled | DIR | N0 of racks to be installed | DIF | N0 fibres to be pulled | Observations
10752 | Replace injection extra kicker | C213AFB172 (DIC) C213AFC104 (DEC) | T. Kramer + J. Borburgh | yes | PRE-DEC Received | ~~330 | PRE-DIC Received | 171 |  |  |  |  | Pre-DIC (80%) 21/12/17 ~2.6km (New) Pré-DEC 21/12/17
11427 | Additional HV cables for KFA45 | C213AFB174 | T. Kramer + J. Borburgh | yes |  |  | DIC Received | 12 |  |  |  |  | DIC Reveived 11/12/17 ~1.5km
10921 | PS Longitudinal Damper | C213AFB155 | Matthias Haase | yes | DEC Received |  | DIC Received |  |  |  |  |  | Foreseen for YETS, postponed to LS2 ~4km

## Slide 6
Deadlines (From EDMS 1776389 – G. Georgiev)
All definitive requests (DIF, DIC, DIR, DEC) for LS2 shall be submitted before 21/12/2017.
All final requests for YETS17-18 shall be submitted
before end of April 2017.
All pre requests (DIF, DIC, DIR, DEC) for LS2 shall be submitted before 31/05/2017.
Today we are here

## Slide 7
Thank you!

## Slide 8
EYETS16-17 PS cabling
547 cables / 46.5 km pulled during EYETS for LIU-PS !
N° PLAN | Action | Equipment or System impacted | Contact | EYETS 2016-2017 | YETS 2017-2018 | DEC | N0 cables to be removed | DIC | N0 cables to be pulled | DIR | N0 of racks to be installed | DIF | N0 fibres to be pulled | Observations
10061 | New plus faster BLMs | Diamond BLMs | C. Zamantzas | yes | no | 0 | 0 | Received | 51+34 |  |  |  |  | Completed (34 pulled during EYETS) - 1366m
10354 | Quadrupoles QSK Power Converters - Ethernet Cables | 40x PR.QSKxx circuits | J.Gomez Costa | yes | no |  |  | Received | 32 |  |  |  |  | Completed - 300m
10354 | Quadrupoles QSK Power Converters - DC Cables | 40x PR.QSKxx circuits | Serge pittet | yes | no |  |  | EN-EL preparation | 40 |  |  |  |  | Completed - 710m
10355 | Low Energy Dipoles DVT Power Converters - Ethernet Cables | 20x PR.DVTxx circuits | J.Gomez Costa | yes | no |  |  | Received | 32 |  |  |  |  | Completed - 300m
10355 | Low Energy Dipoles DHZ Power Converters - Ethernet Cables | 50x PR.DHZxx circuits | J.Gomez Costa | yes | no |  |  | Received | 54 |  |  |  |  | Completed - 658m
10355 | Low Energy Dipoles DVT Power Converters - DC Cables | 20x PR.DVTxx circuits | Serge pittet | yes | no |  |  | EN-EL preparation | 20 |  |  |  |  | Completed - 304m
10355 | Low Energy Dipoles DHZ Power Converters - DC Cables | 50x PR.DHZxx circuits | Serge pittet | yes | no |  |  | EN-EL preparation | 54 |  |  |  |  | Completed - 816m
10434 | Renovation of BWS (including turn-by-turn). Prototype installed in SS54 | Replacing existing install. Need cables for bunch-by-bunch | J. Emery | yes | no |  |  | Received | 20 |  |  | Received | 10 | Completed - 3693m
10647 | Slow BLMs | Ionisation BLMs | C. Zamantzas | yes | no | 0 | 0 | Received | 200 |  |  |  |  | Completed - 35223m
10924 | DC Cables in SS08 |  | Carlo Rossi | yes | no |  |  | Received | 2 |  |  |  |  | Completed - 43m
10967 | Cabling for RF Sources |  | Heiko Damerau | yes | no |  |  | Received | 39 |  |  |  |  | Completed - 766m
11088 | Second new Ionization profile monitor (BGI) IPM Vertical | All new cables, power and aqn | J. Storey | yes | no |  |  | Received | 13 |  |  | Received | 12 | Partially installed (DC cables not defined) - 2060m
11100 | Beam stopper F16.STP176 et F16.STP152 |  | J. Lendaro | yes | no |  |  | Received | 2 |  |  |  |  | Completed - 218m
11169 | Installation of spare power converter - Ethernet Cable | Circuit QFO215 | J.Gomez Costa | yes | no |  |  | Received | 1 |  |  |  |  | Completed - 25m
11169 | Installation of spare power converter - DC Cables | Circuit QFO215 | K. Papastergiou | yes | no |  |  | EN-EL preparation | 4 |  |  |  |  | Completed - 22m