## Slide 1: TDIS WP14 PRR Manufacture and Inspection Plan Procedures, specifications and drawings
David Carbajo Perez (EN-STI-TCD)
TDIS PRR meeting 2018/03/08

## Slide 2: TDIS PRR meeting
Agenda
Manufacture and Inspection Plan
Procedures
Specifications
Drawings
Manufacture and Inspection Plan Procedures, specifications and drawings

## Slide 3: TDIS PRR meeting
Manufacture and Inspection Plan – Proto Sub-assemblies
Assembly | Process | Resources
Vacuum Tanks | Manufacturing | Cinel
 | Metrology Inspection | 
 | RGA test | 
 | Leak test | 
 | Shipping to CERN | 
Transitions | Components manufacturing | EN-MME
 | Metrology Inspection | 
Ion Pumps / NEG cartridges | Components manufacturing | SAES GETTERS
 | Metrology Inspection | 
 | Shipping to CERN | 
Sector valves | Components manufacturing | VAT
 | Valves assembly | 
 | Metrology Inspection | 
 | Shipping to CERN | 
Girder | Components manufacturing | BSB Industry
 | Girder assembly | 
 | Metrology Inspection | 
 | Shipping to CERN | 
Jacks | Components manufacturing | CERN warehouse
Manufacture and Inspection Plan Procedures, specifications and drawings
Jacks
Girder
Vacuum Tanks
Ion Pumps
NEG Cartridges
Transitions

## Slide 4: TDIS PRR meeting
Manufacture and Inspection Plan – Proto Sub-assemblies
Assembly | Process | Resources
Module supports | Components manufacturing | Ext. suppliers
 | Support assembly | EN-MME
 | Metrology Inspection | 
Mechanical tables | Components manufacturing | Ext. suppliers
 | Metrology Inspection | EN-MME
 | Endurance test (1 table) | 
Jaw | Components manufacturing | Ext. suppliers
 | Jaws assembly | EN-STI
 | Metrology Inspection | EN-MME
RF screen | Components manufacturing | EN-MME
 | RF screen assembly | 
 | Metrology Inspection | 
Complete Module | Assembly | EN-STI
Manufacture and Inspection Plan Procedures, specifications and drawings
Mechanical tables
RF screens
Module supports
Jaws

## Slide 5: TDIS PRR meeting
Manufacture and Inspection Plan – Proto Sub-assemblies
Elements to keep an eye on:
Component | Affected systems |  | Remarks
 | TDIS HRMT | TDIS Prototype | 
Roller screws | x | x | Delivery date tight although reachable. A close follow-up of the production is advisable
Ti clamps |  | x | Clamps for HRMT module -> machining by EN-STI. For TDIS prototype -> machining outsourced (Cinel, to be confirmed)
Cooling system | X | x | Outsourcing shifted to Cinel (with large experience in cooling systems for the collimators) since current supplier not confident in achieving requested pipes flatness by machining
TZM stiffener |  | x | Trials ongoing at supplier to improve requested back-stiffener flatness. One piece produced so far but flatness requirement not fulfilled (part to be used for HRMT, where stiffener flatness is not critical)
Manufacture and Inspection Plan Procedures, specifications and drawings

## Slide 6: TDIS PRR meeting
Inspection Plan – Proto/HiRadMat Sub-assemblies
System/Component |  | Dimensional inspection | Chemical composition | Material properties analysis |  | NDT |  |  |  |  | Remarks
 |  |  |  | Mechanical properties | Thermal properties | Ultrasound inspection | SEM analysis | X-ray inspection | Vacuum tests | Pressure test | 
RF-screen |  | x | x | x |  | x |  |  |  |  | Dimensional report to be prepared by CERN
Jaw | Cooling pipes | x | x | x |  | x |  | x |  | x | Radiographies of the radius areas after bending
 | Ti clamps | x | x | x | x | x |  |  |  |  | Material analysis/NDT done by raw material supplier (HWN)
 | Ti-6Al-4V blocks | x | x | x |  | x |  |  |  |  | Material analysis/NDT done by raw material supplier (HWN)
 | CuCrZr blocks | x | x | x |  | x |  |  |  |  | Material analysis/NDT done by raw material supplier (Albaksan)
 | Graphite blocks | x | x | x | x | x |  |  | x |  | Vacuum tests to be done at CERN after vacuum firing treatment
 | TZM stiffener | x | x | x |  | x |  |  | x |  | Mechanical properties measured @RT and @300°C
Mechanical table | Roller screws | x | x | x |  |  | x |  |  |  | SEM analysis before/after cycling test
Vacuum vessels |  | x | x | x |  | x |  |  | x |  | Leak test, RGA to be conducted by supplier (Cinel)
Girder |  | x | x | x |  |  |  |  |  |  | Inspection done by supplier (BSB industry)
Ion Pumps/NEG cartdriges/Valves |  |  |  |  |  |  |  |  |  |  | Validation tests on vacuum, dimensions and materials done in the past for other units. Not requested for this batch.
Sector valves |  |  |  |  |  |  |  |  |  |  | 
Manufacture and Inspection Plan Procedures, specifications and drawings

## Slide 7: TDIS PRR meeting
Inspection Plan – Proto/HiRadMat Sub-assemblies
System/Component |  | Dimensional inspection | Chemical composition | Material properties analysis |  | NDT |  |  |  |  | Remarks
 |  |  |  | Mechanical properties | Thermal properties | Ultrasound inspection | SEM analysis | X-ray inspection | Vacuum tests | Pressure test | 
Jaw | TZM stiffener | x | x | x |  | x |  |  | x |  | Mechanical properties measured @RT and @300°C
Metrology analysis of HiRadMat TZM stiffener
Manufacture and Inspection Plan Procedures, specifications and drawings
EDMS 1897213

## Slide 8: TDIS PRR meeting
Inspection Plan – Proto/HiRadMat Sub-assemblies
System/Component |  | Dimensional inspection | Chemical composition | Material properties analysis |  | NDT |  |  |  |  | Remarks
 |  |  |  | Mechanical properties | Thermal properties | Ultrasound inspection | SEM analysis | X-ray inspection | Vacuum tests | Pressure test | 
Jaw | Ti clamps | x | x | x | x | x |  |  |  |  | Material analysis/NDT done by raw material supplier (HWN)
Manufacture and Inspection Plan Procedures, specifications and drawings
Metrology analysis of the first produced titanium clamp
EDMS 190689

## Slide 9: TDIS PRR meeting
Inspection Plan – Proto/HiRadMat Sub-assemblies
Manufacture and Inspection Plan Procedures, specifications and drawings
System/Component |  | Dimensional inspection | Chemical composition | Material properties analysis |  | NDT |  |  |  |  | Remarks
 |  |  |  | Mechanical properties | Thermal properties | Ultrasound inspection | SEM analysis | X-ray inspection | Vacuum tests | Pressure test | 
Jaw | CuCrZr blocks | x | x | x |  | x |  |  |  |  | Material analysis/NDT done by raw material supplier (Albaksan)
EDMS 1894119

## Slide 10: TDIS PRR meeting
Inspection Plan – Proto/HiRadMat Sub-assemblies
System/Component |  | Dimensional inspection | Chemical composition | Material properties analysis |  | NDT |  |  |  |  | Remarks
 |  |  |  | Mechanical properties | Thermal properties | Ultrasound inspection | SEM analysis | X-ray inspection | Vacuum tests | Pressure test | 
RF-screen |  | x | x | x |  | x |  |  |  |  | Dimensional report to be prepared by CERN
Jaw | Graphite blocks | x | x | x | x | x |  |  | x |  | Vacuum tests to be done at CERN after vacuum firing treatment
Manufacture and Inspection Plan Procedures, specifications and drawings

## Slide 11: TDIS PRR meeting
Inspection Plan – Proto Sub-assemblies
System/Component |  | Dimensional inspection | Chemical composition | Material properties analysis |  | NDT |  |  |  |  | Remarks
 |  |  |  | Mechanical properties | Thermal properties | Ultrasound inspection | SEM analysis | X-ray inspection | Vacuum tests | Pressure test | 
Jaw | Cooling pipes | x | x | x |  | x |  | x |  | x | Radiographies of the radius areas after bending
Manufacture and Inspection Plan Procedures, specifications and drawings
Samples produced to verify the feasibility of the geometry
EDMS 1808269

## Slide 12: TDIS PRR meeting
Inspection Plan – Proto/HiRadMat Sub-assemblies
System/Component |  | Dimensional inspection | Chemical composition | Material properties analysis |  | NDT |  |  |  |  | Remarks
 |  |  |  | Mechanical properties | Thermal properties | Ultrasound inspection | SEM analysis | X-ray inspection | Vacuum tests | Pressure test | 
Mechanical table | Roller screws | x | x | x |  |  | x |  |  |  | SEM analysis before/after cycling test
Manufacture and Inspection Plan Procedures, specifications and drawings
Endurance test of one mechanical table foreseen to validate design. Roller screws supplier already validated for collimators

## Slide 13: TDIS PRR meeting
Manufacture and Inspection Plan – HRMT schedule
HRMT45
Beam Time
6th – 10th August
Manufacture and Inspection Plan Procedures, specifications and drawings

## Slide 14: TDIS PRR meeting
Procedures for the development phase
HL-LHC baseline documentation vs
systems life-cycle (EDMS 1361462)
Documents available in EDMS for the TDIS WP14 (status: in work)
Documents to be created (2Q 2018)
Manufacture and Inspection Plan Procedures, specifications and drawings

## Slide 15: TDIS PRR meeting
Procedures
Foreseen activities for TDIS considered by LS2 coordination team in their app PLAN (code 10015).
All tasks confirmed
Manufacture and Inspection Plan Procedures, specifications and drawings

## Slide 16: TDIS PRR meeting
Procedures
Full TDIS structure to be created in MTF application. Items available for some components already.
Manufacture and Inspection Plan Procedures, specifications and drawings
TDIS Beam Absorber for Injection Segmented | Absorber Module | Motorization | Electrical motor
 |  |  | Roller screw
 |  |  | Linear bearing
 |  |  | Sliding table
 |  |  | Mechanical table frame
 |  |  | Shaft
 |  | Module support | Bracket support
 |  |  | Cooling circuit assembly support
 |  |  | Base plate
 |  |  | Electrical junction box
 |  |  | Protection cover
 |  |  | Keys
 |  | Jaw | Absorber block
 |  |  | Clamp
 |  |  | Back-stiffener
 |  |  | Cooling pipe
 |  |  | Compression spring
 |  |  | Pipes support plate
 |  |  | Springs support plate
 |  |  | Support plate
 |  | Vacuum system | Ion pump
 |  |  | NEG pump
 |  |  | VGRB gage
 |  |  | VGPB gage
 |  | Impedance Hardware | RF screen
 |  |  | RF ferrite tile
 |  |  | Transversal RF finger
 |  |  | Longitudinal RF finger
 |  | Instrumentation | LVDT
 |  |  | PT100 probe
 |  |  | Flow meter
 |  |  | Temperature sensor (cooling)
 |  | Vacuum chamber | Vessel
 |  |  | Flange
 |  |  | Bellow
 | Transition |  | Transition
 | Support assembly |  | Girder
 |  |  | Jacks
 | Sector valve assembly |  | Sector valve

## Slide 17: TDIS PRR meeting
Specifications
Manufacture and Inspection Plan Procedures, specifications and drawings
EDMS 1865250
EDMS 1905241
Excel list with all requirements included in functional specification and the corresponding studies/tests intended to verify that they are fulfilled

## Slide 18
Manufacture and Inspection Plan Procedures, specifications and drawings
# | Page | Chapter | Requirement description | Value | Relevant calculation/study/ mechanism available | Documentation | Result analysis (OK/NOK) | Remarks | Relevant verification testing | Report | Result verification (OK/NOK)
Jaw movement range in operation and setting precision |  |  |  |  |  |  |  |  |  |  | 
1 | 5 | 3.1 | Minimum gap (anti-collision) | 1.0 mm | Anti-collision switch / Mechanical stoppers | Drawing mechanical table LHCTDIS_0011 | OK |  | TDIS prototype validation test program | To be created | 
2 |  |  | Maximum gap | 110.0 mm | Mechanical stoppers integrated in mechanical tables |  | OK |  |  |  | 
3 |  |  | Maximum individual jaw position | ±55.0 mm |  |  | OK |  |  |  | 
4 |  |  | Minimum individual jaw position across axis | ±5.0 mm |  |  | OK |  |  |  | 
5 |  |  | Surface flatness | ±0.10 mm | Tolerance calculation | Tolerance Analysis Jaw block flatness (EDMS 1906421) | OK |  |  |  | 
6 |  |  | Single jaw position precision | ±0.05 mm | Precision given by roller screw thread pitch and motor step | Motor and roller screw technical specifications | OK |  |  |  | 
7 |  |  | Single jaw setting reproducibility | ±0.01 mm | Given by design | Measurements from collimators mechanical tables | OK |  |  |  | 
8 |  |  | Minimum step size | 0.01 mm | Given by motor step | Motor technical specifications | OK |  |  |  | 
9 |  |  | Maximum angle at each module | ±2 mrad | Linking bar between mechanical tables constraints max. angle | Design verified Report to be prepared | OK |  |  |  | 
10 |  |  | Maximum retraction between modules | 20 mm | Limited by software | Software program | OK |  |  |  | 
TDIS Performance vs MKI failure cases |  |  |  |  |  |  |  |  |  |  | 
11 | 6 | 3.2 | Charging failure - no damage | 288x2.0e11 BCMS (inj.) protons on TDIS | Fluka simulation + FEA thermomechanical simulations IP8 Large impact parameter study | FEA calculations reports (EDMS 1851379) | OK | Most critical component: TZM back-stiffener and cooling pipes | HiRadMat HRMT45 to reproduce the worst-scenario conditions | To be created | 

## Slide 19: TDIS PRR meeting
Drawings
Manufacture and Inspection Plan Procedures, specifications and drawings

## Slide 20: Thanks for your attention
Content Input from from Antonio Perillo Marcone, Chiara Braco, Luca Gentini, Hector Garcia Gavela