## Slide 1: AD User schedules
2018 ADUC meeting.
H. Wilkens

## Slide 2: 2018 Fixed Target physics
East Area, nToF: 32.5 weeks starting March 30th. (~2.2x1019 protons on target for nToF)
AD, Isolde, SPS proton FT: 31 weeks, starting April 9th.
November 12th, stop of all proton beams (start LS2 works on the Linac-2 surface equipment & PSB power converter tests).
December 10th, stop of all beams (start of the SPS magnet tests)
SPSC recommended ions for NA61, after the end of availability of high intensity protons at SPS: 4 weeks Pb ion run.
Two scheduled Technical Stops (TS) to maintain the machine operating reliably. UA9 runs in the SPS machine during the radio-protection cooldown prior to the TS.
Large Machine Development (MD) program (Amorphous C-coating (COLDEX), crab-cavities, collimation, special beams, ions…) requires weekly dedicated MDs (Wednesdays) and parallel MDs (Thursdays), and 3 dedicated COLDEX runs.

## Slide 3: AD User schedule
AD operation starts April 9th.
AD Machine development every 3rd Monday 7:00 to 15:00.
42 shifts for ELENA commissioning (Mondays, Wednesdays and Fridays) up to end of July. Eventually p-bars to G-bar already then.
Then operation of ELENA+Gbar as an experiment in the shift rotation scheme. (61 shifts)
BASE, setup with beam 3 weeks in July and September. Priority for refilling the trap on night shifts (Monday to Wednesdays)
Shifts statistics:
ATRAP 21.0%, ASACUSA 20.2%, ALPHA 21.9%, AEgIS 20.2%, Gbar 12.9%, BASE 6.5%
Constrains: ATRAP cannot run after ALPHA (to ramp the magnet), preferably no AEgIS after ALPHA.
ELENA team would like to continue with commissioning after the start of the G-bar experiment: SPS-C emphasis the need for physics beam time for all experiments, ELENA commissioning should be done during G-bar shifts.

## Slide 4: BuilDing the 2018 schedule
backup

## Slide 5: AD MD and ELENA Commissioning till end of July

## Slide 6: Base runs in July and September

## Slide 7: Gbar run after end of ELENA commissioning

## Slide 8: Fair shift rotation among the remaining 4 experiments