## Slide 1: Polarised target status
Norihiro DOSHITA

## Slide 2: Outline
He3 line of the dilution refrigerator
He4 line of the dilution refrigerator
Target cell
Magnet
Precooling
Man power

## Slide 3: He3 line of the DR
Isolation vacuum
- 5 10^-6 mbar
Root pumps running test with dry N2 gas for 24 hours
Leak check
- Pumping line connections
- needle valves and gauges connections
- access tube line
- condensation line
- from He4 line
- root pumps  Leak @ 8th pump back  fixed
- from cooling water
- gas panel
- LN2 trap
New LN2 buffer dewar for LN2 trap

## Slide 4: He4 line
Pump system running test
Leak check
- pumping line  leaks  fixed (TE-CRG) : no more spare helicoflex joint
- needle valves and gauges connection
- cavity pumping line  leak  fixed
- around pump
500 L liquid helium dewar (TE-CRG)
- already delivered (15/2)
- transfer line installation (20/2)
Recovery line modification
- recovery line to cold box closed
- connection to balloon line with a check valve
Purging
- 3 times

## Slide 5: Target cell
All coils installed
Target cell and target holder connection
- a NMR coil cable damaged
Insertion test at room temperature
Check of the NMR cables
Leak check of the holder

## Slide 6: Magnet
New power convertor lack installed (31/1)
Converters commissioning
-- Full current with short cut circuit (12-13/2)
-- MSS signal test on going with the short cut circuit
Flow controllers service
Leak check
-- magnet necks
-- flow controller panel
-- Two big safety valves
Precooling preparation
-- 4 times purging  see next page
-- LN2 line installation
Valve control tests

## Slide 7
Magnet helium vessel pressure
Thur
Fri
Sat
Sun
Mon
1.15 bar
1.10 bar
1.00
34 mbar drop for 60 hours
1st purging
2nd
3rd
4th

## Slide 8: Precooling
Magnet : OK  started at 8:00 in this morning
- purging : done
- Alexey and Fabrice came to check.
- N2 transfer test : done
DR : OK  started at 9:00 in this morning
- purging : done
- 500 L dewar : installed
-- transfer line : installed at 9:00 today
- helium recovery line : OK

## Slide 9: COMPASS Preparation schedule
We are here.

## Slide 10: Man power
Accelerating of preparation since last week
Jaakko, Kaori and Nori
-- Permanently at CERN
Michael : back to CERN on Wednesday
Genki : back to CERN on Thursday
Eric : came to CERN on Thursday for 2 weeks
Three tasks progressed in parallel
Yuri will come from April

## Slide 11
LN2 transfer line
Short cut cable

## Slide 12
He4 pumping line
He3 pumping line
Helicoflex joint

## Slide 13
Target insertion place
Target cell and holder