## Slide 1: Status of atlas resources
Fido Dittus
RRB presentation, 24 April 2018
CERN-RRB-2018-040

## Slide 2: Outline
CERN-RRB-2018-042 2017 and 2019 ATLAS M&O Budgets
Part 1: Closing Report for the 2017 ATLAS M&O Budgets
Part 2: Preliminary 2019 ATLAS M&O Budget Estimate
CERN-RRB-2018-041 ATLAS Upgrade Status Report 2017 – 2018
Status of Phase-I Upgrades
CORE Values [kCHF] delivered in 2017
CORE Values projected to be delivered in 2018
Status of Phase-II Upgrades
Status of Phase-II Common Fund

## Slide 3
2017 M&O Income
2017 M&O-A Payments
2017 M&O-B Payments

## Slide 4: 2017 M&O INCOME
19’901 kCHF budgeted
(M&O A+B, incl. NMS Energy and in-kind contributions)
20’111 kCHF received, including
contr. for 2017 received before 2017
contr. for 2017 received in 2017
in-kind contributions for 2017
contr. outstanding from prev. years
excluding
advance contributions for 2018+ (accounted for in 2019)

## Slide 5: Final 2017 M&O-A Payments [kCHF]
14.895 MCHF, incl. NMS Energy
Cost breakdown by activity:
Technical services 7.0 MCHF
  including NMS Energy 0.7 MCHF
On-line computing 4.4 MCHF
  incl. transf. to buffer 2.3 MCHF
Core computing 2.3 MCHF
Magnet & cryogenics 1.1 MCHF
2.404 MCHF Open commitments
  incl. 2.166 MCHF for HLT processors

## Slide 6: Final 2017 M&O-A Payments [kCHF]
Including in-kind contributions
Including 2.297 MCHF transferred to the TDAQ buffer account
Net underspend of 221 kCHF
2.166 MCHF open commitments in TDAQ due to failed order of HLT processors
  Many thanks to CERN-IT for providing processors on loan !
  Newly ordered processors now installed and paid in March 2018 (3.264 MCHF)

## Slide 7: Final 2017 M&O-B Payments [kCHF]
4.93 MCHF Total
Cost breakdown by activity:
Mechanics, cooling, gas 0.12 MCHF
Electronics 1.68 MCHF
Areas, stores, spares 0.59 MCHF
Technical support 2.54 MCHF
Class 3 OT effort 363 FTE
  incl. 134 FTE for core computing

## Slide 8: Final 2017 M&O-B Payments [kCHF]
Total payments in 2017 were slightly larger (65 kCHF) than the total 2017 budget
  The cumulative budget carry-over decreased from 800 kCHF to 734 kCHF
  After subtracting open commitments (143 kCHF), the carry-over amounts to 592 kCHF

## Slide 9
M&O A+B Evolution
Sharing of the 2019 ATLAS M&O Budgets
  (preliminary)

## Slide 10: M&O A+B Evolution (kCHF)
The M&O A+B budget is kept flat at 21.4 MCHF with the help of the TDAQ buffer.
Because the new HLT processor order was delayed, the unspent 2017 budget was put into the buffer account.
The projection of the TDAQ buffer balance from 2018 onwards is similar to, but 0.45 MCHF lower than to the projection made last summer, due to the higher costs of the processors eventually bought.

## Slide 11: Preliminary 2019 M&O Budgets

## Slide 12: Proposed sharing of 2019 M&O

## Slide 13
Phase-I Progress
  Phase-I Money Matrix
  CORE Values of Phase-I deliverables realized in 2017
  CORE Values of Phase-I deliverables expected to be realized in 2018
Phase-II Progress
  Status of Phase-II Common Fund

## Slide 14: Phase-I Progress
The sharing of the CORE costs, defined in the MoUs, is summarized here in the Phase-I “Money Matrix”.
Phase-I Upgrade TDRs and MOUs | 
CERN-LHCC-2013-006 CERN-RRB-2014-050 | Construction of the ATLAS New Small Wheel (NSW) Sub-Detector
CERN-LHCC-2013-017 CERN-RRB-2014-051 CERN-RRB-2015-064 | Upgrade of the Liquid Argon Calorimeter Trigger electronics
CERN-RRB-2014-052 | Upgrade of the ATLAS Tile Calorimeter
CERN-LHCC-2013-007 CERN-RRB-2014-053 CERN-RRB-2015-001 | Construction of the FTK Sub-System
CERN-LHCC-2013-018 CERN-RRB-2014-054 | Upgrade of the Trigger and Data Acquisition System
CERN-LHCC-2015-009 | ATLAS Forward Proton TDR

## Slide 15: Phase-I Progress
All Phase-I projects have made substantial progress since the last RRB.
See CERN-RRB-2018-041 and the presentation by Ludovico Pontecorvo for detailed, up-to-date information.
CORE values of 6.2 MCHF realized in 2017 (and 2018 →next slide).
The New Small Wheel project remains highly critical
  Top ATLAS priority, full attention by ATLAS management;
  CORE over-costs to be wrapped up comprehensively in 2019 – 20.

## Slide 16: Phase-I Progress

## Slide 17: Phase-II Common Fund
CERN-RRB-2017-058
  Final version presented to RRB in October 2017
  Total cost = 24.420 MCHF
  Flat funding profile over 9 years, 2018–2026 ➠ 2.713 MCHF/year
  To be shared year-by-year exactly like M&O; the sharing by FA in 2018 is detailed in Annex 4.

## Slide 18: Phase-II Common Fund
CERN-RRB-2017-058
  Sent out for signature in November 2017
  17/47 signed by now
  Received 1.794 MCHF already, thanks to a large advance payment

## Slide 19
The ATLAS management, supported by the ATLAS Executive and Collaboration Boards, kindly invites the RRB to take note of
  the Closing Report for the ATLAS 2017 M&O Budgets.
  the Preliminary 2019 ATLAS M&O Budget Estimate and the Sharing by Funding Agency.
  the Progress of the ATLAS Phase-I Upgrade Projects, and the CORE values realized in 2017, and expected to be realized in 2018.
  the Signature Status of Addendum #17 to the Construction MoU on the Phase-II Common Fund, and the funds already collected.
!! THANK YOU FOR SUPPORTING ATLAS !!