## Slide 2: An SRF Test stand in proton beams Design, installation, lessons learned
G.Vandoni

## Slide 3: A TEST BENCH for SRF (Projects)
With HIE-Isolde linac, only 2 complete SRF projects, from cavity to beam:
SPS test bench :Modest, but rich in experience and lessons
Point of view of the SPS Integration Task within WP4/HL-LHC:
Integration = Management of interfaces

## Slide 4: DESIGN

## Slide 5
2x RF amplifiers IOT 60kW each
Faraday cage for LLRF
Cryogenic compressor & oil removal
El. Transformer/ Switchboard/ Control racks
80m long cryo distribution line
Cold-box
Valve-box
LN2 phase separator
2 x He pumping units, 48W
Articulated Y-chambers C-coated
RF transmission lines, rotating coupling
Motorized transfer table 510mm 4mm, remote control
LAYOUT

## Slide 6: DESIGN
Fully remote handling and controls
Ancillary equipment at the surface – refrigeration underground (LN2)
Minimize number of cables
Local safety features
Simple interlocking, following operation scheme
  Personnel protection
  Machine protection
  Equipment protection
Operation ≤10 years

## Slide 7: DESIGN Lessons learned
Minimize cable pulling caused trade-offs
  No camera
  No mech. Instrumentation readout
  High power RF not standalone
Interlock with access for RF too restrictive for operation in LHC
Not all is designed for longstanding robustness (cable protection missing)
Water pressure overhead in tunnel overseen (cryo & RF)
High power RF system should remain fully standalone.
More cables, but less complication. We will apply this strategy in HL-LHC.

## Slide 8: DESIGN for SAFETY
Risk analysis 1.Cryogenic, 2.Cryomodule, 3.Test stand, 4.Table
Safety review Actions / Follow-up meetings
Safety SPS SIR Training Updated
Safety file In Work
Main Hazard | Origin | Treatment
Radiological risk | RF (X-rays, dark currents) | Interlock access
Oxygen deficiency | Cryo spillout | ODH detectors + alarms
Pressure | Pipework, valveboxes, CM | Tests, certification
Mechanical | Table | Alarms, procedures, local key-box
Noise | Compressor, fans | FC sonic insulated
TOOLS

## Slide 9: SAFETY FILE Completion
Safety inspections & documents | Carry out and complete
EIS | Issue intervention PROCEDURE/ update layout database
Cryogenics safety | Implement LN2 feed stop versus ODH signal
 | Update Cryogenic Risk analysis 1730771
 | Provide final PID plan on CDD (SPSQAIL)
 | Issue PROCEDURE for cryoworks on cold CM
Mechanical safety | Issue PROCEDURE for heavy transport at cold CM
 | Issue PROCEDURE for use of table local mode
Ergonomics | Evaluate noise in local BA6 CRG control room
Safety file | Draft and submit to the SPS CSAP
Inspections need to be completed and documented
Procedures must be written and approved
Safety file must be written
List by C.Gascon / C.Gaignant

## Slide 10: DESIGNING for SAFETY
Lessons learned
Needs time
Appropriate tools and culture not generalized, not taken into account in resources
Role and responsibility of HSE, DSO, Project engineers
HSE is consultant WHILE Responsibility is in hierarchy
(DSO support)
RESULT:
Safety design overshooted?
“If we could have so many ODH/meter in LHC as you have here…”

## Slide 11: INSTALLATION

## Slide 12
INSTALLATION
MASTER
PLAN
EYETS = 12 weeks
YETS = 8 weeks
Largest and most complex equipment to install in shortest time

## Slide 13: YETS 17/18 Statistics
64 IMPACTS
200 Estimated participants
~20 Teams involved

## Slide 14: INSTALLATION TIMELINE
Cryomodule/RF
Cryogenics
Cabling

## Slide 15: EN/EL Staging of deadlines
CABLING
CRYOGENICS
TA6/ shaft
Tunnel
BA6
TEST STAND
Transfer Table
RF equipment
CRYOMODULE
TA6/ shaft
Tunnel
BA6
Vacuum
CABLING
POWERING
MAIN ACTIVITIES
Tunnel
Notes: Cabling activities and cryogenics related activities shared all locations, needed the whole timespan. The test stand, in 10m of tunnel length, was the scene of an important co-activity all along the YETS.

## Slide 16: INSTALLATION – Lessons learned
Working hand in hand with services: understanding and integrating specific difficulties, in a creative and collaborative approach.
Field coordination paramount (thanks Simon!): presence/ anticipation/ swift change of sequences to cope with field difficulties (and a lot of patience by the field actors)
We can install a cryomodule in a YETS (cryomodule alone: 14 days)
«Associate transport to design, since the beginning»
«We structured the work by user and not by location. With an initial visit with each user and final handover, this shortened times and improved quality»

## Slide 17: WORKSITE Safety & Coordination
Not outspoken situation:
According to GSI-WS-1 WP4 deliverable responsible was both
TECHNICAL COORDINATOR (planning) and SAFETY COORDINATOR (safety).
Work supervisors not named on all activities, not formed.
Complex contractual situation, communication issues
Large number of involved teams
Small space
No margin schedule
High level of coactivity: stress, hazards
Field treatment of contingency and issues
GSI-WS-1 “Safety Coordination for Works and Services” applied first time after approval 2016.
INTERESTS CONFLICT

## Slide 18: WORKSITE Safety & Coordination
Not outspoken situation:
According to GSI-WS-1 WP4 deliverable responsible was both
TECHNICAL COORDINATOR (planning) and SAFETY COORDINATOR (safety).
Work supervisors not formed, not defined correctly on all activities (cryo!).
Complex contractual situation, communication issues
Large number of involved teams
Small space
No margin schedule
High level of coactivity: stress, hazards
Field treatment of contingency and issues
GSI-WS-1 “Safety Coordination for Works and Services” applied first time after approval 2016.
IN SUCH a TENSE SITUATION:
«We should prioritize safety issues and not track the most inconsequential trifle»

## Slide 19: QUALITY & DOCUMENTATION
With external institutes joining for HL-LHC, we need to be strong and well defined in terms of quality request and communication schemes
Unequal quality culture across SRF teams.
Hand-over should be improved: procedures, implemented design changes, should all be recorded and well documented in the same way.
To “learn the lesson” and use it as reference, we must solve non-conformities, document interfaces, complete the safety file and write missing procedures.
…you got it

## Slide 20: …and for HL-LHC?
Indeed, it was a success story based on people’s commitment, enthusiasm, motivation – not on simple duty!
But we should NOT be relying on good will for the LHC.
At CERN anything is possible if people are willing to work together, even a project with a "negative time margin” in the planning
In the LHC, we will have 8 x more to do… with the same manpower.
If appropriate resources (in number and competence) are not allocated, then we will face serious inefficiencies.

## Slide 21
«Keep the whole community in the information loop»

## Slide 22: CONCLUSIONS
SRF projects are an old yet young story at CERN: standard practice needs to be developped
The crab cavity test stand in SPS was the occasion to elaborate practice and work out interfaces.
Not a sterile intellectual game, but a robust brick to bring in the HL-LHC construction – and in all future SRF projects.
Thank you for your attention

## Slide 24: Main non-conformities
Cryo danger zone not marked
Cryo-lines versus insulation vacuum status, procedure not indicated on items
Water pressure on circulator & load too high
Cable’s hard protection missing
Mechanical instrumentation cables missing
Brakes on motors
Vacuum interlocks to cryo are not hard cabled
VVS interlock to table position is not hard cabled
VB2 and SB mutual distance not according to integration
Helium leak on line between CB and VB1
ODH signals impacted by occasional noise, reach pre-alarm

## Slide 25: DESIGN - INTERLOCKS
Cryogenic distribution line
Type | Why | What
Personnel safety | Radiation (X-rays) ODH and cryo hazard mechanical hazard | Access versus RF Power to cavities Table movement/ LHe level
Machine protection | Aperture Protection SPS and cavities | Beam & extraction versus table position, table movement, vacuum sector valves SIS: set of parameters, to define
Equipment protection | Protection of cavities and their ancillaries | RF Power versus Vacuum (beam/ insulation) Cryogenics (cryo OK given manually+ interlocks) Beam versus HOM power

## Slide 26: INTERLOCK Lessons learned
INTERLOCKS are an INTERFACE between SYSTEMS, by DESIGN:
They should be treated by Integration
Engineering Specification treated only Safety and Machine Protection interlocks
Equipment Protection interlocks in SRF are NOT YET a standard practice:
Some cables not pulled because each partner thought the other would ask
Some interlocks requested even if redundant
Commissioning tests had to be repeated several times because all was not tested in one go
Full documentation of tests needs to be written and recorded in EDMS.

## Slide 27: INTERLOCKS Non-conformities
Non conformity | Solution
Table out of beam: VVS not interlocked | Cable to be pulled for hardware interlock
Table position to Vacuum valves opening is now via software | Cable to be pulled for hardware interlock
Vacuum to cryogenics is now via software | Cable to be pulled for hardware interlock
Interlocks Engineering Specification records only Safety and Machine Protection interlocks, not the Equipment mutual protection | Modify the Interlocks Engineering Specification to include all equipment protection interlocks