## Slide 1: MPP Proposal for Intensity Ramp-up and MPS commissioning status
J. Uythoven, J. Wenninger, D. Wollmann, M. Zerlauth

## Slide 2: Outline
Re-cap intensity ramp-up 2017
Proposal for intensity ramp-up 2018
Intensity ramp-up check list
Ramp-up scenarios after stops and MDs
MPS responsibles
Conclusion

## Slide 3: Intensity ramp-up 2017
The plan: 3 - 12 - 72 - 300 - 600 - 900 - 1200 - 1800 - 2400 – 2550
23.05.
3/12 b
26.05.
75 b
28.05.
315 b
601 b
03.06.
06.06.
Scrubbing 07.-12.06.
12.06.
985 b
15.06.
1225 b
17.06.
1561 / 1741 b
20.06.
24.06.
2029 / 2173 / 2317 b
1225 b after 15 days (excl. scrubbing [1d], injector stop [2d], scrubbing week) – intensity ramp-up combined with beam commissioning
~2500 b after 24 days
Careful check of high energy beam dumps and documentation in11 check lists (8 intensity ramp-up, 1 scrubbing, 1 ramp-up after TS1, 1 intensity cruise) - (EDMS).
Establish cycle
MP dominated
Intensity dominated

## Slide 4: Proposal Intensity Ramp-up 2018
Replacement of TCT and installation of TCL (BB wire collimator), replacement of MKI, intervention in all the LHC, new ramp, …
Intensity ramp-up > 12b: 3 fills, 20h stable beams, checklist
Interleaved increase of stored energy and # of injected bunches
3 - 12 - 72 - 300 - 600 - 900 - 1200 - 1800 - 2400 - 2550
Scrubbing:
  Verify heating of critical elements before stepping up in intensity
  Intermediate checklist after ~300 b (RF power, heating, … ), final checklist at the end of scrubbing
Cruise: Checklist every ~6 weeks (i.e. TS1, end July, TS2, TS3, End run)
Insertion of CT-PPS and AFP roman pots to agreed settings ( CollWG):
  After > 2h in second fill and full third fill at each intensity step.
Establish cycle
MP dominated
Intensity dominated

## Slide 5: Intensity ramp-up checklist: system-responsible
System / categories | Responsible / Deputy
Period | D. Wollmann / M. Zerlauth / J. Uythoven
Fills | D. Wollmann / M. Zerlauth / J. Uythoven
Dump Statistics | D. Wollmann / M. Zerlauth / J. Uythoven
Magnet Powering (MP3) | Z. Charifoulline / A. Verweij
Interlocks | I. Romera / J. Uythoven
RF | W. Hoefle / A. Butterworth / L. Arnaudon
Beam Instrumentation | C. Zamantzas / B. Holzer / T. Medvedeva
Collimation | S. Redaelli / R. Bruce
Operation, orbit, feedbacks | J. Wenninger / L. Ponce?
Beam dump | C. Bracco / W. Bartmann
Injection | C. Bracco / W. Bartmann
Heating of Equipment | B. Salvant / G. Iadarola
Please, update, where required
before 13.04.2018

## Slide 6: Intensity Increase checklist
Review current checklist template:
  Intensity Increase Checklist Run2 V2
Update tabs for respective system, if required
Before 13.04.2018

## Slide 7: Reminder: Standard ramp-up scenarios after stops of nominal operation ( > 48 h)
Without massive HW + SW interventions
One fill with either 2-3 nominal bunches into SB (cycle revalidation etc.).
One fill with 600 bunches and 2 - 5 hours of stable beams (known intensity step to disentangle wrong settings, de-conditioning, etc. from intensity dominated effects at full intensity).
Back to pre-stop intensities.
Total 2 fills for ramp-up
With massive HW + SW interventions
One fill with either pilot bunches or max 2-3 nominal bunches into SB (cycle revalidation etc).
One fill with ~50 bunches and about 1 - 2 hours of stable beams.
One fill with 600 bunches and 2 - 5 hours of stable beams (known intensity step to disentangle wrong settings, de-conditioning, etc. from intensity dominated effects at full intensity).
If > 2000 bunches reached, one fill with about half max number of bunches and about 5 hours of stable beams.
Back to pre-stop intensities.
Total 3-4 fills for ramp-up
Note: other cases, e.g. a triplet quench, will require a validation fill with 2-3 nominal bunches.

## Slide 8: MP systems responsible and MPP presentation dates
MP System | Responsible | MPP presentation | Commissioning procedure
Collimation System | B. Salvachua (Stefano Redaelli / Roderik Bruce) | 16.03. | Update under approval
Injection Protection System | C. Bracco / W. Bartmann | 23.02. | Released
Beam Interlock System | C. Martin / I. Romera | 09.03. | Released
Powering Interlock System | A. Antoine / I. Romera | 26.01. AA | Released
Vacuum System | G. Pigny | 09.03. | Released
Beam Dump System | C. Bracco / W.Bartmann | 23.02 | Released
FMCM | A. Antoine / I. Romera | 26.01. AA | Released
BLM System | C. Zamantzas / B. Holzer | 23.03. | Under Approval
Warm Magnet Interlock System | R. Mompo / A. Miranda Fontan | 26.01. AA | Released
Safe Machine Parameter System | I. Romera / R. Secondo | 09.03. | Released
Software Interlock System | J. Wenninger | 23.03. | Update under approval
Based on the presentations and the procedures a list of MPS tests with beam was derived: MPS re-commissioning 2018  regularly updated

## Slide 9: Conclusion
Intensity ramp-up 2017 proposal based on successful strategy applied in 2016 (1700b reached after 15 days).
Check lists during scrubbing and intensity ramp-up have proven important and useful to analyze and document the correct functionality and performance of machine protection critical systems
Regular check-lists during intensity cruise
Two standard scenarios for intensity ramp-ups after short stops were successfully applied 2016 and 2017 also proposed for 2018
Re-commissioning plans of all machine protection systems were discussed in the MPP  List with required MPS tests with beam was derived and is updated regularly
Notes: Updated