## Slide 1
WP16: Status and Preparation of Annual Meeting
David Ondreka / GSI
Video Conference / 10.04.2018

## Slide 2: WP16: Status
WP Organisation
  Task 16.2 now lead by Kathrin
Task progress
  16.2
    Delayed due to missing man-power, but resuming speed since Kathrin is back
    No trouble with milestones or deliverables
  16.3
    Very good progress on gun design and preparations of environment for testing big gun
    Scaled-down experiment ready, waiting for modulator integration
    Modulator development delayed due to administrative and technical troubles
  16.4
    Very good progress on test stand design
    Common solution for CERN and GSI gun
Task | Name | Participants | Task Leader
16.1 | Coordination | GSI | David Ondreka
16.2 | System Integration | GSI, IAP | Kathrin Schulte-Urlichs
16.3 | Electron Gun and Power Modulator | IAP, RTU | Kathrin Schulte-Urlichs
16.4 | Test Stand and Beam Diagnostics | CERN, GSI | Adriana Rossi

## Slide 3: WP16: Annual Report
Report on progress per task
  Responsibility of task leader
  Contributors should support
  Max. half a page of text per task
  Up to one page if figures included (welcome!)
  Template has been distributed
  Send to WP coordinator by April 30th (latest)
Full WP report
  Completed by WP coordinator
  Sent to ARIES committee by May 15th (latest)
Please keep the dead lines!

## Slide 4: WP16: Annual Meeting
First ARIES Annual Meeting
  Riga, May 22nd to 25th
  Parallel WP meeting on May 22nd
  Plenary highlight talks on May 23rd
    Kathrin on SC Gun Design
    Sergey on Test Stand Design