## Slide 1: Polarized target status
10/4/2018

## Slide 2: Outline
Magnet commissioning status
- commissioning items
- new field rotation procedure
Pump room intervention
Target loading schedule and preparation

## Slide 3
 |  | Magnet Commissioning in 2018
20/3 | MSS Trim | Quench back heater for trim coils, control currents
20/3 | Solenoid | Power ON (10 A)
21/3 | MSS Sol | Slow discharge of solenoid
21/3 | MSS Dip | Slow discharge of dipole
22/3 | MSS Sol | Quench back heater for solenoid, fast discharge at 70 A (6 times)
22/3 | MSS | Resistance of current leads without helium flow
28/3 | Sol | Full current of 646 A
28/3 | Dip | Full current of 590A
28/3 | Sol | Stability test
29/3 | Dip | Stability test
29/3 | MSS | Safety for filed rotation (Logics of “Tiroir de Securité” ) until 4/4
9/4 - | Sol Dip Trim | Present field rotation procedure (longitudinal transverse)
 | Sol Dip Trim | New field rotation procedure (longitudinal transverse)
 | Sol Trim | TE mode procedure (should be finished until 20/4 )
 | Sol Dip | Long stability test by power convertor team NEW request
 | Sol Trim | Field homogeneity with material

## Slide 4: Other issues on the commissioning
Modification
- voltage monitoring cards for current detection (23/3)
- new MSS program
- new power convertor control system (4/4)
- new script for filed rotation (5,6/4)
Magnetic filed warning sign
Magnet field direction
- sol : + current  point to downstream
(opposite from 2015)
- dip : + current  point to up

## Slide 5
Dipole current
Solenoid current
Trim coils setting
+
+650 A
-650 A
-
0
Trim coils operation in 2015
Time

## Slide 6
Dipole current
Solenoid current
Trim coils setting
+
+650 A
0 A
-
0
Trim coils operation in 2015 (Transverse mode)
Time

## Slide 7
Dipole current
Solenoid current
Trim coils setting
+
+650 A
-650 A
-
0
0 A
New trim coils operation in 2018 (Field rotation mode)
-- scenario 1
Time
SMC procedure

## Slide 8
Dipole current
Solenoid current
Trim coils setting
+
+650 A
0 A
-
0
Trim coils operation in 2018 (Transverse mode)
-- scenario 1
Time

## Slide 9
Sol Dip
-
Sol
Dip
+236 A
+465 A
+80 A
-80 A
+135 A
-465 A
-135 A
-236 A
Allowed region by MSS
Done
To be checked
MSS for field rotation

## Slide 10: Pump room intervention
15/11 : Intervention started.
(3 weeks in the first planning)
19/1 : Scaffold was removed.
4/4 : started installation of missing 3 valves
and electrical connections
9/4 : operation test

## Slide 11: Target loading schedule and preparation
17/4 Tue : target loading
16/4 Mon : loading platform installation
- LN2 bath, two LN2 dewars, leak detector
20/4 Fri : loading platform removal
21/4 Sat – 24/4 Tue : TE calibration
LN2 order
Gerhard will arrive on Monday.
The 221 door will Keep key access.
Scaffold for He3 pumping line installed on Monday

## Slide 12
Genki’s Calculation of the filed homogeneity with trim coils

## Slide 13
Produced by Caroline