## Slide 1: glexec/Argus pilot service
Status and short-term plans
Antonio Retico
GDB 10-Feb-10 - CERN

## Slide 2: Agenda
Description of the glexec/Argus pilot
  Use cases
  Objectives and metrics
  Success conditions
  Partners
  Deployment
  Integration works (Experiments)
  Open issues
  Planning
Next Steps
Good morning!

## Slide 3: Use Cases
Use cases
  Experiment frameworks using glexec for production pilot jobs.
    Alice, Atlas, CMS (details in next slides)
  Test of grid-wise banning feature by OSCT
  Gathering of requirements and analysis for monitoring tools
Versions
  Starting from Argus version 1.0 (Patch: #3076 , certified Nov 09 )
  Newer versions deployed if required (in parallel on the pilot and in certification)

## Slide 4: Objectives and Metrics
Functionality
  Correct interaction of pilot jobs submission frameworks with glexec/Argus
  Three frameworks at different level of maturity
  Different requirements and metrics (details in next slides)
Operations
  Sites to judge on Argus operability
Grid Security
  Test OSCT ability to ban users centrally
  No specific intervention of the site administrators needed
Monitoring
  Collection of requirements for monitoring tools

## Slide 5: Success conditions
No major issues present in glexec and Argus
Stable activity for ~2 weeks
Achieved integration with experiments’ frameworks
Positive feedback of site managers about operability

## Slide 6: Partners
Coordination: A. Retico (CERN)
JRA1: JRA1: Argus Product Team (HIP, INFN, NIKHEF, SWITCH)
  Development, support
SA3: G.Pucciani (CERN)
  Interface to certification
SA1: T.Kouba (CESNET), G.Misurelli (INFN-CNAF), A.Ceccanti (INFN-T1), A.Poschlad (KIT), E.Imamagic (SRCE), A.Usai (SWITCH)
  Site installations, support tools (CNAF)
Alice (AliEn): P.Mendez (CERN), S.Schreiner (CERN)
Atlas (PanDA): J.Caballero, M.Potekhin (BNL)
CMS(WMS glidein): S.Padhi (CERN)
Interface to Pilot Jobs Technical Forum: M.Litmaath (CERN)

## Slide 7: Deployment
FZK/KIT (ready since 15th-Jan)
  12 “PPS” cores connected to Argus  Upgrading to 250 cores next week (19th Feb)
  To be extended to full production after testing
  Currently 5000 job slots available with glexec/SCAS
INFN-T1 ( installation in progress )
  Now deploying glexec on WNs (expected by mid-February)
SRCE (ready since 2nd-Feb)
  8 cores
  Developers of glexec monitoring
SWITCH (ready since 1st-Dec)
  First site installation (piloting the pilot)
  Available for integration testing (flexible on set-up but no capacity)
INFN-CNAF (ready since 21st-Dec )
  Test instance with two cores
  Managing the service repositories
CESNET (installation in progress)

## Slide 8: Integration works: Alice
Integration of glexec calls in AliEn
  Analysis of architectural scenarios in progress
  Possible impacts on end users
  Several changes are likely required in AliEn
    user proxy registration into myproxy service
    download of the user proxy into the WN
    implementation of glexec
    redefinition of the job environment
    creation of subdirectories for the real jobs.
Requirements for supporting sites
  dedicated VOBOX for testing
  specific queue pointing to glexec infrastructure
  different sw area from that of production
No forecasts yet for start of testing

## Slide 9: Integration works: CMS
Currently implementing glexec calls in glidein WMS
Planning to start testing by mid-February
  Conditioned to availability of CNAF-T1
  CNAF-T1 + all sites offering glexec at that date (also with SCAS and GUMS)
Special focus on Argus’ ability to handle concurrent authorization requests
  Will use multi-user Pilot jobs on T2s for analysis (not yet the case now)
  It will be a test system

## Slide 10: Integration works: Atlas
glexec calls integrated in PanDA
  tested using SCAS back-end (Feb-Jul 2009)
  output available to other experiments
  in last CHEP’s proceedings
Mainly interested in scalability testing
  Real production work
  E.g. Sudden re-start of activity (wave of jobs)
New use case: multi-user pilot jobs
  Independent on the work already done
Requirement: run on “big” sites (> 100 cores)
  Will participate but only at this scale (later on)

## Slide 11: Integration works: LHCb
glexec calls integrated in DIRAC and use cases tested (Feb-Jul 2009)
  SCAS back-end
Not directly impacted by the change of the back-end
  Changes in the interfaces are not expected
Not enough effort to support infrastructure testing activity

## Slide 12: List of open issues
Open issue | Reported by | bug(s) | Status
The default policy refresh time set to 4hours seems too long | KIT | 62281 | To be discussed with JSPG
PEPd should require client-cert authentication support for connecting pep clients | INFN-T1 | 60041 | fixed with patch 3536 In certification (Argus1.1)

## Slide 13: Planning
kick-off with sites: 25-Nov
1st site available for experiments to test (SWITCH): 1-Dec
kick-off with experiments: 1-Dec
5 sites available for experiments to test: 15-Jan
Start of Alice developments to integrate glexec: 18-Jan
Start of CMS developments to integrate glexec: 15-Feb
END of activity (proposed): 31-Mar

## Slide 14: Next steps
Enable CMS testing
  Finish installation at INFN-T1
  Scale-up installation at KIT
Deploy Argus version 1.1 (update of glexec needed)
Support development of glexec testing at SRCE
Next check-point : 16th of February

## Slide 15: Access info
Home Page
  https://twiki.cern.ch/twiki/bin/view/EGEE/PilotServiceArgus
Meetings
  Minutes of kick-off and 3 check-points
  https://twiki.cern.ch/twiki/bin/view/LCG/PPIslandKickOff
Contacts
  egee-pilot-argus@cern.ch

## Slide 16: Questions?
?