## Slide 1
  The European Spallation Source:
  Designing a Sustainable RI for Europe
  John Womersley, Director General
  Workshop on ‘The Economics of Science’, Brussels, June 2019

## Slide 2
✅ Science case
✅ Technical R&D, cost estimates understood
✅ Project management plan
✅ Credible funding and governance plan
✅ Stakeholder engagement
✅ Compelling investment case
Key challenges in building sustainable support for any science megaproject

## Slide 3: The investment case in a nutshell
Scientific and technological innovation is essential
global challenges of energy, climate, environment, healthcare
economic and societal challenges of stalled productivity and long term wage stagnation

## Slide 4
Materials and molecules
Where are the atoms and what do they do?
New materials, new drugs, new processes, new energy technologies

## Slide 5
ISIS
ILL
Effective thermal neutron flux 1015 n/cm2-s
FRM-II
SNS
J-PARC
LANSCE
NIST
Year
ESS
Chart: 
| 1968 | 1970 | 1986 | 1989 | 2003 | 2008 | 2009 | 2025
 | 0.72 | 4.44 | 2 | 7 | 0.72 | 28 | 43 | 268
Reactor sources
Accelerator-driven sources
CSNS
Our vision is to build and operate the world’s most powerful neutron source, enabling scientific breakthroughs in research related to materials, energy, health and the environment, and addressing some of the most important societal challenges of our time.

## Slide 6
1843 M€ construction cost 2013 prices
5 MW world’s most powerful particle accelerator
2MW at start of operation
15 experimental stations
20 ⨉ more sensitive on average than today’s best
at 2MW
800 experiments per year
2023 first science for users
13 member nations in the ESS ERIC

## Slide 7: How a spallation neutron source works
proton accelerator
target
moderator
sample
instrument
neutrons
“spallation” is the process that releases neutrons from the target nuclei

## Slide 8
Superconducting Proton Accelerator
Neutron Production Target
Experiments

## Slide 9: Organisation and People
499
Employees
54
Nationalities
~ 100
Collaborating Institutions
Notes: Updated September 2017

## Slide 10: September 2014

## Slide 12: ESS is 58 % complete
Peak of construction activity
Accelerator commissioning started
Instrument hall E01 handover summer 2019

## Slide 13: Financing and Governance
Host Countries Sweden and Denmark
Construction 47.5% Cash Investment ~ 97%
Operations 15%
Non Host Member Countries
Construction 52.5% In-kind ~ 70%
Operations 85%
13 European Member Countries
The European Spallation Source ERIC established in 2015

## Slide 14: In-kind contributions
Significant technical workpackages procured or constructed in partner countries rather than centrally
  partner holds and manages the risk
A project management challenge… but a political necessity
  Helps avoid situation where the host region benefits greatly and the others just pay cash
  ESS – 70% for non-hosts, 35% overall, just about manageable
  ITER – 90% in kind, close to unmanageable

## Slide 15
ESS In-kind Partners
Aarhus University
Atomki - Institute for Nuclear Research
Bergen University
CEA Saclay, Paris
Centre for Energy Research, Budapest
Centre for Nuclear Research, Poland, (NCBJ)
CNR, Rome
CNRS Orsay, Paris
Cockcroft Institute, Daresbury
Elettra – Sincrotrone Trieste
ESS Bilbao
Forschungszentrum Jülich
Helmholtz-Zentrum Geesthacht
Huddersfield University
IFJ PAN, Krakow
INFN, Catania
INFN, Legnaro
INFN, Milan
Institute for Energy Research (IFE)
ISIS - Rutherford-Appleton Laboratory, Oxford
Laboratoire Léon Brilouin (LLB)
Lund University
Nuclear Physics Institute of the ASCR
Oslo University
Paul Scherrer Institute (PSI)
Polish Electronic Group (PEG)
Roskilde University
Tallinn Technical University
Technical University of Denmark (DTU)
Technical University Munich (TUM)
Science and Technology Facilities Council
University of Copenhagen (KU)
University of Tartu
Uppsala University
Wigner Research Centre for Physics
Wroclaw University of Technology
Warsaw University of Technology
Zurich University of Applied Sciences (ZHAW)

## Slide 16: Ion source & LEBT installation
Ion Source inauguration

## Slide 17: Project management
Follow best practice
Based on US DOE Office of Project Management energy.gov/projectmanagement/project-management
Resource Loaded schedule
Sufficient contingency
Change control process
…

## Slide 18: Project planning strategy
Accelerator + ICS
CF + Target + NSS (Bunker+TBL) + ICS
NSS (Instrument Program)
RBOT
EOC
BOD
BOD – Beam on Dump
RBOT – Ready for Beam On Target
BOT – Beam On Target
SOUP – Start Of User Program
EOC – End of Construction
TBL – Test Beam Line
Beam Comm.
First instruments
In-kind deliveries
In-kind deliveries
Target Building
BOT
Science
Critical Path
In-kind deliveries
Building
occupancy
We are focused on delivering first science at ESS, initially with three instruments operational, as close as possible to our original goal in 2023

## Slide 19
Meets modern environmental expectations
  Green construction site
  Purchase all electrical power from renewable sources
  Waste heat recovery into Lund district heating system
Support for full computing, software and analysis chain
  Open data model, EOSC-compliant
Development of science and innovation campus between ESS and MAX IV light source

## Slide 20
✅ Science case
✅ Technical R&D, cost estimates understood
✅ Project management plan
✅ Credible funding and governance plan
✅ Stakeholder engagement
✅ Compelling investment case
A few closing observations:

## Slide 21: Why do big projects fail to get started?
In 2016 The European Strategy Forum for Research Infrastructures reviewed implementation progress of the projects on its roadmap
Found inadequate stakeholder engagement and lack of a credible funding plan to be the biggest barriers
  much more so than any weakness of the science case

## Slide 22
Stakeholders include
The General Public
Media, opinion formers
Students
Educators (STEM skills pipeline)
University bosses
Other science areas
Members of Parliament
Science Ministers
Finance Ministers
Opposition political parties
Local and regional politicians
Civil Servants
Economists
× 13 partner countries, each with their own science strengths, industrial profile, media and decision making culture

## Slide 23
Jobs
Innovation
Startup companies
Grand challenges
Education
Public outreach
Openness
Cultural value
International Collaboration
Science drives economic growth
Science for peace
Makes the country worth defending
Democracy
Prosperity
Normative values
Market values
shift in emphasis since the end of the Cold War
Scientists are much happier over here…
… but this is where investment decisions are now made

## Slide 24: A parting challenge
The biggest economic challenges of our time
Globalisation
Together with automation and new technologies
Leading to fewer good jobs
Leading to low growth, stagnant wages
No one really has the answer
… but general consensus that scientific innovation and STEM skills are key
  at least economies and people that have these skills will be better positioned
So what is our project going to do to help?

## Slide 25
Thank you!
@johnwomersley @essneutron europeanspallationsource.se