## Slide 1
ILC tunnel lengths & Commissioning
with
E-driven e+ source
and, a Proposal of the separate tunnel
for the e+ source
T. Omori, 3-Sep-2018
POSIPOL 2018, Sep 3rd - 5th, 2018
CERN, Geneva, Switzerland

## Slide 2
ILC tunnel lengths
E-driven e+ source

## Slide 3
laser straight
laser straight
geoid
geoid
geoid
geoid
BDS tunnel
BDS tunnel
A
Option A
Note:
This was called "Option C" by the end of the last year

## Slide 4
with E-driven e+ source
2361m
with E-driven e+ source 150 m
with E-driven e+ source 150 m
with E-driven e+ source
Total tunnel length 18.5 km
with E-driven e+
remove 3 GeV ML
(130m)
with
E-driven e+ source
With E-driven e+ source, length of electron-BDS becomes significantly shorter (3489m -> 2361 m).
laser straight
laser straight
geoid
geoid
geoid
geoid
BDS tunnel
BDS tunnel
A
Note:
This was called "Option C" by the end of the last year
Option A

## Slide 5
2.36km
2.36km
6.88km
6.88km
total : 18.48 km
3.49km
2.36km
7.31km
7.39km
total : 20.55 km
Option A 31.5 MV/m
laser
straight
laser
straight
geoid
geoid
laser
straight
laser
straight
geoid
geoid
e- BDS
tunnel
Option A 31.5 MV/m
e- linac tunnel
e+ BDS
tunnel
e+ linac tunnel
e- BDS
tunnel
e- linac tunnel
e+ BDS
tunnel
e+ linac tunnel
Tunnel Length Comparison
IP
IP
ILC with undulator positron source
ILC with E-driven positron source

## Slide 6
3489m
2361m
Note:
This was called "Option C" by the end of the last year
Option A

## Slide 7
with E-driven e+ source
2361m
3489m
2361m
with E-driven e+ source 490m
with E-driven
e+ source
1500 m
With E-driven e+ source, length of electron-BDS becomes significantly shorter (3489m -> 2361 m).
Access tunnel to the electron-BDS becomes shorter too (690m -> 490 m).
with E-driven e+ source
Total Accelerator tunnel length
18.5 km
Note:
This was called "Option C" by the end of the last year
Option A
with
E-driven e+ source

## Slide 8
(1) With E-driven e+ source, length of several tunnels can be shorter.
Summary of Tunnel Length
(3) Especially length of electron-BDS (where e+ source is located) becomes
significantly shorter (3489m -> 2361 m).
(4) The access tunnel to the electron-BDS becomes shorter too
(690m -> 490 m).
(5) Both (3) and (4) mean tunnel construction period of electron-BDS
can be shorter than that of the baseline design.
-> possibility of early commissioning of the central part (source and DR).
See next page.
(2) Total footprint length becomes shorter, 20.5 km -> 18.5 km.

## Slide 9
Commissioning strategy
with E-driven e+ source

## Slide 10
Commissioning Strategy
(1) E-driven e+ source is independent of the e- main linac.
(2) Make use of the short construction period of e-BDS tunnel and
the independence, maybe we can start the commissioning of the
e+ source earlier than that of main linacs.
(3) We would like to make an integrated commissioning strategy of ILC
with an integrated tunnel construction plan, in order to start physic
run as early as possible.
My Proposal

## Slide 11
Construction and Commissioning
of e+/e- sources and DR
Central Part Commissioning
sources and DRs
1.5y
Optimistic plan or materials to trigger discussions
ML construction
MLs and ML tunnels
1y
Making Parts
Acc. tubues, Magnets
Klystrons, Modulators
Target, FC, etc.
preparation
production
Installation
Tunnel construction
tunneling, access holes,
finishing, water, electricity
preparation
construction
1.5ys
5ys
1.5ys
5ys
1y
e+ Source Construction
Global Commissioning
with ML
9ys (ML tunnel const. + ML const.)
year
1
2
3
4
5
6
7
8
9
10
year
1
2
3
4
5
6
7
8
9
10

## Slide 12
reference: Construction and Commissioning in TDR

## Slide 13
Summary of Commissioning Strategy
(1) What I showed today is just to trigger discussions.
My Proposal
(2) We would like to make an integrated commissioning strategy
of ILC with an integrated tunnel construction plan, in order to
start physic run as early as possible.

## Slide 14
E-driven e+ source in
a Separate tunnel

## Slide 15
with E-driven e+ source
2361m
3489m
2361m
with E-driven e+ source 490m
with E-driven
e+ source
1500 m
With E-driven e+ source, length of electron-BDS becomes significantly shorter (3489m -> 2361 m).
Access tunnel to the electron-BDS becomes shorter too (690m -> 490 m).
with E-driven e+ source
Total Accelerator tunnel length
18.5 km
Note:
This was called "Option C" by the end of the last year
Option A
with
E-driven e+ source

## Slide 16
with E-driven e+ source
2361m
3489m
2361m
with E-driven e+ source 490m
With E-driven e+ source, length of electron-BDS becomes significantly shorter (3489m -> 2361 m).
Access tunnel to the electron-BDS becomes shorter too (690m -> 490 m).
with E-driven e+ source
Total Accelerator tunnel length
18.5 km
Note:
This was called "Option C" by the end of the last year
Option A
Close up -> next page
with E-driven
e+ source
1500 m
with
E-driven e+ source

## Slide 17
Interaction Region
AT・DR (access point to DR)：763m
AT・DH (branch to detector hall)：693m
2361m
2361m
PM-8
PM+8
AT-8：490m
AT+8：283m
Close up view of the central part

## Slide 18
Slope of
the surface
down
up
2361m
2361m
PM-8
PM+8
AT-8：490m
AT+8：283m
the triangular prism shows
the slope of the surface

## Slide 19
Slope of
the surface
down
up
E-Driven e+ source
1081 m
2361m
2361m

## Slide 20
Slope of
the surface
down
up
E-Driven e+ source
1081 m
Put it into
the BDS tunnel
2361m
2361m
Shared tunnel plan
(current plan)
Shared tunnel plan

## Slide 21
Slope of
the surface
down
up
Put it into a separate
tunnel and
make access
to the surface
E-Driven e+ source
1081 m
2361m
2361m
cost of access tunnel needed
Separate tunnel plan
with additional access tunnel
additional access
to the surface
cost of access tunnel needed

## Slide 22
Slope of
the surface
down
up
E-Driven e+ source
1081 m
Put it into a
Separate tunnel
parallel to the BDS
and make connections
between them.
The separate tunnel
at DR side
looks reasonable
-> working assumption
Separate tunnel plan
parallel to e- BDS tunnel
We choose this a working assumption today.

## Slide 23
e- BDS tunnel (L=2.3 km, w =14 m)
put e-Driven e+ source in the BDS tunnel
e- BDS tunnel (L=2.3 km, w =7.5 m)
e-Driven e+ source tunnel (L=1.1 km, w =9 m)
• Separate tunnel plan
Shared tunnel plan and Separate tunnel plan
• Shared tunnel plan

## Slide 24
e- BDS tunnel (L=2.3 km, w =14 m)
put e-Driven e+ source in the BDS tunnel
e- BDS tunnel (L=2.3 km, w =7.5 m)
e-Driven e+ source tunnel (L=1.1 km, w =9 m)
• Shared tunnel plan
• Separate tunnel plan
• e-Driven e+ soure, RTML, BDS are located.
• undulator e+ source will be added later.
• RTML and BDS are located.
Shared tunnel plan and Separate tunnel plan
• later, tunnel will be widen and
undulator e+ source will be added

## Slide 25
e- BDS tunnel (L=2.3 km, w =14 m)
put e-Driven e+ source in the BDS tunnel
e- BDS tunnel (L=2.3 km, w =7.5 m)
e-Driven e+ source tunnel (L=1.1 km, w =9 m)
• Separate tunnel plan
(a) cost down
(b) cost up
very rough estimation: (a) + (b) ~ 0
Shared tunnel plan and Separate tunnel plan
• Shared tunnel plan
• e-Driven e+ soure, RTML, BDS are located.
• undulator e+ source will be added later.
• RTML and BDS are located.
• later, tunnel will be widen and
undulator e+ source will be added

## Slide 26
Separate tunnel plan
e- BDS tunnel
(L=2.3 km, w =7.5 m)
e-Driven e+ source tunnel
(L=1.1 km, w =9 m)
3 m
1.5 m
Service
Tunnel
Shield
BDS
RTML
3 m
7.5 m
3.5 m
1.5 m
Service
Tunnel
Shield
e+ Source
Tunnel
4 m
9 m

## Slide 27
Summary of Separate tunnel
(1) What I showed today is just to trigger discussions.
My Proposal
(2) Separate tunnel for e-Driven e+ source has potential to make
early commissioning easier.
(3) We can make BDS tunnel (L=2.3 km) narrower (w= 14 m -> 7.5m).
The cost down by the narrow BDS tunnel probably compensate
the cost up by making a separate tunnel (L=1.1 km, w=9 m) for
the e+ source. (we need detailed study)

## Slide 28
Polarization Upgrade
If we start with the E-driven e+ source, we need an upgrade path to the undulator source.
The question is "Can we have it?"
Especially, can we have it when we start with shorten BDS tunnel?

## Slide 29
Polarization Upgrade
If we start with the E-driven e+ source, we need an upgrade path to the undulator source.
The question is "Can we have it?"
Especially, can we have it when we start with shorten BDS tunnel?
Yes we can. We can put undulator and photon drift in the geoid tunnel. --> Yokoya-san's symmetric laser straight scheme

## Slide 30
Yokoya-san's symmetric laser straight scheme
• Only BDS tunnels are laser straight.
• Straight part is symmetric wrt the IP
• Undulator and photon drift (and, of course ML) are in the geoid tunnel.
Polarization Upgrade

## Slide 31
The END
Thank you for your attention.

## Slide 32
A
Note:
This was called "Option C" by the end of the last year
Option A

## Slide 33
My Proposal and Assumption
with E-driven e+ source
Make use of the shorter tunnel length and make effort to optimize tunnel construction schedule of near DR (*), we may try to make it possible to start commissioning of e+/e- sources and DR earlier than global commissioning.
* Length of DR access tunnel is 763 m.
It is half of the longest access tunnel at ML.
* Length of ½ DR tunnel is 1500 m.
It is shorter than a half section of
ML tunnel
* Length of DR connecting
tunnel is 530 m.
* Length of RTML
tunnel is 250 m.
direction of tunnel construction

## Slide 34
K. Yokoya, LCWS2017, 26/Oct., Strasbourg
• In TDR, it is assumed that central region tunnels is finished 1.5 years
earlier than main linac tunnels. Then it is assumed that central region
commissioning starts 1.5 years earlier than global commissioning.
• Today, people say that earlier start of central region commissioning is
NOT realistic.
What TDR says

## Slide 35
Commissioning of the e+ injector system
E-gun
Driver e- Linac
(3GeV)
Target
Capture Linac
(250MeV)
e+ Booster Linac
(5GeV)
e+ DR
(5GeV)
The Tuning Dump
at 100 MeV
The Tuning Dump
at the end of
Driver e- Linac?
(very low current)
Necessary?
Permanent?
Temporally?
The Tuning Dump
at theend of Capture? (at 250 MeV)
(very low current)
Necessary?
Permanent?
Temporally?
• Basic strategy: Commissioning of the entire e+ injector system will be
done through e+ source and the e+ DR at once (一つの放射線申請).
• No partial commissioning will be performed in the injector system.
If we make the commissioning step-by-step for each part (個々別々
の申請), it will rather take long time.
• However the tuning of very low radiation operation at some part may
be useful. Tuning at 100MeV point of the driver e- linac will be useful.
How about at the end of the Driver e- Linac? Maybe NOT necessary?
How about at the end of the Capture? Maybe NOT necessary?