## Slide 1
POPS-B project follow-up
LIU-PSB Meeting 217 03 July 2018
Fulvio Boattini TE/EPC

## Slide 2
POPS B
Main Power Converters

## Slide 3
Main Power Converters
MPC control electronics installation  end July
(FGC, DCCT, DIVPAM, PLC…)
Cooling pipes connections  end July
LV Switchgears and cabling  end July
MV cables and cable heads  end August
Power transformers  end August
Magnetic and capacitor structures  end July
Dummy load  mid July

## Slide 4
Main Power Converters

## Slide 5
POPS B
QTRIM Converters

## Slide 6
QTRIM Converters
First Prototype  October 2018
Tests  December 2018
Series production  September 2019
Commissioning  December 2019 (on full load)
PANDORA

## Slide 7
POPS B
Trims 14 Converters
Trims 23 Converters

## Slide 8
TRIMS 14 and 23 Converters
Trims 14  installed
Trims 23  tests in December 2018 installation in February 2019
COMET

## Slide 9
POPSB remaining activities
EN-CV: realization of water treatment unit and routing of chilled water to the roof
EN/CV: installation of air intake grids and modification of firebrigade cabinet
EN/EL: completion of LV power and auxiliary cabling and testing of the installation and installation of lights in ctrl room
SMB/SE: Installation of explosion vents
SMB/SE: Installation of blast doors
SMB/SE: Steel door for capa room S401
SMB/SE: Modification of floor plates in converter hall
SMB/SE: Completion of CTRL room
BE/ICS: Installation of smoke pipes on top of converters.
TE/EPC: Commissioning of the power converters
TE/EPC: Tests of fuses protection
TE/MSC: replacement of dumping resistors
LS2 / end 2018
Mid August 2018
End of August 2018
BC 76805  ~30kCHF probably missing
End of July 2018
Sept-Dec 2018
LS2
End November