## Slide 1: Linac4 –PSB connection
Controls perspective
Ioan Kozsar BE/CO/IN

## Slide 2: Content
Present status
  Motivations
  Consequences
Future updates
  Timing
  CCS
  FESA
  InCA
  Applications

## Slide 3: Starting point
Commissioning requirements until connection
  Master/slave <-> PSB/Linac4 similar to PSB/Linac2
  Sequencing independent from the PSB
  Independent settings management
Consequences
  New telegram -> CLN4.LN4 TGM_NETWORK (virtual PSB)
  New cycle descriptor LN4.USER.<USERNAME>
  Stand-alone MTG

## Slide 4: CLN4.LN4 / LN4.USER.<USERNAME>
Affected layers
  Applications
    LN4OP profile
    Applications reading/using the LN4 telegram
      CO generic: CCM, WorkingSets, etc.
      OP and Equipment Groups’ expert applications
  FESA
    Instantiation & persistence files

## Slide 5: Linac4 connection
 Updates induced at all levels of the control system

## Slide 6: Linac4 connection – Timing
Switch off the LN4 MTG (coordinated with updates for LN3/LN4->LBE)
Update the PSB telegram (LIN4D group, users)
CCR MTG
OPER.LIC
354 MTG
CLN4.LN4
FEC1
FEC2
FEC4
FEC3

## Slide 7: Linac4 connection – FESA Instantiation / CCS
Replace LN4 with PSB timing domain
CCS will automatically do the replacement
Regenerate all FESA3 instantiation files
FESA2 approaching its EOL; still 27 classes to be migrated
<configuration> <description value="Stripping foil acq system"/> <timingDomain value="LN4"/> <accelerator value="LN4"/> <acceleratorZone value="LINAC4"/> <mainMuxCriterion value="USER"/> <lun idref="_160722143410_0"> <value>6</value> </lun> </configuration>

## Slide 8: Linac4 connection – FESA Persistence
Update the cycle descriptors
Tool to update all persistency files provided by FESA team
Map between PSB and LN4 users will need to be established if new users are defined for PSB (BE/OP)
<acquisitionDelay> <cycle id="0" name="LN4.USER.AD" value="0"></cycle> <cycle id="1" name="LN4.USER.NORMGPS" value="0"></cycle> <cycle id="2" name="LN4.USER.NORMHRS" value="0"></cycle> <cycle id="3" name="LN4.USER.LHC_MD_B" value="0"></cycle> <cycle id="4" name="LN4.USER.EASTA" value="0"></cycle> <cycle id="5" name="LN4.USER.EASTB" value="0"></cycle> <cycle id="6" name="LN4.USER.CNGS" value="0"></cycle> <cycle id="7" name="LN4.USER.SFTPRO" value="0"></cycle> …
</acquisitionDelay>

## Slide 9: Linac4 connection - Applications
LN4OP profile – update the TGM_NETWORK environment variable to OPER.LIC
CO generic applications: CCM, WS, etc. use the environment variable
OP and Equipment group applications might need checking (e.g. hard-coded selector)
Functional modifications due to the connection are led by BE/OP (fixed displays, etc.)

## Slide 10: Linac4 connection – Settings / InCA
Settings can be migrated…
OP would like to keep the settings; migration strategy to be defined
Destination cycle(s) to be defined by BE/OP (new?)

## Slide 11: Linac4 connection - Milestones
LN4 schedule:
  Runs until December 2018
  Restarts in June 2019
CO-related updates will need to be done by May 2019 (see LS2 Master schedule)
Installation requests – to be submitted by the end of September 2018
No major associated risk, rather a coordination effort