## Slide 1: PS WPAs for LIU-PS

## Slide 2: LIU New KFA45 installation
Scope:
  Test the old KFA45 in the ring before removing it (which requires the removal of MU44)
  Removal of the old KFA45 (Will be kept as spare – storage space confirmed)
  Installation of 12 new SF6 free cables
  Installation of the new KFA45
  Consolidation of the generators and their controls inside B.365
  Test the new KFA45 and associated services - IST
Challenges:
  Insure the services for the tests
  Space for the 12 additional cables between B.365 and SS45
  Keep the MU44 outside the ring until the new KFA45 is available (readiness date Jan/2020)
  Keep the KFA45 under vacuum (if needed) until the new internal dumps are available

## Slide 3: LIU BTP modification
Scope:
  Remove all equipment
  Replace some concrete slabs by metal slabs
  Mark the drilling for the new supports and perform the drilling
  Install the new supports
  Install the new equipment
  Align the new line
Challenges:
  The removal and installation of new equipment needs to be performed in synchronization with the MUs 38, 39 and 40 consolidation
  Storage for some equipment that will be re-installed
  Alignment – Procedure not yet defined for all new equipment
  Ownership of some supports
  The fact that we don’t have one unique responsible for all this work – I count a lot on the support given by Mike and Luis

## Slide 4: LIU New demineralised water circuit
Scope:
  Renovation of the cooling towers in B.255
  New cooling station in B.355
  New piping from B.355 towards central ring and then from there to the ring and TT2
  Connection of B.269 to this new circuit
Challenges:
  Maintain water available for the RF tests in B.353 (up to June 2019) and for the KFA45 test (Up to end of January)
  There are still some open points like how to arrive with the pipe from B.355 to gallery 1 (integration still ongoing)
  The connection of B.269 to this circuit
  All the connections in the PS Switch Yard

## Slide 5: LIU B.355 and B.365 modifications
Scope:
  Installation of TE-EPC power converters
  Cabling campaigns
  Connection to the cooling
Challenges:
  Works concerning 6 ECRs only for the part that concerns EPC
  Other installations that are not EPC like the WIC, BE-RF transverse feedback racks, TE-ABT works in B.365, …

## Slide 6: LIU Turning the 80 MHz cavity in SS88
Scope:
  Remove SS88 80 MHz cavity
  Store it under vacuum outside the ring for the period needed for the MUs 88 and 87 renovation
  Re-installation turned by 1800
Challenges:
  Find a secure space to store the cavity and keep it under vacuum for a duration of approximately 2 months (close to SS08)
  Take the cavity out of the ring
  Minimize the time the sector is vented

## Slide 7: De-cabling and Cabling
Scope:
  De-cabling of some areas that really need de-cabling for the installation of new cables (Aprox. 87 Kms of cable to be removed)
  Pull all cables requested (Aprox. 144 Kms of cables to be installed)
  Pull all fibers needed
Challenges:
  Fit in the planning
    The 53 days needed for the de-cabling campaigns (not all in the ring)
    The 345 days needed for the cabling campaigns (not all in the ring)
    The days needed for the optical fibres installation
  The fact that for a considerable amount of these campaigns no-coactivity is possible
  We need to manage to split some of the announced campaigns in smaller campaigns (not possible before beginning of August)

## Slide 8: Summary
WPA | Status | EDMS reference | Indico event reference | ECR
LIU New KFA45 installation | Performed the 31/05/2018 | Document available but not yet in EDMS | 728802 | 1969894
LIU BTP modification | Performed the 12/07/2018 | Document available but not yet in EDMS | 741393 | Not yet available
LIU New demineralised water circuit | Performed the 24/05/2018 | Document available but not yet in EDMS | 728791 | 1835995
LIU LINAC4 connection and associated tests (LIU-PSB) | TBD |  | TBD | 1805620, 1688400, 1688387
LIU B.355 modifications | Performed the 28/06/2018 | Document available but not yet in EDMS | 732721 | 1936132, 1841891, 1886929
LIU B.365 modifications |  |  |  | 
LIU Turning the 80 MHz cavity in SS88 | Performed the 05/07/2018 | Document available but not yet in EDMS | 728805 | 2004437
LIU B.269 modification | TBD |  | TBD | 1870629
Cabling / De-cabling | Performed the 03/07/2018 | Document available but not yet in EDMS | 733810 | NA