# LIU-PM-MIN-0434	EDMS 2020631

# LIU project team meeting

# Notes from the meeting held on 13 September 2018

Present:	G. Bellodi, J. Coupard, G. P. Di Giovanni, A. Funken, B. Goddard, K. Hanke, M. Meddahi, G. Rumolo, R. Scrivens

Excused: A. Lombardi

- Arising matters (M. Meddahi, G. Rumolo)

- Concerning the participation to IPAC 2019 (in Melbourne, Australia): LIU-SPS has approved a 50% LIU funding for Michele Carlà (BE/ABP) and Aaron Farricker (BE/RF); LIU-PS will fully fund Florian Bertin (BE/RF); No requests have been received for LIU-PSB and LIU-ions. This closes the exercise and only the above fellows will be funded by bc 62011, within the approved IPAC2019 guidelines, to be soon distributed.

- Malika received green light from Freddy to organise a dedicated LIU event in 2019. This will take place in the week of 11 February and will involve one or two nights away. The three pillars that will be discussed within the LIU team over this event will be: LIU beam parameter reach and HL-LHC request, LS2 planning and work advancement, plans for post-LS2 beam commissioning.

- Giovanni clarified the performance reach for ions with the 75 ns scheme (i.e. 3 bunches from LEIR batch compressed to 75 ns at the PS flat top). In terms of integrated luminosity, this scheme can only make 67% of the target, or 71% if the 125 ns spacing between batches in the SPS can be put in operation. J. Jowett’s statements at the LMC on 29 August concerned the possible achievement of a record peak luminosity (even beyond HL-LHC) with this scheme, which one could obtain for ATLAS and CMS (i.e. without leveling) if we assume that all the intensity of the 4 bunches of the nominal scheme can be squeezed in the 3 bunches of the 75 ns scheme. This is anyway also not correct, because the SPS transmission plummets from ~55% to 40% when increasing by 4/3 the bunch intensity at injection.

- LS2 planning and general update on LIU-PLI activities (J. Coupard)

- Two ECRs for SPS were reviewed at the last PLI meeting:

  - New RF power feeder lines in SPS point 3 (TA3 and LSS3). This was approved and Sonia will present it to IEFC next week. There is a pending issue concerning the integration of the new sprinkler system in LSS3 for the fire safety (“Mission Impossible” challenge for Integration team)

  - Installation of kicker pulse generators and control equipment in SPS Point 5 during LS2. This was “almost” approved, since there are still cooling pipes and fire detection to be integrated and validated before getting to the final approval. Sonia is following up this part with Fred and will present the ECR to IEFC when actions are complete.

- 27 ECRs remain to be approved for LIU, which have not yet been circulated (1 for ions, 5 for PSB, 10 for PS, 11 for SPS). The configuration managers have this list and they participate in the coordination meeting to remind the responsible people. In most cases, details of integration are missing, but it should be checked more closely, because some times these are not blocking details.

- 7 ECRs are under approval for beam line equipment (2 PSB, 5 PS). Tom is checking what can be approved according to the Integration status.

- 16 ECRs are under approval for EPC. Blanca is checking what can be approved according to the Integration status.

- Integration studies are progressing but with lots of studies to be still completed.

- Planning, schedule:

  - LIU-PSB Linac4 connection. A first internal review was held on the impact of the (de-)cabling campaigns, in particular for the Linac4 run in 2019. The inventory in progress, an issue with general lock-out could come only because of the new ERD installed by James, which is connected to PS power supply. Gerard Cumer is checking, Ana-Paula is aware

  - LIU-SPS RF Upgrade schedule in LS2. The minutes of a first meeting on this subject are available in the document EDMS 2025098. More input from RF is expected in two weeks time to proceed with the planning of the 5 months foreseen by RF for their work.

  - LS2 days will take place on 9-10 October. Malika agreed with Miguel that there will be no need for a dedicated presentation to LIU at this event. All the LIU activities will be addressed individually by the single groups in their presentations, and then Julie will discuss the general schedule including all LIU activities. For information, a cost and schedule review for the Fire Safety Project Review, chaired by M. Lamont, will take place the day after the LS2 days, i.e. on 11th October.

- Round table on progress on the various activities

Linac4  – G. Bellodi

- The set up of the beam up to 3 MeV has been finished last week with maximization of transmission through RFQ.

- 25 mA and pulses of 600 us are reproducibly obtained after RFQ.

- Studies of source stability are ongoing, in particular for pulse flatness and shot-to-shot reproducibility. Different regimes have been explored and by next week a decision will be made on the source standard operation. There is still a drift due to cesiation, which might require increasing the frequency of cesiation.

- The RF tuning has been finished and now there will be cavity phasing over this week.

- The general planning of the run is available in ASM and in the machine check-out tool. Bettina is currently preparing a google document to produce the detailed planning for the month of October.

- Work is ongoing on the source test stand.

PSB – G.P. Di Giovanni

- EN-CV

  - G. Petrika presented the status and activities of EN-CV, excluding B245 whose WP is handled by J. Rodary.

  - In general, all cooling activities are proceeding well.

  - The consolidation of the PSB ventilation was canceled accepting the potential risk of operating an old infrastructure.

  - It is confirmed that cooling will be available on time, i.e. mid Nov 2019 for RF to start testing their equipment.

- Safety files

  - A. Funken presented the status of the safety files in the PSB.

  - The list of equipment that should undergo electrical and pressure testing is being collected, such that HSE could organise and document the dedicated inspections. Deadline: end of the month.

  - General good response from PSB WP holders. More work needed on the Linac4.

- TE-MSC:

  - A. Newborough presented the status and advancement of the LIU-PSB WP3, magnets.

  - All workunit orders have been placed

  - Most of the WUs are under control, but the main critical item is BTM.BHZ10, for which the manufacturer is having difficulties achieving the required tolerances on the yoke. However, it is anticipated that delivery will be ‘just in time’. Close and constant follow-up is in place with several layers of the TE-MSC hierarchy. At the end of this month, the situation should be clearer.

  - A delay of the BTM.BHZ10 will impact the schedule. D. Hay has been contacted by A. Newborough and a discussion is ongoing on how to reshuffle the schedule to accommodate a late arrival.

  - LIU will meet TE-MSC next week, on 19th September.

- Linac4/PSB applications:

  - J.F. Comblin reported on the status and preparation for the OP applications for Linac4 and PSB.

  - The planning is clear. This is a large workload for OP, but all developers have been engaged to be able to meet the deadline. So far no showstopper is anticipated.

  - Few applications are under discussion to better define the specifications.

- EVM reporting:

  - S. Prodon reported the EVM status in the PSB

  - The current schedule variance shows a delay of -2.00 months, almost entirely accumulated in the last two months (in July the delay was -0.65 month). However, the cost variance is positive, i.e. the project is saving money.

  - This is probably due to the EVM not being regularly updated during the summer months so individual emails have been sent to the responsible people, who have started filling their EVM. After this exercise, it will be possible to distinguish what WPs are really delayed and by how much.

PS – K. Hanke

- E-mails have been sent out this morning to all WP holders to remind them to make their EVM reporting before tomorrow.

- BI

  - WS: There have been a few iterations with BI, now the list of measurements to be done for validation of the new prototype has been produced.

  - Injection SEM grid: The progress is being followed on a weekly basis to attempt organizing a future MD session to use this instrument.

- Budget transfer for TOF sweeping magnet: This is anyway a CONS to CONS transfer (because TT2 matters are managed within LIU but they are linked to a CONS budget). The 90 kCHF originally budgeted for the magnet will be transferred to magnet group to build the new permanent magnet. The cost of this magnet has been estimated around 130 kCHF, so the remaining money will have to be found elsewhere.

- At the LIU meeting with ABT taking place tomorrow afternoon, Klaus will be replaced by Heiko.

SPS – B. Goddard

- RF 200 MHz upgrade:

  - Final short-circuit test was passed yesterday with 80 modules on the tower, coming after 2-3 weeks of difficulties.

  - Now the design of the modules is fully validated and we can release a first payment for Thales and move to the series production – to be prepared in next 3-4 months and with special attention that all the modules produced will have the required quality

  - Present schedule has 32 towers delivered by end December 2019

- Report on 200 MHz LLRF upgrade Review (held in March 2018) is ready and will be circulated this week. No changes yet in the internal RF coordination between SW and HW/FW teams, an action on this is expected.

- Layout changes for BI in half-cell 519 have been almost finalized. All the instrumentation has to be moved to other locations with less prompt and residual activation - triggered by small changes seen with the final shielding design, but anyway too high. The deadline for VSC to finalize changes is next week.

- LSS3 cabling/CV works are being planned, but there appears to be a lot of conflict and difficulty to fit into the 9 months available. The options presently on the table are to work more shifts per day, to reduce the scope of some of the works, or to extend the shutdown. A decision will be needed at the management level.

- There has been a discussion in TE/ABT as to whether the single test ZS in LSS6 should be removed. It will be decided within a few days – and if so, it will need new chambers, vacuum layout, ECR.

- Many people are late with EVM reporting, including a couple of important WUs, it is being attempted to get these updated by tomorrow before Sylvie’s data extraction.

PS-ions – R. Scrivens

- There is a coordination meeting next week, concentrating on safety, as Anne is working on the Linac3 safety file.

- Some changes in ABP and BI budget have been clarified with Sylvie.

- Malika asked to check that the EVM reporting on the WPs of LIU-ions is up to date by tomorrow. Action: Richard

Safety – A. Funken

- The fire protection strategy for building 245 was presented to the PS-CSAP on 30th of August. It allowed convincing the PS-CSAP that no additional measures are required for building 245 regarding the fire hazard of the steel structure. A technical note has to be written to explain and document the studies done and the outcome. The demonstrative part is being updated following the other comments received from the PS-CSAP.

- LIU-SPS dump upgrade: EDMS review of the demonstrative part by the contributors and GLs has been launched. The deadline for comments is 21/09. This will be on the agenda of the next SPS-CSAP (27th of September).

- LIU-SPS RF systems upgrade: The descriptive part is being updated. The demonstrative part is being prepared on the same principle as the LIU-SPS dump upgrade. Support is needed from the project side to prepare documents reflecting exhaustively what has been done/will be done in terms of safety and point out any changes having an impact on safety (e.g. building BAF3: the layout of equipment on the mezzanine differs from the one that is taken into account in the present calculation note. New layout requested to BE/RF to allow SMB/SE to redo the calculations). Action: Anne to organize a meeting with Brennan, Eric Montesinos and Gino Cipolla within two weeks to gather all needed safety file information.

- LIU-ions: Safety files for Linac3 are being restarted with help of Richard and Detlef. The aim is to present descriptive and demonstrative parts to the PS-CSAP in November.

- Forecasts of HSE pre-visits regarding electrical safety (risk of direct contact) and HSE inspections (electrical and pressure): A forecast should be provided to HSE (Cecile Pinto) by the end of September. Information is still missing for the LIU-PSB (https://indico.cern.ch/event/734050/) & Linac4-to-PSB connection, LIU-PS and LIU-SPS and LIU-Ions (Linac3, LBS line and source oven). Mainly the needs for pressure inspections need to be provided for LIU-PSB and LIU-PS.

- Safety documentation as required by the LSAs: When needed, Anne will organize dedicated meetings to clarify with HSE and the groups what is the list of documents to provide and the contents, in particular for the inspections.

- AOB

- On Thursday 20 September, 2018, there will be an LIU Beam Performance meeting in which the status of high intensity studies in the PS/SPS will be reviewed.

- The next LIU-PT meeting is planned to take place on Thursday 27 September, 2018.

Minutes by G. Rumolo