## Slide 1: OpenSE 2.0 Task force
Task Force II : Project Lifecycle and Key deliverables
N. Latif, B. Nicquevert, B. Ferreira, E. Peyrat, E. Harrouch, T. Wijnands

## Slide 2
Mandate
Deliverable :
A 20-min presentation to be given on 11 October a.m.
Goals :
• Reviewing the OpenSE knowledge domain as featured in the OpenSE booklet,
• Discussing the appropriateness w.r.t. projects typologies at CERN,
• Discussing the alignment with other standards such as PMBoK, HERMES, PRINCE2, ..
• Discussing the limitations due to CERN support tools such as EDH, MS Project, CERN templates
• Propose improvements (with a rationale), for both the booklet and the OpenSE training material
Note: the aim is not to start rewriting the booklet nor to make a new set of training handout slides!

## Slide 3
OpenSE 2.0 - lifecycles
 | Predictive | Iterative | Agile
Requirements | Defined up front | Elaborated periodically | Elaborated frequently
Delivery | Final delivery at the end | Deliver subsets | Deliver small and ‘customer valued’ subsets
Change | Constrained | Incorporate occasionally | Continuous change during delivery
Stakeholders | Key Stakeholders Involved only at key mile stones | Key stakeholders regularly involved | Key stakeholders continuously involved
Risk & Cost | Controlled via detailed planning Cost control via EVM for entire project | Risk and cost are controlled by progressively elaborating the plans with new information | Risk and cost are controlled as the user requirements and the constraints emerge during the project
Scheduling Tool | MS Project | ? | JIRA

## Slide 4
Lifecycle design - Project Phases
Minimum number of phases is 4
Each phase in the lifecycle must have
  Resource management (financial people, buildings, equipment)
  Criteria to entry a phase
  Criteria to exit a phase
  ‘Documentation’ at a transition
Each project needs at least :
  Approved Proposal
  Management plan
  Close out report
  Benefits plan (may be included in proposal if small)
‘A collection of logically related project activities that culminates in the completion of one or more deliverables’
Rules :

## Slide 5
Documentation @ phase gates
Project Business case
Project Charter
Project Management Plan
Benefits management plan
At the end of a phase, compare the project information against the information that can be found in :
‘every phase needs to be initialized, planned, executed, monitored and controlled and closed’
Results of this comparison can be :
Continue to the next phase - RAS
Remain in the current phase
Rework deliverables from the current phase
Stop the project
Continue to next phase with modifications

## Slide 6
Project Phases
Concept development
Feasibility Study
Customer Requirements
Solution Development
Design
Prototype
Build
Test
Transition
Commissioning
Milestone review
Lessons learned
Examples of phase names :
Management Needs
Nature of the project
Unique characteristics of the company or the technology
Project elements including technology, engineering, business, process or legal
Decision points
Criteria to establish a phase :

## Slide 7
Project Life Cycle
Starting
the project
Organize
and prepare
Carry out the work
Ending the Project
Project Phase
Project Phase
Project Phase
Project Phase
initiating
planning
executing
monitoring
closing
Integration
Scope
Schedule
Cost
Quality
Resource
Communications
Risk
Procurement
Stakeholder
© PMBok PMI 6thEd

## Slide 8
Business Case

## Slide 9
Business Case (without excel !)
Question 1 : Are the ‘pain’, the ‘need’ and the ‘desire’ clearly defined (PND statement) ?
Question 2 : Is the proposed solution compelling and in line with the strategy of the group/department/organization or project ?
Question 3 : Would the strategic objectives of the organization be at risk if nothing were done?
Question 4 : What are the alternative solutions and why are these not preferred? Is this solution the best choice ?
Question 5 : Will the desired outcome satisfy the stakeholders?
Question 6 : What are the risks ? Are the risks manageable with the resources we will have ?
Question 7 : Is the level of uncertainty due to unknowns in the project acceptable ?
Question 8 : Is there a clear definition of success and a clear definition of failure?
Question 9 : Can all the required resources realistically be obtained?
Question 10 : Is the team capable and motivated of delivering success?

## Slide 10
Benefits
Environmental Assessment (Internal/External)
Business Case
Benefits Plan
Project Charter
Project Management Plan
An outcome of actions and/or behaviors that provide utility, value or positive change for the recipients

## Slide 11
Benefits Management plan
How to create, optimize and sustain the benefit provided at the end of the project ?
Question 1 : What are the benefits envisaged by the project ?
Question 2 : How will the performance of the benefits be measured ? (KPI ?)
Question 3 : What is the Net Present Value of each benefit ? (what discount rate ?)
Question 4 : What is the timeframe for realizing the benefits ?
Question 5 : What are the negative impacts of the benefits ? (what does the change mean)
Question 6 : Who is impacted by the change ? (who are the stakeholders)
Question 7 : Who will be in charge of realizing the benefit ? (owner of the new idea, service, product)
Question 8 : When will the ongoing responsibility be transferred ? (end of project/start operations)
Question 9 : : How will the ongoing responsibility be transferred ? (task force, transition project, activity)
Question 10 : How will the benefits be sustained ? (what operational budget ?)

## Slide 12
Example
Calibration of RP instruments
Outsourcing
Build a on-site facility (Bat 772)