# 57th Meeting of the HL-LHC Technical Coordination Committee – 13/09/2018

Participants: A. Apollonio, V. Baglin, M. Bajko, A. Ballarino, I. Bejar Alonso, H. Burkhardt, S. Claudet, D. Delikaris, B. Delille, A. Devred, P. Fessia, J. Gascon, M. Giovannozzi, N. Grada, T. Lefevre, H. Mainaud Durand, P. Martinez Urios, M. Martino, R. Martins, E. Metral, M. Modena, Y. Papaphilippou, A. Perin, M. Pojer, P. Retz, L. Rossi, F. Sanchez Galan, J. Serrano, L. Tavian, E. Todesco, R. Tomas Garcia, S. Yammine, R. Van Weelderen, D. Wollmann, M. Zerlauth (chair).

Excused: O. Brüning.

The slides of all presentations can be found on the website and Indico pages of the TCC.

M. Zerlauth recalled the decisions taken during the 56th HL-LHC TCC.

The first decision regards the approval of the proposed measures by WP3 to increase the b6 in the MQXF magnets. The ECR will be soon circulated for approval.

The second decision is related to the removal of the inner layer quench heaters from the baseline as a redundant protection system to the outer layer heaters for the HL triplets. The baseline will be outer layer quench heaters and CLIQ.

The third decision regards the approval of the proposal to increase the average degradation limit of the bundle barrier PIT cable to 10 %, while keeping the 5 % for the RRP cable. As a follow-up of this decision, MSC should report in the TCC on the outcome of the discussions concerning documentation for cable acceptance criteria.

# IT String day – M. Bajko - slides

M. Bajko introduced the scope of the upcoming IT String review, focusing on the baseline configuration and on the motivation of the associated test program. The review will include considerations regarding personnel and budget. L. Rossi commented that each WP should focus on the foreseen tests in the STRING, mentioning where applicable if tests could be performed in another configuration (e.g. with individual tests) and highlight the advantage of such tests in the full STRING configuration. M. Bajko pointed out that several WPs are counting on tests in the STRING, so no mockups for individual tests are foreseen today. These might lead to additional costs that should be taken into account in the overall evaluation. L. Rossi agreed and encouraged the different WPs to quantify the possible additional costs in case testing in the STRING would not be possible. T. Lefevre commented that for BI for example additional requests for tests to other WPs should be considered without STRING tests. Such tests could be ranked by importance, but potentially each missing test can lead to delays during setting-up of the system in preparation for HL operation.

The review will take place during a single day, with an internal review panel chaired by L. Tavian. As an outcome of the review an executive summary and some recommendations to the CERN management will be provided.

M. Bajko introduced briefly the scope of each talk in the agenda for the STRING day. She mentioned that it is under consideration to add one talk for BI. T. Lefevre mentioned that BI can also provide contributions to other talks where applicable (e.g. alignment, cooling, vacuum), without necessarily requesting a dedicated talk.

L. Rossi stressed that the review should also address the necessity of performing all tests, or possibly to reduce their number and duration, as operating the STRING also entails very high costs and manpower resources.

M. Zerlauth asked if it would be possible to share the latest version of the schedule and planning with all WPs, to make sure all evaluations are based on a common reference for the review. M. Bajko will circulate the latest version of the planning in the coming days. L. Rossi stressed the importance for each WP of stating what are the risks of not respecting the schedule, as having all systems available is clearly a crucial requirement for the STRING test.

# Test results for cryostats for SC link without thermal shield and ECR – A. Ballarino – slides

A.  Ballarino reported to the TCC on the results from the cryogenic tests of the passive cryostats for the SC link. The tests have been running for several months and several groups contributed to this activity of WP6a.

A.  Ballarino recalled the motivation behind considering cryostats without actively cooled thermal shield. When the length of the SC Links was significantly reduced following the new HL underground configuration, the possibility of using flexible cryostats with no active cooling was already considered. This is a consequence of the reduced total integrated thermal load (W/m for a shorter length), while keeping the same enthalpy available (same mass flow rate and same THe). The main advantages of a passive cryostat are a lower weight, a much easier handling, a smaller outer diameter of the SC Link cryostat and a simplified design of the DFH cryostats, overall yielding significantly lower costs of the system. On the other hand, the main disadvantage of a passive cryostat is the higher static heat load. The procurement for 60 m long passive cryostats with a challenging target static heat load of 1.5 W/m was launched. Three companies (Nexans, Cryoworld, Criotec) provided each two cryostats, one with active shield and one without. The baseline today is a 4-walls cryostat (active cooling).

A.  Ballarino highlighted the importance of the experience gained during handling of cryostats and integration of dummy cables. Experience confirmed the easy handling (spooling/un-spooling) of the cryostats without shield.

A.  Ballarino provided a summary of the tests performed in SM18 with three passive cryostats, with different design and tested in different configurations, both horizontal (slide 9) and with a bending radius (slide 11) to study the possible effects on the heat load. The results of the cryostat from Cryotec were significantly worse than those from the other two companies (about 4 W/m wrt 1.5 W/m). However, even the cryostat from Cryotec could be operated with no problems. The tests showed that low heat load can be achieved (1.5 W/m was measured on the Cryoword cryostat and about 2 W/m on the Nexan cryostat). The proposal is therefore to maintain a specification for a heat load < 1.5 W/m for the HL triplets, keeping some margin with respect to the 2.5 W/m that could be tolerated from cryogenics perspectives.

A. Ballarino mentioned that an ECR describing the proposed change of baseline to a cryostat without active shielding is ready to be circulated. S. Claudet commented that the results look very good. He pointed out that the drawback of this solution is that any unexpected deformation (e.g. in the bent section) has a direct effect on the heat load since no thermal shield is anymore available. In such cases there is no way to recover from the cryogenic point of view with additional mass flow, but the non-conformity in the link would have to be corrected. M. Zerlauth asked if the link is instrumented sufficiently to identify and localise these cases. A. Ballarino explained that the link has larger temperature margin with respect to a Nb-Ti link. This will partially compensate for some non-conformity.

M. Bajko asked if local interventions could be possible in case of a damaged SC link. A. Ballarino explained that, independently from the cryostat technology (active or passive), the baseline is to replace a damaged link with a spare. Nevertheless, with the passive solution, the possibility to have local interventions is under consideration and was discussed with one supplier. This aspect is being considered for the final specifications.

L. Rossi asked what would be the order of magnitude of the total saving for the new solution. A. Ballarino commented that the cost of the passive cryostat is expected to be up to one third per meter length with respect to active cryostats. This estimate is based on the cost of the 60 m long prototypes. S. Claudet added that this change would have a small impact on the cost for cryogenics, but a big saving is also coming from the simplification of the DFXs and DFHs.

M. Modena asked if problems with long term reliability (e.g. due to thermal cycles) should be expected. A. Ballarino replied that these components have established industrial applications, they are based on the same concept of cryogenic transfer lines, so no major issues are expected.

B. Delille asked if the number of bends of the link in the final configuration could also affect their reliability. A. Ballarino pointed out that the bent configuration was tested with the cables inside the cryostat to reproduce this scenario and no issues were observed. M. Modena added that to reach the tunnel there will be at least two major bends. L. Tavian commented that in addition, more bends might be necessary to accommodate the extra length of the link, as the total length of ordering will have to include margins for the installation uncertainties.

T. Lefevre asked why the cryostats from Cryotec performed twice worse than the others. A. Ballarino explained that it is related to the design of the internal supports between the inner layer wall of the vacuum chamber and the cold, this was not expected by the company.

L. Rossi asked what are the plans with respect to Cryotec, which is at the moment not capable of providing cryostats conform to specifications. A. Ballarino mentioned that Cryotec is willing to replace the cryostat to be compliant with CERN’s requests. L. Rossi asked if it will be possible to test and verify that effectively they will comply with specifications. A. Ballarino explained that it will not be easy to redo the tests (it took one year the first time), nevertheless by setting tight specifications for the call for tender, compliance to CERN needs should be ensured.

M. Zerlauth recalled that the related ECR will be soon circulated and encouraged WP leaders to provide comments.

M. Zerlauth announced the next meeting of the TCC, which will be held on 20th September.