## Slide 1
117726 | Approved | LEIR | B - Beam Instrumentation | LEIR EE BCT Check | FBCTs verification
117998 | Waiting for Approval | PS&TT2 | B - Beam Instrumentation | LEIR injection BPM amplifier upgrade | Upgrade of amplifiers of BPMs in LEIR ETL line
117958 | Waiting for Approval | PS&TT2 | B - Beam Instrumentation | Upgrade of PR.BGI82 readout electronics | Replace GEFE based readout electronics with Versatile Processing Board & Quad GBTx.
117940 | Waiting for Approval | PS&TT2 | B - Beam Instrumentation | PS LIU wire-scanner inspection, tests and PMT installation S54 | We will perform functional tests of a wire scanner outside the vacuum connected to the scanner cabling. At the surface, we will Connect the new electronics platform dedicated to the motion control. We will also install a new photo-multiplier assembly made of 4 PMT for increasing the acquisition dynamic range.
117869 | Approved | PS&TT2 | B - Beam Instrumentation | SEMGRID SS52 | Visual inspection of the SEMGRID in SS52
117658 | Waiting for Approval | PS&TT2 | B - Beam Instrumentation | Inspection of PU cables | Inspection of PU cables
117655 | Waiting for Approval | PS&TT2 | B - Beam Instrumentation | FT16.UES208, FT16.UES228 maintenance | Test and calibration of UES208 and UES228 front-end electronics
117846 | Waiting for Approval | PS Booster | B - Beam Instrumentation | PSB 2L1 WS replacement | replacement of 2H WS in 2L1
117700 | Waiting for Approval | PS Booster | B - Beam Instrumentation | BTM line inspection for future BI equipments installation | BTM line inspection for future BI equipments installation
PS complex TS2 activity list

## Slide 2: PS complex LS2
ECR
Information to the group machine coordinator
Activity declared
WDP/RP assessment
IMPACT

## Slide 3
PS/TT2 LS2 overview:
General access from Tue 15/01/2019 to mon 10/08/2020
Several periods with total closure of some of the sectors because of:
Exchange of ~43 MU(BI support required)
LINAC4 connection test
Asbestos removal campaign
+ other long duration activities

## Slide 4
PSB LS2 overview
General access from mon 7/01/2019 to wed 8/04/2020
Dismantling phase at the beginning(BI support required)
BI line: week 2 to week 4 2019(BI.BTV30, BI.BPM20, BI.BCT10, BI.BTV20)
BT line: week 4 to week 6 2019
Section 1L1: week 7 to week 9 2019(BTV50,BTV60, BR3.MSF1L1 SEMfil)

## Slide 5
LINAC3 LS2 overview
General access from mon 10/12/2018 to Friday 26/06/2020

## Slide 6
10596 | Replacment of 7 BCTs in LINAC2 | LINAC 2 | removal of the old BI stuff 22-25/03/19 BI equipments installation 15-23/04/2019 | 
10198 | Completion of L4 transfer line installation after sector test (3 tanks, SEM+wires) |  | LINAC 4 | no date available
10071 | Installation of new SEM monitor for PSB injection matching | PS Booster | 08/07/2019 | 
10438 | Wire scanners for LIU in the PSB (BWSRE) x8 | PS Booster | 08/07/2019 | 
10632 | Modified BTVs for the Booster Transfer lines (BT2/BT3.BTV10 and BI.BTV30) | PS Booster | BI dismantling 30/01/19-11/02/19 BT dismantling 12/02/19-26/02/19 BI installation 04/09/19-24/09/19 BT installation 05/07/19-31/07/19 | 
11376 | Design and production of BT.BTV20 (x2 for KFA.10) | PS Booster |  | 
11549 | Stripline pickup in the BI line | PS Booster | un-19 | 
11630 | Consolidation of BTVs in the Booster | PS Booster | no date available | 
10393 | Replacement of obsolete SEMs in the PS | PS&TT2 | SS48 8-15/10/19 SS54 20-26/09/19 | 
10437 | Wire scanners for LIU in the PS (BWSRE) x5 | PS&TT2 | SS64 4-11/06/19 SS65 4-11/06/19 SS68 14-20/03/19 SS85 9-17/04/19 | 
10639 | New SEM for PS injection (Septum 42) | PS&TT2 | 8-15/10/19 | 
11088 | Installation of a second Beam Gas Ionisation monitor (BGI) in vertical plane | PS&TT2 | 1-8/04/20 | 
11631 | Exchange of TPS15 | PS&TT2 | no date available | 
Maintenance activities