| No | Technical task | Responsible institution and person | Deadline | Expected result | Cost of material | Cost of personnel | Link to the WP, milestone, deliverable |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Manufacturing of reaction vessel and simplified scrubber* | RTU, RKB, INCT, Remontowa | 01.07.2019. | Reaction vessel and simplified scrubber including all subsystems and integration interface fabrication using final technical documentation | To be filled by RTU, RKB, INCT, Remontowa | To be filled by RTU, RKB, INCT, Remontowa | WP2.3 T2.3.1. (T2.7.) D5 |
| 2 | Radiological dosimetry of assembled electron lamp and reactor vessel, for licensing authorities | RTU, CERN, Fraunhofer, INCT | To be filled by RTU, CERN, Fraunhofer, INCT | Radiological dosimetry of assembled electron lamp and reactor vessel, for licensing authorities | To be filled by RTU, CERN, Fraunhofer, INCT | To be filled by RTU, CERN, Fraunhofer, INCT | WP2.3 T2.3.2. |
| 3 | Manufacturing of cooler* | RTU, RKB, INCT, Remontowa | 01.07.2019. | Cooler fabrication using final technical documentation | To be filled by RTU, RKB, INCT, Remontowa | To be filled by RTU, RKB, INCT, Remontowa | WP2.3 T2.3.3. (T2.7.) D5 MS1 |
| 4 | Manufacturing of air curtain* | RTU, ebeam, CERN, Fraunhofer, INCT | 01.08.2019. or to be filled by RTU, ebeam, CERN, Fraunhofer, INCT | Air curtain fabrication using final technical documentation | To be filled by RTU, ebeam, CERN, Fraunhofer, INCT | To be filled by RTU, ebeam, CERN, Fraunhofer, INCT | WP2.3 T2.3.4. (T2.7.) D5 |
| 5 | On site installation of cooler, reaction vessel, Electron Beam Lamp, air curtain* | RTU, RKB, Fraunhofer, ebeam, INCT, Remontowa | 10.08.2019. | Cooler, reaction vessel, Electron Beam Lamp, air curtain installed in the engine exhaust system, using principal | To be filled by RTU, RKB, Fraunhofer, ebeam, INCT, Remontowa | To be filled by RTU, RKB, Fraunhofer, ebeam, INCT, Remontowa | WP2.3 T2.3.5. (T2.7.) D5 |
| 6 | Measuring devices are provided and installed on the prototype * | INCT; RTU | 10.09.2019. | Measuring devices are installed in the engine exhaust system following design drawings and principal schemes | To be filled by RTU and INCT | To be filled by RTU and INCT | WP2.3 T2.3.6. D6 |
| 7 | Prototype is made ready for the tests * | All | 10.10.2019. | Prototype assembly ready and prepared for tests |  |  | WP2.3 T2.3.7. (T2.9.) MS2 |
| 8 | Radiological Dosimetry measurements of the Electron Beam Lamp operation in the reactor vessel | CERN, RTU, Fraunhofer, | 30.10.2019. or to be filled by CERN, RTU, Fraunhofer, | Radiological Dosimetry measurement results of the functioning Electron beam lamp | To be filled by CERN, RTU, Fraunhofer, | To be filled by CERN, RTU, Fraunhofer,, | WP2.3 T2.3.8. |