## Slide 1: SMB –DI Open Days 2019

## Slide 2
Agenda
1. Introduction
2. Work packages
3. Feedback

## Slide 3
2019 Open Days
When: 14-15 September 2019.
Theme: The future of particle physics research.
Slogan: “Explore the future with us”
Who is it for? CERN neighbors, but visitors will come from further afield
Budget: 2MCHF
Will follow model of 2013 Open Days:
  Underground visits and campus visits
  Events: talks, debates, film screenings
  Activities: hands-on physics experiments and demonstrations
  Exhibitions of art & science; showcasing contributions of MS and partner laboratories to CERN research
Internal Communication:
  E-group: SMB-OpenDays2019@cern.ch
  SharePoint: https://espace.cern.ch/SMB-OpenDays2019

## Slide 4
Work packages
Branding and Design
(Fabienne Landua)
Digital Communications
(Kate Khale)
Press and Media
(Arnaud Marsollier)
Photography and Video
(Paola Catapano)
Evaluation
(Emma Sanders)
Budget planning and control
(Laure Esteveny)
Host State Relations
(Friedemann Eder)
CORE TEAM
Volunteers
(Loraine Massarotti)
Visitors access and flow
(François Briard)
CERN Shop
(Yesika Enriquez)
Documentation, Minutes & Reports
(Marika Flygar)
Food and Refreshments
(Fatima Najeh)
Events programming
(Claudia Marcelloni)
Thematic Zones
(TBC)
Surface visit points
(Dominique Bertola)
Underground visit points
(TBD)
Safety
(Yann Lechevin)
IT support
(Wayne Salter)
Logistics and Supplies
(Didier Constant)
Site Maintenance
(Didier Constant)
Ana Godinho (Lead)
Marika Flygar
François Briard
Dominique Bertola
Yann Lechevin
Didier Constant

## Slide 5
SMB Work packages
Name | Milestone / Deliverable | Leader
Logistics and Supplies | Supply and delivery of necessary material and equipment to all visit points | Didier Constant (SMB-DI)
Site and maintenance | Electricity, Green spaces, Toilets, Cleaning services, Small building works, | Didier Constant (SMB-DI)
IT Support | IT infrastructure and support for events and AV coverage: hardware, network connections. Open Days App | Wayne Salter (IT-CF)

## Slide 6: Some key points for SMB
A controlled communication,
A search for internal and external synergies
A good anticipation,
Respect for milestones,
Provide a substitute for each WP,
Pay attention to the holiday period,
Think about the personal on call and FSU and volunteers needs.

## Slide 7
Point Information Sheet

## Slide 8
Stop / Start / Continue
What from previous Open Days should we stop doing?
What should we start doing?
What should we continue doing?