## Slide 1: ELENA Project
TRANFER LINES INSTALLATION LS2
ADUC 30 Oct 2018

## Slide 2: ELENA in AD hall
AD machine
ELENA
ASACUSA
ALPHA
ATRAP
AEGIS
BASE
GBAR
AEGIS 2

## Slide 3: LS2 : 12 Nov 2018 – March 2021
Existing magnetic TLs to be replaced by electrostatic TLs

## Slide 4: Transfer lines works
Lock-out, cables disconnection, flexible cooling pipes disconnection
Remove all magnetic transfer lines plus corresponding supports
Remove all corresponding cables
Re-organize part of the shielding walls
Re-route cable trays and water pipes
Install electrostatic transfer lines, instrumentation, vacuum and services
Commission new transfer lines
TIME

## Slide 5: Central region (DE0 – DE5)
Vacuum disconnection central part (DE0 / DE5)
Remove cables and cable trays
TIME
Lock-out / disconnect cables/pipes from equipment
12 Nov 2018 – 16 Nov 2018
Remove equipment central part
(Vac, BTV, STP, GEM, Magnets, cooling pipies, supports)
16 Nov 2018 – 19 Nov 2018
20 Nov 2018 – 23 Nov 2018
26 Nov 2018 – 21 Dec 2018
DE0 / DE5
2 shield blocks,
5 magnets,
1 GEM, 1 BTV, 1 STP
TE/MSC
BE/BI
EN/STI
VSC
MSC
VSC
BI, STI
CV, HE
EL
DE5.BHZ10, DE5QN20, DE5BHZ25,
DE5DVT28 DE0.QN40 DE0XGEM42
DE5BTV15 DE5STP27

## Slide 6: In parallel: Stoch cooling + RFQD dismantling
RFQD faraday cage + RF amplifier removal
TIME
RFQD racks, power supplies removal
ATRAP workshop+ stuff removal, move EL cabinets
12 Nov 2018 – 21 Nov 2018
22 Nov 2018 – 28 Nov 2018
Stochastic cooling equipment measure, drain, remove
12 Nov 2018 – 23 Nov 2018
13 Nov 2018 – 26 Nov 2018
EPC, EA
RF, HE
RF, HE
ATRAP, HE, EL
RF, HE, CV
RFQD
RFQD
Stoch cooling
ATRAP
EL cabinets
Transfo

## Slide 7: DE0 line inside shielding
Open shielding, remove DE0 line
(Vac, 1 GEM, 1 STP, 4 Magnets)
TIME
17 Dec 2018 – 08 Jan 2019
Remove CV pipe, Shielding wall modifs
07 Jan 2019 – 04 Feb 2019
CV, HE
BI
CV HE MSC
DE0
Shield wall
Magnets to be removed: DE0.BHZ18, DE0QN20, DE0QN30, DE0DHV35
GEM to be removed: DE0MWPC15
Stopper: DE0STP16

## Slide 8: DE1 –DE5 removal
Remove BASE TL (DE5): 5 Magnets, 2 BTV
Remove ASACUSA TL (DE1):
10 magnets, 3 GEM, 1 buncher, 1STP, 1 RFQD
Remove ATRAP/ALPHA TL (DE2, DE3, DE4)
20 magnets, 7 GEM, 3 stopper
04 Feb 2019 – 18 Feb 2019
19 Feb 2019 – 07 Mar 2019
08 Mar 2019 – 03 Apr 2019
BI, CV, HE, MSC, VSC
BI, STI, RF
CV, HE, MSC, VSC
STI, BI, VSC
CV, HE, MSC
DE5QN30, DE5DVT33, DE5BHZ35, DE5DHV38, DE5QN40
DE5BTV32, DE5BTV37
DE0 BHZ10, DE1QN20, DE1DHV25, DE1DHV28, DE1QN30,
DE1QN40, DE1QN50, DE1DN60, DE1DHV65, DE1DHV67
DE1XGEM27, DE1XGEM45. DE1XGEM47
DE1STP26
DE1BUNCHER; RFQD
DE0DHV45, DE0QN50, DE0QN60, DE0QN70, DE0QN80, DE0DHV85,
DE0DHZ87, DE0QN90, DE0QN100, DE2BHZ10
DE0STP105
DE0XGEM65, DE0XGEM82, DE0XGEM107
Vertical lines:
DE3BVT10, DE3QN20, DE3BVT25, DE4DHV10, DE4QN20, DE4BVT25
DE3STP15, DE4STP15
DE3XGEM17, DE4XGEM17
Dans Zone ALPHA:
DE2DHV15, DE2QN20, DE2QN30, DE2DHV35
DE2XGEM12, DE2XGEM40
TIME

## Slide 9: Infrastructure modifs
Removal of DE0 access control gate | BE/ICS, EN/HE | 1 day | Mon 12/11/18 | Mon 12/11/18
Long concrete beam cut | SMB-CE | 3 days | Mon 17/12/18 | Wed 19/12/18
Remove big demi water piping | EN-CV | 1 wk | Mon 07/01/19 | Fri 11/01/19
AD shielding wall dismantle | EN-HE | 2 wks | Mon 14/01/19 | Fri 25/01/19
New AD shielding wall re-install | EN-HE | 1 wk | Mon 28/01/19 | Fri 01/02/19
New demi water piping install | EN-CV | 1 wk | Mon 04/02/19 | Fri 08/02/19
Install steel barriers ATRAP zone | EN-EA | 2 days | Wed 15/05/19 | Thu 16/05/19
Remove steel cross bracing on BASE shielding | EN-EA | 2 days | Fri 10/01/20 | Mon 13/01/20
Modify BASE exp area shielding | EN-HE | 1 wk | Tue 14/01/20 | Mon 20/01/20
Disconnect / reconnect BASE access door | BE-ICS | 2 days | Tue 21/01/20 | Wed 22/01/20

## Slide 10: Electrostatic lines to be installed
LNE00
LNE01
LNE02
LNE03
LNE04
LNE05
LNE06
LNE07
LNE50
LNE51

## Slide 11: Installation of the new lines
Install Equipment (Electrostatic + vacuum + SEM)
TIME
Vacuum connections + pump + leak check + bake out
Cabling campaign (signal, AC, optical fibres)
Survey Marking
Floor drilling
Install mechanical supports
Survey /Align Equipment
05 April 2019– 8 May 2019
23 May 2019– 05 June 2019
06 June 2019– 26 June 2019
27 June 2019– 31 July 2019
01 August 2019– 29 Aug 2019
30 Aug 2019– 15 Nov 2019
06 Jan 2020 – 03 Apr 2020
HW tests / Global commissionning
06 April 2020 – AD restart 2021
SMM
MME
MME
ABT, VSC
HE
SMM
VSC
EL
ABT EPC VSC + OP
Lissage, SEM measurement
18 Nov 2019– 06 Dec 2019
SMM

## Slide 12: In the context of AD consolidation…

## Slide 13: Readiness status
All the teams are aware and accepted the work to be perfomed through PLAN and in regular ADTC + ELENA IIC meetings
Production of all components either complete (electrostatic elements, pumps) or on time for installation (vac pipes, mechanical supports)
Remaining worries: SEM electronics availability, vac tests of SEM, possible need for magnetic shielding near Aegis/ATRAP
Schedule available at https://espace.cern.ch/en-ea-planning/SitePages/Plannings.aspx?RootFolder=%2Fen%2Dea%2Dplanning%2FShared%20Documents%2FLS2%20Plannings&FolderCTID=0x0120005F33F2ECA6929F4FB4BE25060D74BD71&View=%7B7615CB2E%2D344A%2D4AE5%2DA726%2D8B89A68DFB8A%7D