## Slide 1: ELENA Project
TRANFER LINES SEM’s schedule

## Slide 2: Electrostatic lines to be installed
LNE00
LNE01
LNE02
LNE03
LNE04
LNE05
LNE06
LNE07
LNE50
LNE51

## Slide 3: Vacuum sectors
Sector 0-1
Sector 7
Sector 6-5
Sector 5
Sector 1-2
Sector 2
Sector 1-3
Sector 3-4
ATRAP 1
ATRAP 2
Sect valve
SEM

## Slide 4: Assumptions for delivery
9 complete systems delivered by M. Hori for end Nov 2018 (including coated rods), then 3 new units every 6 weeks delivered at CERN
BE-BI takes 1 week to fully assemble and test 1 setup: Continuous dedication of BE-BI for SEM’s assembly from Nov 2018 till end 2019
3 weeks for vacuum acceptance test + transport + installation of 3 complete setups: part dedication of TE-VSC for tests !

## Slide 5: SEM HW delivery vs installation
Chart: SEM's: Available vs Needed
Commissioning start
Elelctrostatic elements installation
Cabling by EN-EL
Pump down – Bake-out
20/01/2020
Cables connections
Survey - alignement
14/10/2019
09/12/2019

## Slide 6: Number of SEM per vac sector
Sector 3-4: 6 SEM (6/24) Leak check: 05/09/2019
ATRAP 2: 1 SEM (7/24) Leak check: 05/09/2019
Sector 1-3: 6 SEM (13/27) Leak check: 17/09/2019
ATRAP 1: 1 SEM (14/27) Leak check: 17/09/2019
Sector 1-2: 3 SEM (17/27) Leak check: 23/09/2019
Sector 2: 1 SEM (18/27) Leak check: 27/09/2019
Sector 0-1: 4 SEM (22/27) Leak check: 07/10/2019
Sector 7: 3 SEM (25/27) Leak check: 11/10/2019
Sector 6-5: 6 SEM (31/27) Leak check: 21/10/2019
Sector 5: 5 SEM (36/30) Leak check: 29/10/2019

## Slide 7: Conclusions
Last moment for SEM’s installation is vacuum check of concerned sector
Bake-out operations 05/09/2019 – 21/12/2019 (after that: cables installation till April 2020)
According to planned delivery schedule, 9 missing SEM’s won’t be available by end 2019
Impacted lines: LNE05-06 (ASACUSA): install 4 blank flanges on vac sector 6-5 to bake-out sector 0-1
Missing SEM’s installed when available, but bake-out possible only after cable pulling: impact on start of commissioning of LNE05-06 only.
All efforts should be done to speed –up delivery