Agenda (https://indico.cern.ch/event/772568/)

1.	Approval of minutes and follow-up of the previous meeting (K. Hanke)

2.	Communications (K. Hanke)

3.	Follow-up of open actions (K. Hanke)

3.1	ECRs by BE/BI

3.2	ECRs by BE/RF

3.3	ECRs by TE/MSC

4.	Status of power converters for injection equipment

4.1 Status of power converters for injection bumper magnets (J.-M. Cravero)

4.2 Manufacture and commissioning of the SMH42 power converter (T. Todorcevic)

5.	AOB

5.1 Update on RF activities (H. Damerau, C. Rossi)

4.2 EVM status report (S. Prodon)

6.	Tour de table

Present: T. Birtwistle, D. Bodart, J.-B. Bonnamy, J. Borburgh, J.-M. Cravero, H. Damerau, S. Deleval, J. Ferreira, A. Floriduz, V. Forte, A. Guerrero, K. Hanke, A. Huschauer, A. Lasheen, F. Pedrosa, S. Pittet, S. Prodon, C. Rossi, F. Tecker, T. Todorcevic

# Approval of minutes and follow-up of the previous meeting (K. Hanke)

The minutes of the previously held meeting were approved.

# Communications (K. Hanke)

K. Hanke reported about the different meetings and activities that have taken place since the last LIU-PS meeting.

One LIU Project Team meeting has taken place:

- 8th November 2018 (https://indico.cern.ch/event/768431/)

One LIU Beam Performance meeting has taken place:

- 1st November 2018 (https://indico.cern.ch/event/766645/)

Dedicated meetings between LIU and the equipment groups:

- With EN/EL on 8th November 2018 (https://indico.cern.ch/event/753673/)

  - The installation of a beam quality monitor (BQM) in the PS has been discussed. The device would be a new wall-current monitor and cables need to be pulled during LS2.

K. Hanke furthermore reported that a discussion on the cooling of the main magnets downstream the internal dumps has taken place. It has been agreed that during the first year of operation after LS2, the currently installed ventilation system will be monitored to understand how often the system is actually activated. In case of frequent use, a consolidation programme will be established and a new system shall be foreseen under the responsibility EN/STI.

An additional meeting related to potential cost savings with EN/STI has taken place. An immediate outcome concerns the design of the ralentisseur, which will remain unchanged with respect to the currently installed device. Only the plate intercepting the beam will be exchanged to cope with the increased beam intensity. J. Ferreira remarked that the vacuum seal for the current design has a non-standard size for which spare parts are difficult to obtain. He will follow this matter up offline with F.-X. Nuiry.

# Follow-up of open actions (K. Hanke)

The list of actions, concerning the missing ECRs, can be found in Annex 0.

## ECRs by BE/BI

- New vertical BGI monitor and magnet: the action has been closed.

## ECRs by BE/RF

- New feedback amplifiers for the 40 and 80 MHz cavities: the action remains open with deadline 31st January 2019.

## ECRs by TE/MSC

- Upgrade/installation of injection bumper magnets: the action remains open with deadline 31st October 2018.

# Status of power converters for injection equipment

## 4.1 Status of power converters for injection bumper magnets (J.-M. Cravero)

J.-M. Cravero presented the status of the power converters for the injection bumper magnets (Annex 1). Five identical converters are foreseen; however, the eddy current bumper in SS42 requires the installation of an additional pulse transformer in the tunnel. The challenging aspect of the converter design is the achievement of the specified tracking precision.

At the moment tests are being performed on a PSB converter that has been modified to comply with the needs for the PS injection systems. Special focus is being put on the design of the current control loops and first magnetic measurements on the bumper prototype have been performed using this converter.

The ongoing work on the current control loops is extremely important, as the required precision has not yet been achieved. It remains a challenge to achieve the specified performances, and is mainly seen as deviation from a perfect half-sine wave in the beginning of the pulse. All converters will however behave in an identical manner.

All the required hardware will at latest be ready for installation in the beginning of 2019 (excluding the DCCTs, which will be part of a common order with PSB equipment).

## 4.2 Manufacture and commissioning of the SMH42 power converter (T. Todorcevic)

T. Todorcevic presented the status of the power converter for the new injection septum (Annex 2). Similar to the injection bumper in SS42, powering SMH42 will require a pulse transformer in the tunnel and a stripline as connection to the magnet. The difference with respect to the converters for the injection bumpers is the necessity of a regulated flat top on the current wave form.

A prototype converter has been assembled and is currently being tested. In terms of voltage and current discharge behavior, the design has been validated and a full sine wave discharge through a pulse transformer has been demonstrated.

The integration of the equipment in the tunnel has been finalized and equipment procurement is ongoing. Tests with the actual septum magnet are foreseen for December, and will be followed by tests to evaluate the cross-talk between septum and bumper magnets early next year. Furthermore, the design of the active filter to deliver the specified flat top performances remains to be done.

# AOB

## 5.1 Update on RF activities (H. Damerau, C. Rossi)

C. Rossi reported that the re-profiling of 100 kCHF to next year has been finalized.

H. Damerau explained that the last beam measurements have been completed and that the 80 MHz filters for the multi-harmonic feedback have arrived in time to be successfully tested with protons on the multi-harmonic feedback of one cavity.

## 4.2 EVM status report (S. Prodon)

S. Prodon presented the EVM status report (Annex 2). The schedule variance is relatively stable at -3.4 months and the cost variance has increased, reflecting the cost overrun by EN/STI.

Approximately on third of schedule variance is due to injection systems and one third due to RF work packages. J. Borburgh explained that difficulties with the vacuum tank of SMH42 have been encountered, which will be solved by the main workshop.

J. Ferreira explained that he has not received any partial invoicing from EN/MME. He will check once again and come back to S. Prodon if necessary.

# Tour de table

S. Deleval explained that the dismantling of old CV-equipment has started.

D. Bodart reported that 14 November was the final date set for the quotes of the injection bumper magnets. He furthermore explained that passive dosimeters will be installed on the magnets downstream the internal dumps to assess the cooling requirements.

V. Forte reported about very good progress with the multi-turn measurements at injection and that post-processing was ongoing.

Minutes by A. Huschauer on 22nd November 2018