## Slide 1: SPS Schedule, Co-activities & Logistics
D. Mcfarlane EN-ACE
on behalf of all contributors

## Slide 2: Content
Organisation
LS2 Master and Baseline Schedules
LS2 Activities & ALARA works
LS2 LIU Main Activities
Critical Paths
Documentation Status
Summary

## Slide 3: LIU Project: SPS
LIU SPS Technical Coordination
Chair B. Goddard
Deputy E. Shaposhnikova
LIU Executive Committee
IEFC
LS2C
LMC
LIU SBDS coordination (EC)
LIU 200 MHz (FG)
LIU aC/Impedance (PC)
Ad Hoc meetings
LIU Commissioning Coordination
V. Kain, G. Rumolo, A. Huschauer
LIU SPS Commissioning WG
Chair K. Li
LIU RF integration (KL)
LIU SBDS integration (FV)
Ad-hoc meetings
Other projects in SPS
SPS Shutdown Coordination
Chair D.Mcfarlane
LIU Beam Dynamics Coordination
H. Bartosik, G. Rumolo
LIU SPS BD WG
Chairs E. Shaposhnikova, H. Bartosik
As needed

## Slide 4: Organisation
Activity Technical Coordinator
De-cabling/Cabling Georgi Minchev Georgiev
Upgrade of the RF 200 MHz in BA3 Eric Monesinos
aC coating & impedance reduction Wil Vollenberg
Beam dump Project Etienne Carlier
Exchange of the ZS in LSS2 Bruno Balhan
Facility Coordinators
David Mcfarlane Julie Coupard(Deputy)
EROS
Emmanuel Paulat
John Etheridge
Integration
Frederic Galleazzi
Scharif Mehanneche
Daniel Del Alamo
Configuration / Layout DB
Sonia Bartolome Machine
Blanca Vazquez Surface
WP1 Fire Compartments A. Martinez Selles
WP2 Fire Detection Michael Dole
WP3 Dry Riser Willy Van Den Broucke
WP4 Fire Sprinkler Anna Suwalska
BA1 & BA5
Jonathan Meignan
Beamline activities
Antonio Grande Mallavia
Jean-Baptiste Mayolini

## Slide 5: LS2 Master Schedule 1.4
3
Closure of the SPS
Start of Access to the SPS
19.5 months
14th January 2019
18th September 2020
Period with possible access restrictions
More details of this will be presented in the talk given by James Ridewood in Session 3 tomorrow morning

## Slide 6: LS2 machine activities SPS
Extraction protection devices:
Replacement of TPSC4 (LSS4)
Replacement of TPSG6 (LSS6)
200 MHz RF power upgrade (LSS3, BA3, BAF3)
200 MHz low level RF upgrade
Reconfiguration of LSS1 (LSS1, BA1)
New beam loss monitors
New upgraded scraper
Replace one injection kicker MKP
Reconfiguration of the enlarged quadrupoles (11610, 11710, 11810)
New rotational Wire Scanners BWSRE
(LSS4, LSS5)
Change all the electrostatic septum ZS (LSS2)
LHC injection lines TI2 and TI8 (see LHC coordination)
New collimators TCDIs
New beam loss monitors
New vacuum valves
aC coating (QF SSS, MBB 5+ 6-, LSS drifts all)
New flanges for the impedance reduction
LIU Project
Replacement MOPOS electronics (Sextants 1,2,3,4,5,6)
Add a vacuum valve (sector 210)
Reconfiguration of LSS5 (ECA5, ECX5, LSS5)
New Beam Dump
New beam loss monitors
Replace beam gas ionisation profile monitor (BGI)
Replace the synchrotron light monitor (BSRT)
New kicker magnet with vertical deflection for dumping MKDV (and generator)
Reconfiguration of the enlarged quadrupoles (51610, 51810)

## Slide 7: LS2 machine activities SPS
Fire Safety
Fire compartments
Fires safety systems
Manual fire fithing systems
Automatic fixed fire fihting systems
Fire Safety Project
New PPS Project
Consolidations
Maintenance
Upgrade
New access systems
New personnal access devices PAD
New material access Devices MAD
New emergency exite doors
New beam loss monitors
De-cabling Project
New UA9 cristal and goniometer pair
New emergency lighting systems
New safety cable tray
Consolidation of the B-train
WIC and BIS deployment
Refurbishment of the lift (BA3, BA6)
Electrical sub-station consolidation (BA1,2,4,6)
Extraction protection devices:
Replacement of TPSC4 (LSS4)
Replacement of TPSG6 (LSS6)
200 MHz RF power upgrade (LSS3, BA3, BAF3)
200 MHz low level RF upgrade
Consolidation of BB3 cooling plant
New modern static var compensator (BEQ1)
Reconfiguration of LSS1 (LSS1, BA1)
New beam loss monitors
New upgraded scraper
Replace one injection kicker MKP
Reconfiguration of the enlarged quadrupoles (11610, 11710, 11810)
New rotational Wire Scanners BWSRE
(LSS4, LSS5)
Change all the electrostatic septum ZS (LSS2)
LHC injection lines TI2 and TI8 (see LHC coordination)
New collimators TCDIs
New beam loss monitors
New vacuum valves
aC coating (QF SSS, MBB 5+ 6-, LSS drifts all)
New flanges for the impedance reduction
LIU Project
Replacement MOPOS electronics (Sextants 1,2,3,4,5,6)
Add a vacuum valve (sector 210)
Reconfiguration of LSS5 (ECA5, ECX5, LSS5)
New Beam Dump
New beam loss monitors
Replace beam gas ionisation profile monitor (BGI)
Replace the synchrotron light monitor (BSRT)
New kicker magnet with vertical deflection for dumping MKDV (and generator)
Reconfiguration of the enlarged quadrupoles (51610, 51810)
De-cabling Project

## Slide 8: ALARA level III
Facility | Work | Group in charge | Activity/Project Leader | Committee date
SPS | SPS fire safety upgrade (reduced scope) [excl. cabling] | BE-ICS | Ronny Billen | November 2018 (1st Part approved) Mid 2019 (2nd part)
SPS | Cabling BA1 & BA2 [incl. cabling SPS fire, TIDVG LSS1 removal] | EN-EL | Guillaume Gros | September 2019
SPS | Safety lighting infrastructure installation | EN-EL | Gerardo Velazquez Gutierrez | November 2018 (Approved)
SPS | TIDVG removal in LSS1 [excl de-cabling] | TE-ABT | Etienne Carlier | February 2019 (Approved)
SPS | Installation of new ZS in the SPS LSS2 extraction channel | TE-ABT | Bruno Balhan | March 2019
LIU related

## Slide 9: SPS Linear Schedule Baseline https://edms.cern.ch/document/1892837/2.0

## Slide 10: LS2 Main LIU Activities

## Slide 11: LIU Beam dump activities during LS2 (Point 1 & Point 5)
Move the SPS Beam Dumping System from SPS1 to SPS5 (ECX5)
Reconfiguration of the LSS5
  Dismantling more than 100 meters of beam line
  De-cabling / cabling campaign
  Civil engineering in ECX5
  Re-installation following the new layout including the new dump
Reconfiguration of the LSS1
  Removal of the dumps and their instrumentation
  Transfer of the kickers to LSS5
  Re-installation of the simplified LSS1, including e-cloud
New Beam dump
Scope of the project:
Old dumps
Kickers
More details of this project will be presented in the talk given by Etienne Carlier in Session 2 this afternoon
ECR 1976294 / 1963473 / 1574176

## Slide 12: LIU Beam dump activities during LS2 (Point 1 & Point 5)
Preparation
Civil engineering
Re-installation
Re-configuration
Old dump removal

## Slide 13: LS2 Transport restriction due to LIU Beam Dump Works BA5
9 months of Civil Engineering works in ECX5
Location of “Goods” lift
The scheduling of works that require transport of equipment around the tunnel has taken this constraint into account.
Transport crossing other works will have to be carefully addressed.

## Slide 14: LIU 200 Mhz RF Upgrade in BA3
…
Before LS2
After LS2
ECR 1900971
The upgrade of the 200 MHz RF system, which is the frequency at which main accelerating system of the SPS operates. This involves the addition of two new travelling-wave cavities and the construction of two new RF systems that will feed them, as well as the installation of the surrounding equipment to ensure the correct functioning of said systems.
More details of this project will be presented in the talk given by Frank Gerigk in Session 2 this afternoon

## Slide 15: De-cabling & Cabling Campaign SPS POINT 3
 | Campaign Code | QTY [KM] | QTY Cables | Duration* [Weeks]
 | SP3CUC0-CD01 | 252 | 2827 | 17
 | SP3LIU0-CD01 | 69 | 1344 | 5
TOTAL | SPS point 3 | 321 | 4171 | 22
Original estimation was 12 weeks
 | Campaign Code | QTY [KM] | Duration* [Weeks]
 | SP3FS0-CC01 | 10.2 | 5
 | SP3PPS0-CC03 | 25 | 8
 | SP3SMT0-CL201 | 0.8 | 1
 | SP3SMT0-CL2M1 SP3UTT0-CL2M1 | NA | 0.5
 | SP3LIU0-CC06 | 53 | 22
TOTAL |  | 89 | 36.5
Original estimation was 12 weeks
De-cabling
Cabling

## Slide 16: Planning (LIU 200 Mhz RF Upgrade in BA3)
De-cabling, Cabling & Auxilary works
Cavities removal
Install cavities
RF Commissioning
During May, June & July work teams will be split into Shifts to avoid co-activity in the same area

## Slide 17: Installation of new ZS in the SPS LSS2 extraction channel
In order to reduce high spark rate and vacuum activity with LHC beams in the LSS2 ZS electrostatics septa, a new layout has been proposed.
The principal modifications to improve the vacuum in the ZS concern the installation of 5 new ZSs equipped with vacuum pumps directly onto the vacuum vessels. Each vacuum pumps will be equipped with a passive getters pumping system (Saes® CapaciTorr® D2000). Also the beam impedance of the new ZSs is reduced by introducing RF screens and grounding the anode support.
ECR 1949753

## Slide 18: De-cable and re-cable ZS girder in LSS2 As presented in the LS2C #27 – 16th November 2018
Particular cables have been identified and needing to be replaced in during LS2:
2.6 km cables for ABT from patch.
3.8 km for BI and VSC from TA.
An addition 8 weeks of cabling has been added to the planning to accommodate this additional works.
The LSS2 general re-cabling campaign to replace all (irradiated) cables has been postponed to LS3.
The first cables start (Long HV cable in Sept ’18, short cable in BA2 in November) to die.

## Slide 19: Planning (Installation of new ZS in the SPS LSS2)
Removal
Cabling Campaigns
Installation
ZS Cabling
Testing & Commissioning

## Slide 20: aC Coating & Flange Impedance Reduction: LS2
BA1
BA2
BA3
BA4
BA5
BA6
Meyrin, P1 LHC
(magnet lift)
Prevessin site
(magnet lift)
RF
TT40 ext
TT20 ext
Future
dump
Injection
& Dump
TT60 ext
ECX5
BHA5
(magnet lift)
9 QF (EYETS 2016)
3 QF quads (LS1 & YETS)
(LS2)
(LS2)
(LS2)
(LS2)
(LS2)
(LS2)
LS2:
87 QF to be coated in SPS: 2 benches 1
87 SSS QF to be coated in 867: 2 benches 2
~ 30 drifts to be coated in 181 (already started)
Flange impedance reduction at 87 SSS QF (2-4 impedance improvements per SSS QF position)
Work sequence BA5 to BA2 anticlockwise, then BA5 to BA2 clockwise.
1 SPS
2 867
ECR 1968345

## Slide 21: Planning (aC Coating & Flange Impedance Reduction)
Remove Magnets
Coating in-situ
Re-install Magnets

## Slide 22: Upgrade of the TCDI Collimators in the SPS to LHC Transfer Lines (TI2/TI8)
This LHC injection protection collimator system in the SPS to LHC transfer lines (TI2/TI8) needs upgrading in order to safely bring the LHC into the high luminosity era. The existing TCDI collimators will be removed and replaced with longer collimators, and a limited number of TCDIM masks will also be replaced.
As these collimators are physically located in the LHC ends of TI2 &TI8, the coordination of these works is being followed by the LHC coordination team
ECR 1577759

## Slide 23: Planning (TCDI Collimators)

## Slide 24: SPS Beam Line Activities Vacuum sectors
Over 90% of the vacuum sectors will be open/closed (68 to 71 vacuum sectors)
3 long straight section will be mostly reconfigured for the LIU
Activities related to LIU will be held in all points of the SPS
  More than 75% of vacuum sectors will be opened due to LIU activities
*Change in total number due to vacuum sector reconfiguration
Total number may change depending of the magnet campaign
In each sector: (sectors opened / total)
In purple, sectors that will be opened to perform LIU activities
Courtesy of Antonio Grande

## Slide 25: SPS Beam Line Activities VSC resources levelling
Chart: Sectors Opened
Current situation | 0 | 6 | 17 | 24 | 26 | 26
19 sectors opened in line with planning
1 extra sector opened for TT10 access
1 extra sector opened for magnet campaign
2 sectors opened before for granting TT20 – TT60 access
2 sectors opened before for Maintenance/OP request
1 sector opened before for COLDEX
In time | Extra* | In advance | Delayed
19/19 | 2 | 5 | 0
Sectors opened during LS2 (week 6):
26 of 68
Week 6
Courtesy of Antonio Grande

## Slide 26: Critical Paths
Any delay in one work area will have a direct affect on the critical path in the other areas

## Slide 27: SPS Documentation Status (Engineering Change Request status)
54 ECRs/SRRs for LS2
35 related to the LIU project
10 ECRs “In Work”:
SPS-B-EC-0006: “Dismantling of obsolete SPS equipment for K-modulation during LS2” (BE-BI)
SPS-BLM-EC-0005: “Installation of new BLM system in TT10” (BE-BI)
SPS-SFD-EC-0002 SPS fire safety - Fire partitions during LS2
SPS-U-EC-0001: “SPS Fire Protection: Fire dampers and ventilation related works” (EN-CV)
  Related to the LIU project:
  SPS-BSRTA-EC-0001: “Installation of a BSRT tank in LSS5 of the SPS during LS2” (BE-BI)
  SPS-LJ-EC-0017: “Layout Optimisation for Machine Elements Upstream of QFA.21610 for Mitigation of Beam Impedance” (BE-RF)
  SPS-LO-EC-0002: “Proposal for SPS octupole relocation to restore the lattice symmetry” (BE-ABP)
  SPS-TMASC-EC-0001: “New masks for SPS during LS2” (EN-STI)
  SPS-LJ-EC-0014: “LSS1 vacuum layout after LS2” (TE-VSC)
  SPS-LJ-EC-0015: “LSS5 Vacuum Layout after LS2” (TE-VSC)

## Slide 28: SPS Documentation Status (Integration status)
Total number of registered Integration Studies:
82
Number of LIU related Integration Studies:
29
Number of needed Integration Studies:
0
The completion of all the ECR and Integration study processes (Life Cycle) depend on the input and quality of information provided by the design offices in each Group.
29

## Slide 29: Documentation Status (Work Package Analysis status)
Dedicated Procedures
Mise hors tension partielle du SPS lors des YETS, EYETS et LS https://edms.cern.ch/document/2058234/0.1
Under Approval
Demande de « SEPARATION DU RESEAU » par le Facility coordinator https://edms.cern.ch/document/2049809/1 Released
De-cabling – SPS5 lock-out procedure for De-Cabling during LS2 https://edms.cern.ch/document/1983418/1.0 Released
De-cabling – SPS3 lock-out procedure for De-Cabling during LS2 https://edms.cern.ch/document/1991126/1.0 Released
De-cabling – Identification, labelling and disconnection procedure for obsolete cables SPS1 and SPS3 during LS2 https://edms.cern.ch/document/2052872/1.0 Released
17 WPAs
New for the SPS
LIU related
(5 of which are for LIU works)

## Slide 30: Summary
19.5 months of access into the SPS during LS2.
  Open date: 14th January 2019.
  Closure date: 18th September 2020.
The LS2 is now in progress and we are currently on schedule.
Additional projects have been taken into account when organizing the LIU planning.
  Fire Safety project
  New PPS
  De-cabling / Cabling campaigns
Co-activities cannot be avoided and are identified (multiple project activities).
  These are being addressed (dedicated meeting, on-site visits, VICs etc.).
  Mitigations are proposed and are being validated (ex. Shifts in BA3).
Transport and Logistics to be carefully defined and are being followed-up on site.
  We have already faced our first difficulties, but support from LS2 space management and very good reactivity of RP and EN-HE to unblock situation.
We must keep a close eye on the critical path.

## Slide 31: Thank you Q’s

## Slide 32: Back up slides

## Slide 33: RF upgrade in SPS 3 during LS2 (2019)
33
LSS3
TA3
PA3
SURFACE &
SHAFT/TA35
RF upgrade works Surface/BA3/BAE3  Jan’19-Feb’20
De-cabling campaign surface  Jan-March & June’19
De-cabling campaign shaft/TA  April & June’19
Install RF coaxial lines shaft  Jan-Feb’19
Install new ventilation dampers shaft  Feb’19
Remove redundant CV pipework in shaft  Feb’19
Install RF coaxial lines TA  June-July’19
Install Fibre-optic ducts Shaft/TA  July’19
Cabling campaign shaft/TA July-Nov’19
FS_WP2 & 4 Shaft/TA  Nov-Jan’20
LSS3
Disconnection/removal of the Cavities & beam line Jan-Feb’19
Remove redundant CV pipework in LSS3  March’19
Install RF coaxial  April-May’19
CV works for new RF Cavities  April-July’19
De-cabling campaign  May-June’19
Cabling Campaign  Aug-Nov’19
FS-WP2 LSS3- then LSS3+ Nov-Dec’19
Cleaning of LSS3  Nov’19
Install new cavities & beamline Dec’19-May’20
During May, June & July work teams will be split into Shifts to avoid co-activity in the same area

## Slide 34: RF upgrade in SPS 3 during LS2 (2020)
SURFACE &
SHAFT/TA35
LSS3
The location of Sprinklers in the LSS3 have not yet been identified by integration!
RF upgrade works Surface/BA3/BAE3  Jan’19-Feb’20
FS_WP2 & 4 Shaft/TA  Nov-Feb’20
EL Maintenance and AUG test Beginning of Feb’20
Testing of FS_WP2 & 4 Feb’20 (Outside working hours)
Dismantling old fire detection system March’20
New PPS access system  March -May’20
Monte-Charge refurbishment June-Aug’20
Install new cavities & beamline Dec’19-May’20
Testing of FS_WP2 & 4 Feb’20 (Outside working hours)
FS_WP3 Dry risers  March-April’20
IST RF Conditioning  June-Sept’20

## Slide 35: De-cabling project
As presented in the LS2C #23 – 27th July 2018

## Slide 36: LIU Beam dump activities during LS2 (Point 1 & Point 5)
Move the SPS Beam Dumping System from SPS1 to SPS5 (ECX5)
TIDH &
TIDVG
End of life
New Beam dump
Scope of the project
ECR XXXXXXX

## Slide 37: SPS 1: Main works during 2019
LSS1
  Removal of the dumps
  Removal of the beam line
  Cabling campaigns
BA1/Shaft/TA
  ABT racks reconfiguration
  PPS upgrade
All underground areas
  Fire safety WP3
Arc 1+/ Arc 1-
  aC coating

## Slide 38: SPS 1: Main works during 2020
LSS1
  Re-installation of the beam line
  Fire safety WP4
  EN-EL cabling (High radiation areas)
BA1
  Fire safety WP3
Shaft/ TA/ LSS1
  Fire safety WP2

## Slide 39: SPS 5: Main works during 2019
All underground areas
  Fire safety WP2 + WP3 (ECX5 in 2020)
  EN-EL cabling/de-cabling
  Kickers transmission line
Surface (BB5)
  Mock up of new beam dump
LSS5/ECX5
  Removal of the beam line
  Civil engineering for SBDS
No access in ECX5/ECA5 from 01/04/19 until 20/12/19!

## Slide 40: SPS 5: Main works during 2020
ECA5
  Works in Kickers platform (El + ABT + CV)
Surface (BA5/BB5)
  Fire safety WP3 (+ECX5)
  PPS upgrade
LSS5/ECX5
  Re-installation of the beam line
  SBDS cabling campaign 04
  Dump installation
  Cooling skid
Courtesy S.Mehanneche

## Slide 41: On-site storage strategy – “Bases de chantier”
1) Storage request via Sharepoint
2) Analysis + approval process
3) Space attribution on-site (see EDMS 1989344)
As presented in the LS2C #22 – 22nd June 2018

## Slide 42: Fire Safety Project (BE-ICS / EN-CV / SMB-SE)
The implementation consists of a combination of four WPs
  WP1: Comprehensive active and passive fire compartment scheme with ventilation isolation
  WP2: Automatic fire detection and protection system
  WP3: Significantly enhanced manual fire fighting means with dry risers and Compressed Air Foam System trailers
  WP4: Modern water based automatic fire sprinkler protection system in access shafts, access galleries and long straight sections
The safety outcome depends on the integration of the four work packages acting as a whole.
The full period of SPS underground access during LS2 will be needed and used for the required works affecting all points of the SPS.
As presented in the LS2C #22 – 22nd June 2018

## Slide 43: New access system (BE-ICS)
2018
LS2
Renovation to cope with:
  Technical Obsolescence
  Commitments to Nuclear Regulatory Body
  Increase safety of the personnel
Complete refurbishing of the SPS Access System
Pilot access point installation in BB5 completed
LS2 Installation of 15 access zones and CCC tools

## Slide 44: Surface activities (BA1)
2019
2020
2021
BA1
Legend:
SPS Fire Safety WP2 Fire detection Systems
SPS Fire Safety WP4 Sprinklers
SPS Fire Safety WP1 Fire Doors
SPS Fire Safety WP3 Dry Riser
SPS New Personnel Protection System
MACAO Power Converter for the SPS Ring and Transfer Lines Dipole
Consolidation Project
Distributed Optical Fibre Radiation Temperature Sensing in the SPS ring and TT20
Power converter modifications in building BA1/BA5 required by LIU-SPS
BA1 reconfiguration after relocation of SPS Beam Dumping System to LSS5
Consolidation of the SPS Tune Kickers during LS2
BLM Installation
Toilet refurbishment
Cabling Campaign

## Slide 45: Surface activities (BA2)
Legend:
SPS Fire Safety WP2 & WP4
SPS Fire Safety WP1
SPS Fire Safety WP3 Dry Riser
SPS New Personnel Protection System
MACAO Power Converter for the SPS Ring and Transfer Lines Dipole
Consolidation Project
Distributed Optical Fibre Radiation Temperature Sensing in the SPS ring and TT20
Toilet refurbishment
Cabling Campaign
2019
2020
2021
BA2

## Slide 46: Surface activities (BA3)
2019
2020
2021
BA3
Legend:
SPS Fire Safety WP2 & WP4
SPS Fire Safety WP1
SPS Fire Safety WP3 Dry Riser
SPS New Personnel Protection System
MACAO Power Converter for the SPS Ring and Transfer Lines Dipole
Consolidation Project
Distributed Optical Fibre Radiation Temperature Sensing in the SPS ring and TT20
De-cabling / Cabling Campaign

## Slide 47: Surface activities (BA4)
2019
2020
2021
BA4
Legend:
SPS Fire Safety WP2 & WP4
SPS Fire Safety WP1
SPS Fire Safety WP3 Dry Riser
SPS New Personnel Protection System
MACAO Power Converter for the SPS Ring and Transfer Lines Dipole
Consolidation Project
Distributed Optical Fibre Radiation Temperature Sensing in the SPS ring and TT20
Legend:
SPS Fire Safety WP2 & WP4
SPS Fire Safety WP1
SPS Fire Safety WP3 Dry Riser
SPS New Personnel Protection System
MACAO Power Converter for the SPS Ring and Transfer Lines Dipole
Consolidation Project
Distributed Optical Fibre Radiation Temperature Sensing in the SPS ring and TT20
Cabling Campaign

## Slide 48: Surface activities (BA5)
2019
2020
2021
BA5
Legend:
SPS Fire Safety WP2 & WP4
SPS Fire Safety WP1
SPS Fire Safety WP3 Dry Riser
SPS New Personnel Protection System
MACAO Power Converter for the SPS Ring and Transfer Lines Dipole
Distributed Optical Fibre Radiation Temperature Sensing in the SPS ring and TT20
Power converter modifications in building BA1/BA5 required by LIU-SPS
De-Cabling / Cabling Campaign

## Slide 49: Surface activities (BA6)
2019
2020
2021
BA6
Legend:
SPS Fire Safety WP2 & WP4
SPS Fire Safety WP1
SPS Fire Safety WP3 Dry Riser
SPS New Personnel Protection System
MACAO Power Converter for the SPS Ring and Transfer Lines Dipole
Distributed Optical Fibre Radiation Temperature Sensing in the SPS ring and TT20
Consolidation Project
Cabling Campaign