## Slide 1: Implementation of Earned Value Management (EVM) in HLLHC Project
R. Martins
12/12/2018

## Slide 2: Goal of HL-LHC as fixed in 2010
The main objective of HiLumi LHC Design Study is to determine a hardware configuration and a set of beam parameters that will allow the LHC to reach the following targets:
A peak luminosity of Lpeak = 5×1034 cm-2s-1 with levelling, allowing: An integrated luminosity of 250 fb-1 per year, enabling the goal of Lint = 3000 fb-1 twelve years after the upgrade. This luminosity is more than ten times the luminosity reach of the first 10 years of the LHC lifetime.
From FP7 HiLumi LHC Design Study application
Ultimate performance established 2015-2016: with same hardware and same beam parameters: use of engineering margins:
Lpeak ult  7.5 1034 cm-2s-1 and Ultimate Integrated Lint ult  4000 fb-1
LHC should not be the limit, would Physics require more…
Project approved by CERN Council in June 2016

## Slide 3
Technology landmarks

## Slide 4
Core Activities of Accelerator and Technology sector

## Slide 5: Accelerator and Technology Sector Directorate Office (ATS-DO)
Director for Accelerators & Technology
ATS DO Unit
BE Department
EN Department
TE Department
Unit of the Accelerator and Technology (A&T) sector
Staffed by persons working on main projects or studies such as HL-LHC, FCC, CLIC and EU Activities.
No hierarchical functions within the departments of the A&T sector.
Project and Study leaders report directly to the Director for Accelerators and Technology.
Source
https://espace.cern.ch/acc-tec-sector/mandate.aspx

## Slide 6: EVM Guidelines
Organization
(5 criteria)
Planning / Schedule / budgeting
(10 criteria)
EVM Analysis / Reports
(6 criteria)
Revision / data maintenance
(5 criteria)
Accounting Considerations
(6 criteria)
EIA – 748 Standard for Earned Value Management
(32 criteria)
BAC
(BAC) Budget at completion
Total amount of money originally planned to spend on the project.
(PV) planned value
Approved budget for the work scheduled to be completed by a specif date
(EV) Earned value
Quantification of the “worth”
of the work done to date by Project Engineers
Reporting Progress
(AC) Actual Cost
Costs Actually incurred
for the work completed
by a specific date
Accouting System
$

## Slide 7: EVM Guidelines Analyzes and Management reports
EV < PV | EV = PV | EV > PV
(-) SV | (0) SV | (+) SV
Behind | On | Ahead
Am I spending more than I expected?
?
$
Am I on schedule?
?
CHF
Time
Baseline
EAC
EV
SV
CV
EV < AC | EV = AC | EV > AC
(-) CV | (0) CV | (+) CV
Over | On | Under
SV – Schedule variance
CV – Cost variance
AC – Actual cost
PV – Planned value
BAC – Budget at Completion
AC
BAC
PV

## Slide 8: EVM & Planned value evolution since 2016 950 MCHF (Material)
HL-LHC has passed the cap of 180 MCHF in expenditure >350 MCHF in commitment.

## Slide 9: EVM in the context of the HL-LHC project Providing input to
WP management process
Project Steering Meetings
HL-LHC Project C&S Reviews
Financial Reporting to CERN Committees
Project Reporting to CERN Committees
In general weekly
Technical updates
WP Progress monitoring
In general 3x a year
WP Progress monitoring
C&S Update
Savings/Loss monitoring
Every 18 months
Project Progress reporting
C&S Update
Savings/Loss reporting
Baseline changes proposal
Committees every 3 months
Project Progress reporting
C&S Update
Baseline changes reporting

## Slide 10: Training
PMI Project Management course
2 French courses
AXEL course

## Slide 11: Thank you!